## Sheet1
Module site | Module Type | Modules to make | Spines required | Spines Delivered | % delivered | pre-qual & | Usable spines for | usable % | unassembled | assembled | Produced | total trashed | % produced | CERN | unknown | total
|  |  | 1 |  |  | mechanical, trashed | real modules | of required |  |  | (arrived at cern) |  | (produced-mechanical/required) |  | ie in transit
Manchester | outer | 245 | 245 | 209 | 0.85306 | 20 | 189 | 0.77143 | 10 | 199
| middle | 288 | 288 | 54 | 0.1875 | 11 | 43 | 0.14931 | 18 | 36
| inner | 84 | 84 | 0 | 0 |  | 0 | 0 | 0 | 0
Valencia | outer | 120 | 120 | 26 | 0.21667 | 5 | 21 | 0.175 | 16 | 2
| middle | 194 | 194 | 123 | 0.63402 | 22 | 101 | 0.52062 | 13 | 89
Geneva | outer | 565 | 565 | 217 | 0.38407 | 12 | 205 | 0.36283 | 33 | 179
Mel | outer | 191 | 191 | 18 | 0.094241 | 8 | 10 | 0.052356 | 4 | 7
NIKHEF | inner | 171 | 171 | 84 | 0.49123 | 5 | 79 | 0.46199 | 19 | 62
Freib. | inner | 226 | 226 | 72 | 0.31858 | 23 | 49 | 0.21681 | 41 | 20
MPI | middle | 288 | 288 | 105 | 0.36458 |  | 105 | 0.36458 | 65 | 40
| inner | 481 | 481 | 156 | 0.32432 | 28 | 128 | 0.26611 | 60 | 82 | 217 | 15 | 0.39293 | 41 | 35 | 232
| middle | 770 | 770 | 282 | 0.36623 | 33 | 249 | 0.32338 | 96 | 165 | 284 | 21 | 0.32597 | 11 | 2 | 295
| outer | 1121 | 1121 | 470 | 0.41927 | 45 | 425 | 0.37913 | 63 | 387 | 513 | 23 | 0.41748 | 67 | 8 | 545
| all types | 2372 | 2372 | 908 | 0.3828 | 106 | 802 | 0.33811 | 219 | 634 | 1014 | 59 | 0.3828 | 119 | 45 | 1072
0.3828

## Sheet2
SITE | Type of module | type | number required | number of modules | number of ATLAS spec | number of pass modules | pre-qual & | number of spines | shipped since | ratio of modules made/spines at site
| to make |  | to make | made to date (inc pre qual) | modules made to date | made to date | mechanical, trashed | at location to date | 2004-02-20
Manchester | outer | fmModuleOutK5 | 245 | 209 | 189 | 67 | 20 | 209 | 142 | 1
| middle | fmModuleMidLK5 | 288 | 16 | 5 | 0 | 11 | 54 | 59 | 0.2963
| inner | fmModuleInnK5 | 84 | 0 |  |  |  | 0 | 0 | #DIV/0!
Valencia | outer | fmModuleOutK5 | 120 | 7 | 2 |  | 5 | 26 | 21 | 0.26923
| middle | fmModuleMidLK5 | 194 | 88 | 87 | 75 | 1 | 123 | 84 | 0.71545
Geneva | outer | fmModuleOutK5 | 565 | 176 | 164 | 153 | 12 | 217 | 149 | 0.81106
Melbourne | outer | fmModuleOutK5 | 191 | 8 | 0 | 0 | 8 | 18 | 9 | 0.44444
NIKHEF | inner | fmModuleInnK5 | 171 | 63 | 58 | 0 | 5 | 84 | 74 | 0.75
Freiburg | inner | fmModuleInnK5 | 226 | 22 | 10 | 5 | 12 | 72 | 76 | 0.30556
MPI | middle | fmModuleMidSK5 | 288 | 55 |  | 1 |  | 105 | 53 | 0.52381
|  | inner | 481 | 85 | 68 | 5 |  | 156 | 150
|  | middle | 770 | 159 | 92 | 76 |  | 282 | 196
|  | outer | 1121 | 400 | 355 | 220 |  | 470 | 321
|  | all types | 2372 | 644 | 515 | 301 |  | 908 | 667
|  | % |  | 0.2715 | 0.21712 | 0.1269
question: when did real modules start?
question: give me the numbers of spines that were shipped before 20/02/2004.
number of ATLAS spec modules made to date = not including pre-qual and prototype modules
number of pass modules made to date = from database has figures of modules as passed. If not tested wont have passed
geneva = 12 modules that are either pre-seriers (4 modules) or not production modules
manchester | first module = M-O-042
| pre-qual = | 1
| mechanical = | 19
| qual = | 10
| in dB trashed = | 20
(=pre-qual+mechanical)
I would like to have an update at the next SG on the spine production on
Tues 8th. Ideally what I would like is a project plan showing the number
of spines of each type and their status i.e. how many have been produced,
how many accepted and where they are. Do you think you could do this?
Do you have or could you produce a summary table showing the number of
spines required for each assembly site (7 for each type) and the number
shipped

## Sheet4
total shipped since 20/02/2004 |  |  | Average RATE
spines/month
inner | 150 |  | 32.1429
middle | 196 |  | 42
outer | 321 |  | 68.7857
Total | 667 |  | 142.9286
To whom | Type | Shipped | Spine Rate | Good Spines | Predicted Module rate |  |  | spine rate since
|  | since 20/02/2004 | (per month) | (per month) | (per month) |  |  | 2004-06-09 | Good | Yeild | plotted yeild
Manchester | outer | 142 | 30.4286 | 26.2024 | 52.2 | 4.3452 |  | 47 | 40.4722 | 0.86111 | 86.1111
| middle | 59 | 12.6429 | 10.8869 | 52.2 |  |  | 59 | 47.2 | 0.8 | 80
| inner | 0 | 0 | 0 | 0 | Good spine yeild= |  | 0 | 0 |  | 0
Valencia | outer | 21 | 4.5 | 3.375 | 26.1 | 0.80376 |  | 21 | 16.8 | 0.8 | 80
| middle | 84 | 18 | 13.5 | 26.1 |  |  | 39 | 29.25 | 0.75 | 75
Geneva | outer | 149 | 31.9286 | 27.6863 | 34.8 |  |  | 57 | 49.4266 | 0.86713 | 86.7133
Melbourne | outer | 9 | 1.9286 | 1.6723 | 0 |  |  | 8 | 0 |  | 0
NIKHEF | inner | 74 | 15.8571 | 12.7453 | 13.05 |  |  | 43 | 34.5616 | 0.80376 | 80.3759
Freiburg | inner | 76 | 16.2857 | 12 | 21.75 |  |  | 39 | 28.7368 | 0.73684 | 73.6842
MPI | middle | 53 | 11.3571 | 9.1284 | 26.1 |  |  | 21 | 16.8789 | 0.80376 | 80.3759
Total
| outer | 300
| middle | 196
| inner | 150
| all types | 667
One month ago |  | 2004-06-09 | 38147
Start date |  | 2004-02-20 | 38037
Today |  | 2004-07-09 | 38177
Days past |  | 140
30
Number of modules made and spines at assembly sites from DataBase
Modules made |  | type | Made since | Module Rate | Made in | Spines | Spines | Trashed | Total made | Trashed | Made inc
|  |  | 2004-02-20 | (mod/month) | last month | unassembled | Assembled | Spines | (since 1999) | modules | trashed
Manchester | outer | fmModuleOutK5 | 146 | 31.2857 | 45 | 10 | 199 | 0 | 189 | 20 | 209
| middle | fmModuleMidLK5 | 2 | 0.42857 | 2 | 18 | 36 | 0 | 5 | 11 | 16
| inner |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Valencia | outer | fmModuleOutK5 | 0 | 0 | 0 | 16 | 2 | 8 | 5 | 2 | 7
| middle | fmModuleMidLK5 | 60 | 12.8571 | 30 | 13 | 89 | 21 | 87 | 1 | 88
Geneva | outer | fmModuleOutK5 | 114 | 24.4286 | 35 | 33 | 179 | 5 | 176 | 0 | 176
Melbourne | outer | fmModuleOutK5 | 0 | 0 | 0 | 4 | 7 | 7 | 8 | 0 | 8
NIKHEF | inner | fmModuleInnK5 | 33 | 7.0714 | 15 | 19 | 62 | 3 | 58 | 5 | 63
Freiburg | inner | fmModuleInnK5 | 15 | 3.2143 | 5 | 41 | 20 | 11 | 22 | 0 | 22
MPI | middle | fmModuleMidSK5 | 46 | 9.8571 | 20 | 65 | 40 | 0 | 51 | 4 | 55
Month | till Feb22nd | February (last week) | March | April | May | June | July | August | September | October | November | Total
Outer | 162 | 32 | 42 | 114 | 75 | 58 | 0 | 0 | 0 | 0 | 0 | 321
Middle | 68 | 0 | 31 | 38 | 25 | 67 | 35 | 0 | 0 | 0 | 0 | 196
Inner | 52 | 9 | 40 | 19 | 23 | 36 | 23 | 0 | 0 | 0 | 0 | 150
Total | 282 | 41 | 113 | 171 | 123 | 161 | 58 | 0 | 0 | 0 | 0 | 667
Cumative total | 282 | 323 | 436 | 607 | 730 | 891 | 949 | 949 | 949 | 949 | 949
Cumative Outer | 162 | 194 | 236 | 350 | 425 | 483 | 483 | 483 | 483 | 483 | 483
Cumative Middle | 68 | 68 | 99 | 137 | 162 | 229 | 264 | 264 | 264 | 264 | 264
Cumative Inner | 52 | 61 | 101 | 120 | 143 | 179 | 202 | 202 | 202 | 202 | 202

## Sheet5
date | shipped to whom | number shipped | type | returns | okay for dummy modules | yeild | average | number of returns | Insitute | Yeild
[7 empty] | yield | serial number | Geneva | 0.86713 | 143 | 19
[7 empty] | 0.80376 |  | Manchester | 0.86111
[9 empty] | Valencia | 0.75 | 36 | 9
[9 empty] | Freiburg | 0.73684 |  | 20
2003-12-03 | Geneva | 27 | outer | 9 |  | 0.66667 |  |  | Manchester middle | 0.8
2004-02-23 | Geneva | 18 | outer | 0 |  | 1
2004-03-01 | Geneva | 20 | outer | 2 | 0 | 0.9 |  | 363 | 374
[8 empty] | 20220990290539 | 20220990290550
2004-04-28 | Valencia | 6 | middle | 4 |  | 0.33333 |  | 135 | 167 | 159 | 166
total upto | [7 empty] | 20220990290576 | 20220990290608 | 20220990290600 | 20220990290607
2004-05-10 | Manchester | 180 | outer | 25 |  | 0.86111 |  | 338 | 323 | 311 | 275 | 259 | 204 | 255 | 194 | 187 | 185 | 183 | 179 | 178 | 177 | 173 | 171 | 156 | 69 | 90 | 102 | 119 | 123 | 81 | 399 | 417
[8 empty] | 20220990290514 | 20220990290499 | 20220990290487 | 20220990290787 | 20220990288511 | 20220990288331 | 20220990288355 | 20220990288269 | 20220990288273 | 20220990288252 | 20220990288250 | 20220990288247 | 20220990288246 | 20220990288245 | 20220990288431 | 20220990288429 | 20220990284589 | 20220990130142 | 20220990235889 | 20220990158085 | 20220990158095 | 20220990158083 | 20220990158005 | 20220990291167 | 20220990291038
2004-05-04 | Valencia | 28 | middle | 3 | 3 | 0.89286 |  | 114 | 180 | 204
[8 empty] | 20220990290425 | 20220990290938 | 20220990290967
2004-03-29 | Geneva | 32 | outer | 1 | 0 | 0.96875 |  | 145
20220990290825
2004-04-25 | Geneva | 12 | outer | 2 | 0 | 0.83333 |  | 391 | 390
[8 empty] | 20220990290790 | 20220990290789
2004-04-29 | Geneva | 9 | outer | 2 | 0 | 0.77778 |  | 489 | 490
[8 empty] | 20220990290987 | 20220990290988
2004-06-11 | Geneva | 5 | outer | 3 | 0 | 0.4 |  | 495 | 549 | 440
[8 empty] | 20220080000067 | 20220080000099 | 20220990291056
2004-05-10 | Geneva | 20 | outer | 0 |  | 1
2004-06-29 | Freiburg | 0 | inner | 8 | 2 | #DIV/0! |  | 131 | 135 | 10 | 170 | 74 | 83 | 68 | 62 | plus two for dummies
| Valencia | 2 | middle | 2 |  | 0 |  | 193 | 234
[8 empty] | 20220990290956 | 20220080000041
| Freiburg | 0 |  | 4 |  | #DIV/0! |  | 10 | 22 | 116 | 160
[8 empty] | 20220990032349 | 20220990107573 | 20220990288276 | 20220990290844
2004-03-23 | Freiburg | 0 |  | 8 |  |  |  | 10 | 28 | 22 | 62 | 80 | 82 | 88 | 93
[8 empty] | 20220990032349 | 20220990107555 | 20220990107573 | 20220990232739 | 20220990232756 | 20220990232758 | 20220990232763 | 20220990232767
2004-07-06 | NIKHEF |  |  | 1 |  |  |  | 121
20220990290612
2004-07-06 | Manchester |  | middle | 3 |  |  |  | 167 | 217 | 218
[8 empty] | 20220990290608 | 20220080000024 | 20220080000025