## istc
ISTC series | 27.10.2003 |  | 2003-11-28 |  | 2003-12-09 |  | 2003-12-23 |  | 2004-01-15 |  | 2004-01-26 |  | 2004-02-04 |  | 2004-02-09 |  | 2004-02-16 |  | 2004-02-20 |  | 2004-02-27 |  | 9.03.2004 |  | 15.03.2004 |  | 24.03.2004 |  | 26.03.2004 |  | 2.04.2004 |  | 2004-04-15 |  | 2004-04-20 |  | 2004-04-26 |  | 2004-05-05 |  | 2004-05-12 |  | 2004-05-17 |  | 2004-05-19 |  | 2004-05-26 |  | 2004-05-31 |  | 2004-06-15 |  | 2004-06-21 |  | 2004-06-29 |  | 2004-06-30 |  | 2004-07-05 |  | 2004-07-21 |  | 2004-07-30 |  | 2004-08-04 |  | 2004-08-31 |  | 2004-09-15 |  | 2004-09-27 |  | 2004-10-10 |  | 2004-10-20 |  | 2004-11-30
current status of the
Spine production since: | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
TPG ELEMENTS
OUTER
TPG raw (in NIIGraphite)
TPG raw (in NIITAP) | [8 empty] | 250 | 100 | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
TPG cut (in NIITAP) | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40
TPG polished (in NIITAP) | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40
TPG coating (in NIITAP) |  |  | 70 | 70 | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ? | 70 | ?
TPG opening window |  |  |  |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70
TPG elements ready (in NIITAP) |  |  |  |  | 70 | 70 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 0 | 70 | 38 | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70
TPG elements ready (in IHEP) | [7 empty] | 32 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 70 | 38 | 108 | 0 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38 | 108 | 38
MIDDLE
TPG raw (in NIIGraphite)
TPG raw (in NIITAP) | [8 empty] | 210 | 110 | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210
TPG cut (in NIITAP) | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30
TPG polished (in NIITAP) | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30
TPG coating (in NIITAP) |  |  | 60 | 60 | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ? | 60 | ?
TPG opening window |  |  |  |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60
TPG elements ready (in NIITAP) |  |  |  |  | 60 | 60 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5
TPG elements ready (in IHEP) | [7 empty] | 55 | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55
INNER
TPG raw (in NIIGraphite)
TPG raw (in NIITAP) | [8 empty] | 200 | 150 | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210
TPG cut (in NIITAP) | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25
TPG polished (in NIITAP) | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25
TPG coating (in NIITAP) |  |  | 35 | 35 | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ? | 35 | ?
TPG opening window |  |  |  |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35
TPG elements ready (in NIITAP) |  |  |  |  | 35 | 35 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35
TPG elements ready (in IHEP) | [7 empty] | 34 | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 41 | 7 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0 | 48 | 0
CERAMIC ELEMENTS
AlN#2 (in NIITAP)
AlN#2 (in IHEP) | [7 empty] | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
AlN#3 (in NIITAP) | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800
AlN#3 (in IHEP) | [7 empty] | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
AlN#4 (in NIITAP) INNER,MIDDLE
AlN#4 (in IHEP) INNER,MIDDLE | [7 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157
AlN#4 (in NIITAP) OUTER
AlN#4 (in IHEP) OUTER | [7 empty] | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
AlN#5 (in NIITAP) INNER | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450
AlN#5 (in IHEP) INNER | [7 empty] | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134 |  | 134
AlN#5 (in NIITAP) MIDDLE | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540
AlN#5 (in IHEP) MIDDLE | [7 empty] | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
AlN#5 (in NIITAP) OUTER | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700
AlN#5 (in IHEP) OUTER | [7 empty] | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
AlN#7 (in NIITAP) | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150
AlN#7 (in IHEP) | [7 empty] | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180 |  | 180
AlN#8 (in NIITAP) | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800
AlN#8 (in IHEP) | [7 empty] | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
Al2 O3 Spacer (in NIITAP) | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340
Al2 O3 Spacer (in IHEP) | [7 empty] | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257 |  | 257+257
SPINES
Assembling spines (IHEP) outer | 0 |  | 0 |  |  |  |  | 32 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 38 |  | 0 |  | 38 |  | 38 |  | 56 |  | 52 |  | 38 |  | 22+45 |  | 22+45 |  | 22+45 |  | 13+45 |  | 45 |  | 59 |  | 59 |  | 77 |  | 46 |  | 42 |  | 56 |  | 56 |  | 18 |  | 3 |  | 73 |  | 73 |  | 73 |  | 73
Assembling spines (IHEP) middle | 0 |  | 0 |  |  |  |  | 55 |  | 25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 74 |  | 58 |  | 50 |  | 40+30 |  | 21+30 |  | 16+30 |  | 1+30 |  | 30 |  | 50 |  | 29 |  | 52 |  | 45 |  | 37 |  | 70 |  | 70 |  | 7 |  | 7 | [9 empty] | 8 |  | 8
Assembling spines (IHEP) inner | 0 |  | 0 |  |  |  |  | 34 |  | 34 |  | 22 |  | 12 |  | 10 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7 |  | 0 |  | 0 |  | 0 |  | 62 |  | 62 |  | 48 |  | 48+10 |  | 29+10 |  | 29+10 |  | 0 |  | 0 |  | 28 |  | 28 |  | 81 |  | 64 |  | 58 |  | 86 |  | 86 |  | 11 |  | 3 |  | 32 |  | 32 |  | 32 |  | 32 |  | 54 |  | 54
Assembled spines (IHEP) outer | 0 |  | 0 | [5 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 70 | 38 | 70 | 38 | 70 | 33 | 114 | 0 | 118 | 0 | 132 | 10 | 148 | 18 | 148 | 18 | 148 | 9 | 157 | 13 | 157 | 3 | 215 | 35 | 215 | 2 | 225 | 12 | 256 | 43 | 260 | 47 | 274 | 61 | 274 | 7 | 300 | 26 | 309 | 38 | 368 | 1 | 437 | 65 | 485 |  | 485 |  | 559 | 74 | 559 | 74
Assembled spines (IHEP)middle | 0 |  | 0 | [5 empty] | 30 | 20 | 55 | 45 | 55 | 45 | 55 | 33 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 77 | 0 | 93 | 0 | 101 | 7 | 111 | 13 | 130 | 13 | 136 | 0 | 151 | 0 | 151 | 0 | 180 | 12 | 201 | 0 | 216 | 2 | 223 | 9 | 231 | 3 | 241 | 13 | 256 | 6 | 270 | 14 | 277 | 3 | 350 | 20 | 361 | 21 | 362 |  | 372 |  | 440 | 68 | 491 | 68
Assembled spines (IHEP)inner | 0 |  | 0 | [7 empty] | 12 | 12 | 22 | 22 | 24 | 22 | 34 | 14 | 34 | 8 | 34 | 5 | 34 | 0 | 34 | 0 | 41 | 7 | 41 | 7 | 41 | 1 | 50 | 0 | 50 | 0 | 64 | 1 | 64 | 1 | 83 | 20 | 83 | 19 | 113 | 26+10 | 115 | 0 | 125 | 6 | 129 | 4 | 129 | 4 | 145 | 20 | 151 | 26 | 162 | 37 | 177 | 5 | 199 | 27 | 205 | 32 | 206 |  | 237 | 31 | 256 |  | 256 |  | 257 | 1 | 324 | 1
Shipped to CERN outer | 0 |  | 0 | [13 empty] | 32 | by ISTC: 32 | 32 |  | 32 |  | 32 |  | 32 |  | 32 |  | 32 |  | 37 | 5(by courier) | 114 | 77(by ISTC) | 118 | 4(by courier) | 122 | 4(by courier) | 130 | 8(by courier) | 130 |  | 139 | 9(by courier) | 144 | 5(by courier) | 167 | 23(by istc) | 180 | 13(by couirer) | 213 | 33(by istc) | 213 |  | 213 |  | 213 |  | 213 |  | 267 | 54 | 268 | 1 | 271 | 3 | 367 | 96 | 372 | 5 | 485 | 113 | 485 |  | 485 |  | 721 | 236
Shipped to CERN middle | 0 |  | 0 | [6 empty] | 10 | 10 |  | 10 |  | 22 | 12 | 55 | by ISTC: 33 | 55 |  | 56 | by "courier":1(#143) | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 77 | 21(by courier) | 93 | 16(by courier) | 94 | 1(by courier) | 98 | 4(by courier) | 117 | 19(by courier) | 136 | 19(by courier) | 151 | 15(by courier) | 152 | 1(by istc) | 168 | 16(by couirer) | 201 | 33(by istc) | 214 | 13(by couirer) | 214 |  | 228 | 14(by couirer) | 228 |  | 250 | 22 | 263 | 13 | 274 | 11 | 330 | 56 | 340 | 10 | 362 | 22 | 372 | 10 | 372 |  | 491 | 119
Shipped to CERN inner | 0 |  | 0 | [11 empty] | 2 | 2 | 20 | by "courier": 18 | 26 | by "courier": 6+1(see "repair) | 29 | by "courier": 3+4(see "repair) | 38 | by "courier" 5+4(see "repair) | 38 |  | 38 |  | 38 |  | 44 | 6(by couirier) | 50 | 6(by ISTC) | 50 |  | 63 | 13(by courier) | 63 |  | 63 |  | 64 | 1(by courier) | 77 | 13(by courier) | 115 | 38(by istc) | 119 | 4(by couirer) | 121 | 2(by istc) | 121 |  | 121 |  | 121 |  | 121 |  | 172 | 51 | 172 | 0 | 173 | 1 | 206 | 33 | 206 | 0 | 256 | 50 | 256 |  | 256 |  | 324 | 68

## ISTC_q1_is done
ISTC series | 27.10.2003 |  | 2003-11-28 |  | 2003-12-09 |  | 2003-12-23 |  | 2004-01-15 |  | 2004-01-26 |  | 2004-02-04 |  | 2004-02-09 |  | 2004-02-16 |  | 2004-02-20 |  | 2004-02-27 |  | 9.03.2004 |  | 15.03.2004 |  | 24.03.2004 |  | 26.03.2004 |  | 2.04.2004 |  | 15.04.2004
current status of the
Spine production since: | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
QUARTER 1
Shipping of series (171 spines, Quarter 1) is done 15.04.04
TPG ELEMENTS
OUTER
TPG raw (in NIIGraphite)
TPG raw (in NIITAP) | [8 empty] | 250 | 100 | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
TPG cut (in NIITAP) | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40
TPG polished (in NIITAP) | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40 | 110 | 40
TPG coating (in NIITAP) |  |  | 70 | 70 | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 | ?
TPG opening window |  |  |  |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70
TPG elements ready (in NIITAP) |  |  |  |  | 70 | 70 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 38 | 70 | 0 | 70 | 38
TPG elements ready (in IHEP) | [7 empty] | 32 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 70 | 38 | 108 | 0 | 70 |  | 70 |  | 70
MIDDLE
TPG raw (in NIIGraphite)
TPG raw (in NIITAP) | [8 empty] | 210 | 110 | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210
TPG cut (in NIITAP) | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30
TPG polished (in NIITAP) | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30 | 90 | 30
TPG coating (in NIITAP) |  |  | 60 | 60 | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 | ?
TPG opening window |  |  |  |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60 |  | 60
TPG elements ready (in NIITAP) |  |  |  |  | 60 | 60 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5 | 60 | 5
TPG elements ready (in IHEP) | [7 empty] | 55 | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 55 |  | 56 |  | 56 |  | 56
INNER | [28 empty] | Shipping of series (171 spines, Quarter 1) is done 15.04.04
TPG raw (in NIIGraphite)
TPG raw (in NIITAP) | [8 empty] | 200 | 150 | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210 |  | 210
TPG cut (in NIITAP) | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25
TPG polished (in NIITAP) | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25 | 65 | 25
TPG coating (in NIITAP) |  |  | 35 | 35 | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 | ?
TPG opening window |  |  |  |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35 |  | 35
TPG elements ready (in NIITAP) |  |  |  |  | 35 | 35 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 | 1 | 35 |  | 35
TPG elements ready (in IHEP) | [7 empty] | 34 | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 34 |  | 41 | 7 | 48 | 0 | 45 |  | 45 |  | 45
CERAMIC ELEMENTS
AlN#2 (in NIITAP)
AlN#2 (in IHEP) | [7 empty] | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 90 |  | 90 | 171 |  | 171 |  | 171
AlN#3 (in NIITAP) | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800
AlN#3 (in IHEP) | [7 empty] | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 90 |  | 90 | 171 |  | 171 |  | 171
AlN#4 (in NIITAP) INNER,MIDDLE
AlN#4 (in IHEP) INNER,MIDDLE | [7 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 157 |  | 157 | 101 |  | 101 |  | 101
AlN#4 (in NIITAP) OUTER
AlN#4 (in IHEP) OUTER | [7 empty] | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 70 |  | 90 |  | 90 | 70 |  | 70 |  | 70
AlN#5 (in NIITAP) INNER | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450 |  | 450
AlN#5 (in IHEP) INNER | [7 empty] | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 80 |  | 134 |  | 134 | 45 |  | 45 |  | 45
AlN#5 (in NIITAP) MIDDLE | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540 |  | 540
AlN#5 (in IHEP) MIDDLE | [7 empty] | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 90 |  | 90 | 56 |  | 56 |  | 56
AlN#5 (in NIITAP) OUTER | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700 |  | 700
AlN#5 (in IHEP) OUTER | [7 empty] | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 90 |  | 90 | 70 |  | 70 |  | 70
AlN#7 (in NIITAP) | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150 |  | 1150
AlN#7 (in IHEP) | [7 empty] | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 260 |  | 180 |  | 180 | 250 |  | 250 |  | 250
AlN#8 (in NIITAP) | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800
AlN#8 (in IHEP) | [7 empty] | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 170 |  | 90 |  | 90 | 171 |  | 171 |  | 171
Al2 O3 Spacer (in NIITAP) | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340
Al2 O3 Spacer (in IHEP) | [7 empty] | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 340 |  | 257+257 |  |  | 342 |  | 342 |  | 342
SPINES | [28 empty] | Shipping of series (171 spines, Quarter 1) is done 15.04.04
By ISTC:AWB # 724-42687315 Swiss International, flight # LX1335 on April 24th to Geneva Airport
Assembling spines (IHEP) outer | 0 |  | 0 |  |  |  |  | 32 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 38 |  | 0 |  | 0 |  | 0 |  | 0
Assembling spines (IHEP) middle | 0 |  | 0 |  |  |  |  | 55 |  | 25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Assembling spines (IHEP) inner | 0 |  | 0 |  |  |  |  | 34 |  | 34 |  | 22 |  | 12 |  | 10 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7 |  | 0 |  | 0 |  | 0 |  | 0
[32 empty] | ASSEMBLING of this series (171 spines) IS FINISHED at 24.03.04 |  | ASSEMBLING of this series (171 spines) IS FINISHED at 24.03.04
Assembled spines (IHEP) outer | 0 |  | 0 | [5 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 70 | 38 | 70 | 38 | 70 | 33 | 70 | 0
Assembled spines (IHEP)middle | 0 |  | 0 | [5 empty] | 30 | 20 | 55 | 45 | 55 | 45 | 55 | 33 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0 | 55 | 0
Assembled spines (IHEP)inner | 0 |  | 0 | [7 empty] | 12 | 12 | 22 | 22 | 24 | 22 | 34 | 14 | 34 | 8 | 34 | 5 | 34 | 0 | 34 | 0 | 41 | 7 | 41 | 7 | 41 | 1 | 41 | 0
Shipped to CERN outer | 0 |  | 0 | [13 empty] | 32 | by ISTC: 32 | 32 |  | 32 |  | 32 |  | 32 |  | 32 |  | 32 |  | 37 | 5(by courier) | 70 | 33(ISTC)
Shipped to CERN middle | 0 |  | 0 | [6 empty] | 10 | 10 |  | 10 |  | 22 | 12 | 55 | by ISTC: 33 | 55 |  | 56 | by "courier":1(#143) | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 56
Shipped to CERN inner | 0 |  | 0 | [11 empty] | 2 | 2 | 20 | by "courier": 18 | 26 | by "courier": 6+1(see "repair) | 29 | by "courier": 3+4(see "repair) | 38 | by "courier" 5+4(see "repair) | 38 |  | 38 |  | 38 |  | 44 | 6(by couirier) | 45 | 1 (istc)
current status of assembling continued at ISTC_quarter2 since 1.04.04
componets manufacturing see at at ISTC_quarter3 since 1.04.04
Shipping of series (171 spines, Quarter 1) is done 15.04.04
AWB # 724-42687315 Swiss International, flight # LX1335 on April 24th to Geneva Airport

## ISTS_q2_is done
ISTC series | 26.03.2004 |  | 5.04.2004 |  | 6.04.2004 |  | 12.04.2004 |  | 15.04.2004 |  | 20.04.2004 |  | 26.04.2004 |  | 5.05.2004 |  | 12.05.2004 |  | 17.05.2004 |  | 19.05.2004 |  | 26.05.2004 |  | 31.05.2004
current status of the
Spine production since: | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
quarter 2
(SERIES 257)
TPG ELEMENTS
OUTER
TPG raw (in NIIGraphite)
TPG raw (in NIITAP)
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP) | 62 |  | 62
TPG elements ready (in IHEP) | 38 | 38 | 38 |  | 100 | 62 | 100 | 62 | 100 | 56 | 100 | 52 | 100 | 37 | 100 | 22 | 100 | 22 | 100 | 22 | 100 | 13 | 100 | 0 is done | 100 | 0 is done
MIDDLE
TPG raw (in NIIGraphite)
TPG raw (in NIITAP)
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP) | 90 |  | 90
TPG elements ready (in IHEP) |  |  |  |  | 95 | 95 | 95 | 95 | 95 | 74 | 95 | 58 | 95 | 50 | 95 | 40 | 95 | 21 | 95 | 15 | 95 is done | 0 | 95 is done | 0 | 95 is done | 0
INNER
TPG raw (in NIIGraphite)
TPG raw (in NIITAP)
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP) | 67 |  | 67 |  | 67
TPG elements ready (in IHEP) | [6 empty] | 67 | 67 | 67 | 62 | 67 | 62 | 67 | 48 | 67 | 48 | 67 | 29 | 67 | 29 | 67 is done | 0 | 67 is done | 0 | 67 is done | 0
CERAMIC ELEMENTS | ALL CERAMICS ARE IN IHEP
AlN#2 (in NIITAP) | A
AlN#2 (in IHEP) | L |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257
AlN#3 (in NIITAP) | L
AlN#3 (in IHEP) |  |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257
AlN#4 (in NIITAP) INNER,MIDDLE | C
AlN#4 (in IHEP) INNER,MIDDLE | E |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157 |  | 157
AlN#4 (in NIITAP) OUTER | R
AlN#4 (in IHEP) OUTER | A |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
AlN#5 (in NIITAP) INNER | M
AlN#5 (in IHEP) INNER | I |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67 |  | 67
AlN#5 (in NIITAP) MIDDLE | C
AlN#5 (in IHEP) MIDDLE | S |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
AlN#5 (in NIITAP) OUTER
AlN#5 (in IHEP) OUTER | I |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
AlN#7 (in NIITAP) | N
AlN#7 (in IHEP) |  |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380 |  | 380
AlN#8 (in NIITAP) | I
AlN#8 (in IHEP) | H |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257
Al2 O3 Spacer (in NIITAP) | E
Al2 O3 Spacer (in IHEP) | P |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257
Al2 O3 Spacer (in IHEP) metalized |  |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257 |  | 257
SPINES
series 257 is done
Assembling spines (IHEP) outer |  | 38 |  | 36 |  | 18+62=80 |  | 62 |  | 56 |  | 52 |  | 38 |  | 22 |  | 22 |  | 22 |  | 13 |  | 0 |  | 0
Assembling spines (IHEP) middle |  | 0 |  | 0 |  | 95 |  | 95 |  | 74 |  | 58 |  | 50 |  | 40 |  | 21 |  | 15 |  | 0 |  | 0 |  | 0
Assembling spines (IHEP) inner |  | 0 |  | 0 |  | 0 |  | 67 |  | 62 |  | 62 |  | 48 |  | 48 |  | 29 |  | 29 |  | 0 |  | 0 |  | 0
[24 empty] | series 257 is done |  | series 257 is done
Assembled spines (IHEP) outer |  |  | 2 | 2 | 20 | 20 | 38 | 18 | 44 | 0 | 48 | 0 | 62 | 10 | 78 | 18 | 78 | 18 | 78 | 9 | 87 | 13 | 100 | 3 | 100 | 0
Assembled spines (IHEP)middle | [8 empty] | 21 | 0 | 37 | 0 | 45 | 7 | 55 | 13 | 74 | 13 | 80 | 0 | 95 | 0 | 95 | 0 | 95 | 0
Assembled spines (IHEP)inner | [8 empty] | 5 | 0 | 5 | 0 | 19 | 1 | 19 | 1 | 38 | 20 | 38 | 19 | 67 | 26 | 67 | 0 | 67 | 0
series 257 is done
Shipped to CERN outer | [8 empty] | 44 | 44(istc) | 48 | 4(by courier) | 52 | 4(by courier) | 60 | 8(by courier) | 60 |  | 69 | 9(by courier) | 74 | 5(by courier) | 74+23=97 | 23(by ISTC) | 97+3=100 | 3(by courier)
Shipped to CERN middle | [8 empty] | 21 | 21(by courier) | 37 | 16(by courier) | 38 | 1(by courier) | 42 | 4(by courier) | 61 | 19(by courier) | 80 | 19(by courier) | 95 | 15(by courier) | 95 |  | 95
Shipped to CERN inner | [8 empty] | 5 | 5(istc) | 5 |  | 18 | 13(by courier) | 18 |  | 18 |  | 19 | 1(by courier) | 32 | 13(by courier) | 32+35=67 | 35(by istc) | 67
Shipping of series (263 spines, Quarter 2) is done 30.05.04

## ISTS_q3_is done
| 5.04.2004 |  | 12.04.2004 |  | 5.05.2004 |  | 19.05.2004 |  | 26.05.2004 |  | 31.05.2004 |  | 15.06.2004 |  | 21.06.2004 |  | 29.06.2004 |  | 30.06.2004 |  | 5.07.2004 |  | 14.07.2004 |  | 21.07.2004 |  | 4.08.2004
ISTC series | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
current status of the
Spine production started: 1.04.04
Quarter 3
(SERIES 300)
TPG ELEMENTS
in sheets:
TPG raw (in NIIGraphite) O+M+I (total) | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360
TPG raw (in NIITAP) O+M+I (total) | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360
TPG polished (in NIITAP) | 40 | 40 | 40 | 40 | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40 |  | 40
as elements:
OUTER
TPG cut (in NIITAP) |  |  |  | 24
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP) | [5 empty] | 45 |  | 45 | 45 |  | 104 | 0+59 | 104 | 0+59 | 104-1+29 | 0+29 | 104-1+29 | 46 | 104-1+29 | 42 | 160=105+55(see Q4) | 42+27+1 | 160=105+55(see Q4) |  | 160=105+55(see Q4) |  | 160=105+55(see Q4)
MIDDLE
TPG cut (in NIITAP) |  |  |  | 18
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP) | [5 empty] | 30 |  | 30 | 30 | 29 | 80 | 0+50 | 80 | 0+29 | 80-1+38 | 0+38 | 80-1+38 | 45 | 80-1+38 | 37 | 160=100+60(see q4) | 37+42+1 | 160=100+60(see q4) |  | 160=100+60(see q4) |  | 160=100+60(see q4)
INNER
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP) | [5 empty] | 10 |  | 0 | 0 | 0 | 38 | 0+28 | 38 | 0+28 | 38-4+57 | 0+57 | 38-4+57 | 64 | 38-4+57 | 58 | 130=95+35(q4) | 58+35+4 | 130=95+35(q4) |  | 130=95+35(q4) |  | 130=95+35(q4)
CERAMIC ELEMENTS
current status of laser cut full series: |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done
status of treatment, metaliz., profiling: |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done |  | is done
is ready:
AlN#2 (in NIITAP) |  |  | 590 | 590 | 590 | 590 | 590 | 590 | 590 |  | 590 |  | 590 |  | 590 |  | 590 |  | 590 |  | 590 |  | 590 |  | 590 |  | 590
AlN#2 (in IHEP) |  |  |  |  | 85 | 85 | 85 | 85 | 85 | 90 | 140 | 50 | 140 | 50 | 140+124=264 | 124 | 140+124=264 | 124 | 140+124=264 | 124 | 140+124=264 | 124 | 140+124=264 | 124 | 140+124=264 | 124 | 140+124=264 | 124
AlN#3 (in NIITAP) | 24 | 24 | 56 | 32 | 56 | 32 | 56 | 32 | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 56 |  | 56
AlN#3 (in IHEP) |  |  |  |  | 90 | 90 | 90 | 90 | 90+90=180 | 90 | 90+90+50=230 | 50 | 90+90+50=230 | 50 | 90+90+50=230+129=359 | 129 | 90+90+50=230+129=359 | 129 | 90+90+50=230+129=359 | 129 | 90+90+50=230+129=359 | 129 | 90+90+50=230+129=359 | 129 | 90+90+50=230+129=359 | 129 | 90+90+50=230+129=359 | 129
AlN#4 (in NIITAP) INNER,MIDDLE |  |  | 310 | 310 | 310 | 310 | 310 | 310 | 310 |  | 310 |  | 310 |  | 310 |  | 310 |  | 310 |  | 310 |  | 310 |  | 310 |  | 310
AlN#4 (in IHEP) INNER,MIDDLE |  |  |  |  | 40 | 40 | 40 | 40 | 40 |  | 120 | 80 | 120 | 80 | 120+100=220 | 100 | 120+100=220 | 100 | 120+100=220 | 100 | 120+100=220 | 100 | 120+100=220 | 100 | 120+100=220 | 100 | 120+100=220 | 100
AlN#4 (in NIITAP) OUTER |  |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
AlN#4 (in IHEP) OUTER |  |  |  |  | 45 | 45 | 45 | 45 | 45 |  | 105 | 60 | 105 | 60 | 105+30=135 | 30 | 105+30=135 | 30 | 105+30=135 | 30 | 105+30=135 | 30 | 105+30=135 | 30 | 105+30=135 | 30 | 105+30=135 | 30
AlN#5 (in NIITAP) INNER
AlN#5 (in IHEP) INNER |  |  |  |  | 20 | 20 | 20 | 20 | 20+90=110 | 90 | 20+90+60=170 | 60 | 20+90+60=170 | 60 | 20+90+60=170+114=284 | 114 | 20+90+60=170+114=284 | 114 | 20+90+60=170+114=284 | 114 | 20+90+60=170+114=284 | 114 | 20+90+60=170+114=284 | 114 | 20+90+60=170+114=284 | 114 | 20+90+60=170+114=284 | 114
AlN#5 (in NIITAP) MIDDLE | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20
AlN#5 (in IHEP) MIDDLE | [5 empty] | 60 |  | 60 | 60+90=150 | 90 | 60+90+10=160 | 10 | 60+90+10=160 | 10 | 60+90+10=160+88=248 | 88 | 60+90+10=160+88=248 | 88 | 60+90+10=160+88=248 | 88 | 60+90+10=160+88=248 | 88 | 60+90+10=160+88=248 | 88 | 60+90+10=160+88=248 | 88 | 60+90+10=160+88=248 | 88
AlN#5 (in NIITAP) OUTER | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3
AlN#5 (in IHEP) OUTER |  | 48 |  | 48 | 48 | 48 | 48 | 48 | 48 |  | 78 | 30 | 78 | 30 | 78+60=138 | 60 | 78+60=138 | 60 | 78+60=138 | 60 | 78+60=138 | 60 | 78+60=138 | 60 | 78+60=138 | 60 | 78+60=138 | 60
AlN#7 (in NIITAP) |  |  | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200
AlN#7 (in IHEP) |  |  |  |  | 150 | 150 | 150 | 150 | 150 |  | 370 | 220 | 370 | 220 | 370+140=510 | 140 | 370+140=510 | 140 | 370+140=510 | 140 | 370+140=510 | 140 | 370+140=510 | 140 | 370+140=510 | 140 | 370+140=510 | 140
AlN#8 (in NIITAP) | 90 | 90 | 200 | 110 | 200 | 110 | 200 | 110 | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200 |  | 200
AlN#8 (in IHEP) | [5 empty] | 90 |  | 90 | 90+90=180 | 90 | 90+90+50=230 | 50 | 90+90+50=230 | 50 | 90+90+50=230+122=352 | 122 | 90+90+50=230+122=352 | 122 | 90+90+50=230+122=352 | 122 | 90+90+50=230+122=352 | 122 | 90+90+50=230+122=352 | 122 | 90+90+50=230+122=352 | 122 | 90+90+50=230+122=352 | 122
Al2 O3 Spacer (in NIITAP) |  |  | 770 | 770 | 770 | 770 | 770 | 770 | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770
Al2 O3 Spacer (in IHEP) |  |  |  |  | 170 | 170 | 170 | 170 | 170 |  | 770 | 600 | 770 | 600 | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770 |  | 770
SPINES
Assembling spines (IHEP) outer | [5 empty] | 45 |  | 45 |  | 45 | 104 | 59 | 104 | 59 | 133-1 | 77 | 133-1 | 46 | 133-1 | 42 | 105 | 1 | 105 | 0 | 105 | 0 | 105 | 0
Assembling spines (IHEP) middle | [5 empty] | 30 |  | 30 |  | 29 | 80 | 50 | 80 | 29 | 118-1 | 52 | 118-1 | 45 | 118-1 | 37 | 100 | 10 | 100 | 0 | 100 | 0 | 100 | 0
Assembling spines (IHEP) inner | [5 empty] | 10 |  | 0 |  | 0 | 38 | 28 | 38 | 28 | 95-4 | 81 | 95-4 | 64 | 95-4 | 58 | 95 | 51 | 95 | 28 | 95 | 0 | 95 | 0
Assembled spines (IHEP) outer | [10 empty] | 45 | 35 | 45 | 2 | 55 | 12 | 86 | 43 | 90 | 47 | 104 | 61 | 105 | 44 | 105 | 0 | 105 | 0
Assembled spines (IHEP)middle | [8 empty] | 1 | 1 | 29 | 12 | 50 | 0 | 65 | 2 | 72 | 9 | 80 | 3 | 90 | 13 | 100 | 0 | 100 | 0 | 100 | 0
Assembled spines (IHEP)inner | [6 empty] | 10 | 10 | 10 | 10 | 10 | 6 | 10 | 4 | 10 | 4 | 27 | 20 | 33 | 26 | 44 | 37 | 67 | 24 | 94 | 1 | 95 | 0
Shipped to CERN outer | [10 empty] | 10 | 10(by couirer) | 43 | 33(by istc) | 43 | 0 | 43 | 0 | 43 | 0 | 43 | 0 | 61 | 18 | 105 | 44 | 105 | 0
Shipped to CERN middle | [8 empty] | 1 | 1(by istc) | 17 | 16(by couirer) | 50 | 33(by istc) | 63 | 13(by couirer) | 63 | 0 | 77 | 14(by couirer) | 77 | 0 | 100 | 23 | 100 | 0 | 100 | 0
Shipped to CERN inner | [8 empty] | 1 | 1(by istc) | 5 | 4(by couirer) | 7 | 2(by istc) | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 43 | 36 | 94 | 51 | 95 | 1
after 5.07 see also sheet "ISTC_Q4"
Shipping Q3 is finished 4.08.2004

## istc_quarter4_is done
| 5.07.2004 |  | 14.07.2004 |  | 21.07.2004 |  | 30.07.2004 |  | 4.08.2004 |  | 31.08.2004 |  | 15.09.2004 |  | 27.09.2004
ISTC series | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
current status of the
Spine production started: 1.07.04
Quarter 4
finished 30.09.2004
(SERIES 300)
TPG ELEMENTS
in sheets:
TPG raw (in NIIGraphite) O+M+I (total) | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360
TPG raw (in NIITAP) O+M+I (total) | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360 |  | 360
as elements:
OUTER
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP) | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 73 | 55 | 73 | 55 | 73
MIDDLE
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP) | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 60 | 0 | 60 | 0
INNER
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP) | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 32 | 35 | 32 | 35 | 32
CERAMIC ELEMENTS
current status of laser cut full series: |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing
status of treatment, metaliz., profiling: |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing |  | is doing
is ready:
AlN#2 (in NIITAP)
AlN#2 (in IHEP) | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101
AlN#3 (in NIITAP)
AlN#3 (in IHEP) | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91
AlN#4 (in NIITAP) INNER,MIDDLE
AlN#4 (in IHEP) INNER,MIDDLE | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
AlN#4 (in NIITAP) OUTER
AlN#4 (in IHEP) OUTER | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
AlN#5 (in NIITAP) INNER
AlN#5 (in IHEP) INNER | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
AlN#5 (in NIITAP) MIDDLE
AlN#5 (in IHEP) MIDDLE | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
AlN#5 (in NIITAP) OUTER
AlN#5 (in IHEP) OUTER | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
AlN#7 (in NIITAP)
AlN#7 (in IHEP) | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
AlN#8 (in NIITAP)
AlN#8 (in IHEP) | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98
Al2 O3 Spacer (in NIITAP)
Al2 O3 Sp. (in IHEP) (with metal.) | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
Al2 O3 Sp. (in IHEP) (without metal.) | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
SPINES
Assembling spines (IHEP) outer | 55 | 55 | 55 | 55 | 55 | 45 | 55 | 18 | 55 | 3 | 111+73=184 | 0+73(31.08) | 111+73=184 | 0+73(31.08) | 111+73=184 | 0+73(31.08)
Assembling spines (IHEP) middle | 60 | 60 | 60 | 56 | 60 | 28 | 60 | 7 | 60 | 7 | 126 | 0+0 | 126 | 0+0 | 126 | 0+0
Assembling spines (IHEP) inner | 35 | 35 | 35 | 35 | 35 | 31 | 35 | 11 | 35 | 3 | 33+32=65 | 0+32(31.08) | 33+32=65 | 0+32(31.08) | 33+32=65 | 0+32(31.08)
Assembled spines (IHEP) outer |  |  |  |  | 10 | 0 | 37 | 26 | 52 | 38 | 111 | 1 | 180 | 65 | 228
Assembled spines (IHEP)middle |  |  | 4 | 4 | 32 | 6 | 53 | 14 | 53 | 3 | 126 | 20 | 137 | 21 | 138
Assembled spines (IHEP)inner |  |  |  |  | 4 | 4 | 24 | 24 | 32 | 32 | 33 | 0 | 64 | 31 | 83
Shipped to CERN outer |  | 0 |  | 0 | 10 | 10 | 11 | 1 | 14 | 3 | 110 | 16+80=96 | 115 | 5 | 228 | 113
Shipped to CERN middle |  | 0 | 4 | 4 | 26 | 22 | 39 | 13 | 50 | 11 | 106 | 51+5=56 | 116 | 10 | 138 | 22
Shipped to CERN inner |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 33 | 0 | 83 | 50
after 27.09 see also sheet "ISTC_Q5"
Shipping Q4 is finished 27.09.2004

## ists_q5
| 10.10.2004 |  | 20.10.2004 |  | 28.10.2004 |  | 30.11.2004
ISTC series | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
current status of the
Spine production started: 1.10.04
Quarter 4
finished:
(SERIES 300)
TPG ELEMENTS
in sheets:
TPG raw (in NIIGraphite) O+M+I (total)
TPG raw (in NIITAP) O+M+I (total)
as elements:
OUTER
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP)
MIDDLE
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP)
INNER
TPG cut (in NIITAP)
TPG polished (in NIITAP)
TPG coating (in NIITAP)
TPG opening window
TPG elements ready (in NIITAP)
TPG elements ready (in IHEP)
CERAMIC ELEMENTS
current status of laser cut full series:
status of treatment, metaliz., profiling:
is ready:
AlN#2 (in NIITAP)
AlN#2 (in IHEP)
AlN#3 (in NIITAP)
AlN#3 (in IHEP)
AlN#4 (in NIITAP) INNER,MIDDLE
AlN#4 (in IHEP) INNER,MIDDLE
AlN#4 (in NIITAP) OUTER
AlN#4 (in IHEP) OUTER
AlN#5 (in NIITAP) INNER
AlN#5 (in IHEP) INNER
AlN#5 (in NIITAP) MIDDLE
AlN#5 (in IHEP) MIDDLE
AlN#5 (in NIITAP) OUTER
AlN#5 (in IHEP) OUTER
AlN#7 (in NIITAP)
AlN#7 (in IHEP)
AlN#8 (in NIITAP)
AlN#8 (in IHEP)
Al2 O3 Spacer (in NIITAP)
Al2 O3 Sp. (in IHEP) (with metal.)
Al2 O3 Sp. (in IHEP) (without metal.)
SPINES
Assembling spines (IHEP) outer
Assembling spines (IHEP) middle |  |  |  | 8
Assembling spines (IHEP) inner |  |  |  | 54
Assembled spines (IHEP) outer |  |  | 74 | 74 | 76 |  | 236
Assembled spines (IHEP)middle |  |  | 78 | 68 | 100 |  | 119
Assembled spines (IHEP)inner |  |  | 1 | 1 | 24 |  | 68
Shipped to CERN outer |  |  |  |  | 76 | 76 | 236 | 150
Shipped to CERN middle | 10 | 10 | 10 |  | 100 | 90 | 119 | 19
Shipped to CERN inner |  |  |  |  | 24 | 24 | 68 | 44

## series229 is done
date: | 27.10.2003 |  | 28.10.2003 |  | 31.10.2003 |  | 10.11.2003 |  | 13.11.2003 |  | 2003-11-28 |  | 2003-12-05 |  | 2003-12-09 |  | 2004-01-06 |  | 2004-01-28 |  | 2004-02-09 |  | 2004-02-16
current status of the | [22 empty] | IS FINISHED
Spine production SERIES 229 | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial | integrated | differencial
TPG ELEMENTS
OUTER
TPG raw (in NIIGraphite) | 250 | 0 | 250 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG raw (in NIITAP) | 250 | 0 | 250 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG cut (in NIITAP) | 230 | 0 | 230 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG polished (in NIITAP) | 230 | 0 | 230 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG coating (in NIITAP) | 185 | 45 | 185 | 45 |  | 45 |  | 45 |  | 45 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG opening window | 185 | 50 | 185 | 50 |  | 33 |  | 33 |  | 33 |  | 39 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG elements ready (in NIITAP) | 185 | 50 | 185 | 50 |  | 0 |  | 0 |  | 0 |  | 0 |  | 39 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
TPG elements ready (in IHEP) | 85 | 37 | 85 | 27 |  | 7+67=74 |  | 7+67=74 |  | 74-15=59 | 190 | 31 | 190 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
[15 empty] | EXTRA series is done |  | EXTRA series is done |  | EXTRA series is done |  | EXTRA series is done |  | EXTRA series is done
rejected (in IHEP) TPG elements,
shipped back to NIITAP | [9 empty] | 15
CERAMIC ELEMENTS
AlN#2 (in NIITAP) | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#2 (in IHEP) | 230 | 182 | 230 | 172 | 230 | 152 | 230 | 108 | 230 | 98 | 230 | 40 | 230 | 90 | 230 | 90 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#3 (in NIITAP) | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#3 (in IHEP) | 230 | 182 | 230 | 172 | 230 | 152 | 230 | 108 | 230 | 73 | 230 | 40-25+25=40 | 230 | 62 | 230 | 62+26=88 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#4 (in NIITAP) OUTER | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#4 (in IHEP) OUTER | 230 | 182 | 230 | 172 | 230 | 152 | 230 | 108 | 230 | 98 | 230 | 40 | 230 | 58 | 230 | 58 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#5 (in NIITAP) OUTER | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0
AlN#5 (in IHEP) OUTER | 460 | 364 | 460 | 344 | 460 | 304 | 460 | 216 | 460 | 145 | 460 | 80-51=29 | 460 | 64 | 460 | 64+28=92 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0
AlN#7 (in NIITAP) | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0
AlN#7 (in IHEP) | 460 | 364 | 460 | 344 | 460 | 304 | 460 | 216 | 460 | 196 | 460 | 80 | 460 | 80 | 460 | 80 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0
AlN#8 (in NIITAP) | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
AlN#8 (in IHEP) | 230 | 182 | 230 | 172 | 230 | 152 | 230 | 108 | 230 | 84 | 230 | 40-14+30=56 | 230 | 71 | 230 | 71+15=86 | 230 | 0 | 230 | 0 | 230 | 0 | 230 | 0
Al2 O3 Spacer (in NIITAP) | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0
Al2 O3 Spacer (in IHEP) | 460 | 364 | 460 | 344 | 460 | 304 | 460 | 216 | 460 | 196 | 460 | 80 | 460 | 80 | 460 | 80 | 460 | 0 | 460 | 0 | 460 | 0 | 460 | 0
[23 empty] | F | F
rejected (in IHEP) ALN elements, | [9 empty] | #3-25 | [12 empty] | I | I
shipped back to NIITAP | [9 empty] | #5-51 | [12 empty] | N | N
[10 empty] | #8-14 | [12 empty] | I | I
SPINES | [22 empty] | S | S
[23 empty] | H | H
Assembling spines (IHEP) outer | 85 | 37 | 85 | 27 | 152 | 74 | 152 | 30 | 152 | 24 | 190 | 31 | 190 | 0 | 230 | 40 | 230 |  | 230 |  | 230 |  | 230
Assembled spines (IHEP) outer | 48 |  | 58 |  | 78 | 20 | 122 | 26 | 122 | 36 | 159 | 18 | 190 | 39 | 190 | 39 | 230 | 70 | 230 | 60 | 230 | 40 | 230 | 0
Shipped to CERN outer | 48 | 13 | 58 | 10 |  |  | 76 | 18 | 86 | 10 | 141 |  | 151 |  | 151 |  | 160 |  | 170 | 10 | 190 | 20 | 230 | 40 | SHIPPED VIA ISTC SINCE 16.02.04
[18 empty] | SERIES 229 is done |  | SERIES 229 is done |  | SERIES 229 is done |  | SERIES 229 is done

## intas (hidden)
date: | 29.10.2003
SHIPPING REST OF INTAS
(AFTER October 1, 2003 only) | integrated | differencial | integrated | differencial | integrated | differencial
rest of INTAS shipped
AFTER October 1, 2003
Shipped to CERN outer (INTAS)
Shipped to CERN middle(INTAS)
Shipped to CERN inner (INTAS) | 3 | 3
The current our dept (INTAS)
outer (INTAS) | 14
middle(INTAS) | 22
inner (INTAS) | 24
REMARKS: all components were ready long time ago, TPG elements still are at recoating by Parylene in NIITAP

## repair
The folow spines were brocked and recived to IHEP for repairation:
the type of spine | date of reciving |  | status of repairation |  | READY NN | date of shipping back to CERN
outer |  |  | 2004-02-06
#254 | 2003-12-11 |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#259 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#245 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#246 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#261 |  |  | TPG is brocked!
#268 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#251 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#275 |  |  | was repaired! |  | 7 | shipped via ISTC 16.02.2004
2004-02-06
outer | 2003-12-20
#168 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#198 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#204 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#205 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#215 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004 | shipping via ISTC repaired:
#262 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004 | At 16.02.0 | outer | 20
#263 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004 | middle |  | 2
#271 |  |  | was repaired! |  |  | shipped via ISTC 16.02.2004 | inner |  | 0
#241 |  |  | was repaired! |  | 9 | shipped via ISTC 16.02.2004
2004-02-06
outer | never were at CERN
#5 | never were at CERN |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#20 | never were at CERN |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#22 | never were at CERN |  | was repaired! |  |  | shipped via ISTC 16.02.2004
#287 | never were at CERN |  | was repaired! |  | 4 | shipped via ISTC 16.02.2004
2004-02-06
inner | never were at CERN
#91 | never were at CERN |  | was repaired!
#111 | never were at CERN |  | was repaired! |  |  | shipped via courier 20.02.2004
#114 | never were at CERN |  | was repaired! |  |  | shipped via courier 1.03.2004
#85 | never were at CERN |  | was repaired! |  |  | shipped via courier 1.03.2004
#68 | never were at CERN |  | was repaired! |  |  | shipped via courier 1.03.2004
#97 | never were at CERN |  | was repaired! |  |  | shipped via courier 1.03.2004
## | never were at CERN |  | was repaired! |  | 7 |  |  |  | At 5.03.04
Nothing for repairing
[7 empty] | outer |  | 0
middle | never were at CERN | [5 empty] | middle |  | 0
#113 | never were at CERN |  | was repaired! |  |  | shipped via ISTC 16.02.2004 | inner |  | 0
#169 | never were at CERN |  | was repaired! |  |  | shipped via ISTC 16.02.2004
2
| at 6.02.04 |  |  |  |  | At 20.02.04
READY for shipping repaired: |  |  |  | READY for shipping repaired:
outer |  | 17 |  | outer |  | 0
middle |  | 2 |  | middle |  | 0
inner |  | 3 |  | inner |  | 6

## current filling
date | before 1.04.04 | after 1.04.04 | apr.2004 | may 2004 | jun 2004 | jul 2004 | aug. 2004 | sep. 2004 | oct.2004 | nov 2004
| inside INTAS, series 229 | produced
| inside 1, 2 quarters of ISTC | inside 1, 2,3 quarters of ISTC |  | ISTC quarter 3 | [5 empty] | ISTC quarter 5
| according to Protvino meeting | das not included into "before…" |  |  |  |  | ISTC quarter 4
MARCH 31.04.2004
INNER |  | at 30.11.04(ready)
needed for module production |  |  | 61 | 44 | 33 | 110 | 44 | 55
done inside ISTC working plan | Intas:95 | (6 sipped by ISTC 15.04)+6+13+1+13+38(shipped by ISTC 26.05)+4+2(istc 15.06)=83+36=121+51=172+1+68=322 | 25 | 56 | 2 | 36+51=87 | 1+33=34 | 50 | 24 | 44
done extra ISTC working plan | ISTC:44
assembled (in Protvino) total
delivered to CERN (total) | 139 | 322 | 25 | 56 | 2 | 87 | 34 | 50 | 24 | 44
MIDDLE |  | at 30.11.04(ready) |  |  | 2
needed for module production |  |  | 140 | 84 | 49 | 66 | 115 | 107
done inside ISTC working plan | 72 | 21(15.04)+16+1+4+10+19(12.05)+19+15+1+16+33+13+14=172+11+16+13=199+22=234+11+5+51+10+22=333+119=452 | 38 | 74 | 60 | 27+22+13=62 | 11+5+51=67 | 10+22=32 | 10+90=100 | 19
done extra ISTC working plan | Intas:95
assembled (in Protvino) total
delivered to CERN (total) | 167 | 452 | 38 | 74 | 60 | 62 | 67 | 32 | 100 | 19
OUTER |  | at 30.11.04(ready) |  |  | 46
needed for module production |  |  | 115 | 126 | 100 | 70 | 77 | 144
done inside ISTC working plan | 54 | 77 (shipped via ISTC 15.04)+5+4+4+8(1.05)+9+5+23+13+33+1=182+3=185=471+150=621 | 90 | 8+9+5+23+13=58 | 33 | 18+54+1=73 | 3+80+16=99 | 5+113=118 | 76 | 150
done extra ISTC working plan | Intas:100+extra 229
assembled (in Protvino) total
delivered to CERN (total) | 382 | 621 | 90 | 58 | 33 | 73 | 99 | 118 | 76 | 150
TOTAL (delivered) | 689 | 153+188=341+95=436+222=658+200+200=1058+413=1471 | 153 | 188 | 95 | 222 | 200 | 200 | 200 | 213
Quarter 3 is finished
Quarter 4 is finished
TOTAL: 1471spines

## shipped components for repair
shipped components for repair (to CERN) |  |  |  | used after 10.03 | 0.1.03.2004 | 2004-03-25 | 2004-04-26 | shipped17.05.2004
date of shipping: | TOTAL shipped | avialable at | avialable at
shipped since: march 2004 |  | CERN at:2.04.04 | CERN at:26.04.04
TPG ELEMENTS
OUTER
TPG elements
MIDDLE
TPG elements
INNER
TPG elements
CERAMIC ELEMENTS
AlN#2 | 27 |  | 0+6+10 | 2 | 9 |  | 6 | 10
AlN#3 | 34 |  | 11+10 | 5 | 19 |  |  | 10
AlN#4 INNER,MIDDLE | 22 |  | 10+10 | 2 | 10 |  |  | 10
AlN#4 OUTER | 24 |  | 6+10 | 2 | 12 |  |  | 10
AlN#5 INNER | 22 |  | 0+6+6 | 6 | 4 |  | 6 | 6
AlN#5 MIDDLE | 24 |  | 19+4 |  | 20 |  |  | 4
AlN#5 OUTER | 29 |  | 10+10 |  | 19 |  |  | 10
AlN#7 | 1 |  | 20 |  | 1
AlN#8 | 29 |  | 7+10 | 5 | 14 |  |  | 10
Al2 O3 Spacer metalized | 46 |  | 4+10 | 11 | 10 | 15 | 15 | 10
Al2 O3 Spacer | 29 |  | 5+10 | 4 | 15 |  |  | 10