Spine numbers required to produce total Endcap module production

Required number of modules = 2371

This includes a 20% contingency

Module breakdown

Inner	480

Middle	768

Outer	1124

(of which long modules = 1892)

Total 	2372

At present we have about 10% of spines lost in module production. This number might fall, as we make less dummies, but we should keep this figure to be safe.

So number of spines required for module production is:

Inner	528

Middle	845

Outer	1235

Total 	2305 (of which total long = 2080)

Total number of spines ordered

INTAS project:

Pre-series

Outer	= 100

Middle	= 100

Inner	= 100

Total	= 300

229 run

Outer	= 229

ISTC run

Outer  	= 1021

Middle = 651

Inner 	= 349

Total	= 2021

Total number of spines ordered:

Outer	= 1262

Middle	= 682

Inner	= 383

Total	= 2327

(of which long = 1944)

Compare ordered with required:

| Type | Ordered | Required – spines (required modules * 1.1) | Required - modules (before 20%) | Spine Ratio ordered/required (ordered spines /required modules) |
| --- | --- | --- | --- | --- |
| Outer | 1262 | 1236 | 1124 (936) | 1.02 (1.12) |
| Middle | 682 | 845 | 768 (640) | 0.81 (0.88) |
| Long | 1944 | 2081 | 1892 (1576) | 0.93 (1.03) |
| Inner | 383 | 528 | 480 (400) | 0.73 (0.80) |
| Total | 2327 | 2608 | 2372 (1976) | 0.89 (0.98) |

Conclusion:

We need to order more spines

Should order extra spines as:

Outer	= 0

Middle	= 163

Inner	= 145

TPG supply

INTAS project:

466 plates all used in INTAS project

229 run

Outer	= 250 (extra 10% supplied in this case)

ISTC order

Long plates	= 1900

Short 		= 600

Total 		= 2500 (only charged for 90% of cost)

Total TPG = 2750 (long = 2150, short = 600)

According to an e-mail from NIITAP, (August 2005), one can say that the yield for TPG plates going to TPG for spines is 66% for long plates and 80% for short plates. Infact the damaged long plates can often be used for short plates and therefore the good short plate number is enhanced slightly.

| Type | Ordered | After loss in NIITAP | Ordered spines | Required Spines | Extra TPG required |
| --- | --- | --- | --- | --- | --- |
| Long | 2150 | 1419 | 1944 | 2081 | 1003 |
| Short | 600 | 480 | 383 | 528 | 60 |
| Total | 2750 | 1899 |  |  | 1063 |

After loss in NIITAP calculates as ordered x yield

Extra TPG required calculated as (Required spines – TPG after loss in NIITAP) / yield

Yield = 0.8 for short plates and 0.66 for long plates

Therefore we need to order more long TPG plates

Conclusions:

Require and need to order extra spines as:

Outer	= 0

Middle	= 170

Inner	= 150

Require and need to order extra TPG plates as:

Long 	= 1000

Short	= 60

To date spine production numbers from the database are:

| Type | Spines arrived at CERN including trashed ones | Good spines produced | Spines shipped from CERN |
| --- | --- | --- | --- |
| Outer | 742 | 693 | 632 |
| Middle | 468 | 438 | 384 |
| Inner | 351 | 316 | 266 |