## spine summary
Status December 10 2003
component | spines | [5 empty] | target delivery date |  | from stock pages
type | I |  | M |  | O |  |  |  | all spines delivered (including assembled and trashed ones)
required/delivered | requested | delivered | requested | delivered | requested | delivered | dummy | real | inner | middle | outer | all
UK |  | 0 |  | 8 | 15 | 80 | asap | 2002-11-01 | 0 | 10 | 83 | 93
Valencia |  | 0 |  | 52 | 18 | 18 | asap | 2002-12-01 | 0 | 52 | 22 | 74
Geneva/CERN |  | 0 |  | 0 | 15 | 100 | 2002-12-01 | 2003-01-01 | 0 | 0 | 90 | 90
Melbourne |  | 0 |  | 0 | 10 | 17 |  | 2002-01-03 | 0 | 0 | 16 | 16
Freiburg | 15 | 48 |  | 0 |  | 0 | asap | 2003-01-01 | 47 | 0 | 0 | 47
Munich/Prague |  | 0 |  | 57 |  | 0 |  |  | 5 | 52 | 2 | 59
NIKHEF | 7 | 45 |  | 0 |  | 0 | asap | 2002-11-01 | 28 | 0 | 0 | 28
total | 22 | 93 | 0 | 117 | 58 | 215 |  |  | 80 | 114 | 213 | 407
|  | 93 |  | 117 |  | 215 |  | 425
type | to | number | comment | search string |  |  | Spines available (not assembled, not trashed etc)
inner | NIKHEF | 2 | old (dummies) | innerNIKHEF | 15-Oc-02 |  | Outer |  |  | Middle |  |  | inner |  | all
inner | Freiburg | 2 | old (dummies) | innerFreiburg | 15-Oc-02 |  | CERN | 103 |  | CERN | 49 |  | CERN | 47 | 199
outer | UK | 2 | good | outerUK | 15-Oc-02 |  | MPI | 0 |  | MPI | 29 |  | MPI | 5 | 34
outer | Valencia | 2 | good | outerValencia | 15-Oc-02 |  | Melbourne | 6 |  | Melbourne | 0 |  | Melbourne | 0 | 6
inner | NIKHEF | 5 | good | innerNIKHEF | 2002-10-20 |  | Geneva | 31 |  | Geneva | 0 |  | Geneva | 0 | 31
outer | UK | 3 | good | outerUK | 2002-10-20 |  | Valencia | 3 |  | Valencia | 16 |  | Valencia | 0 | 19
outer | Melbourne | 1 | dummy | outerMelbourne | 2002-10-18 |  | UK | 28 |  | UK | 3 |  | UK | 0 | 31
outer | Valencia | 3 | dummy | outerValencia | 2002-10-18 |  | Freiburg | 0 |  | Freiburg | 0 |  | Freiburg | 46 | 46
inner | Freiburg | 11 | good | innerFreiburg | 2002-12-02 |  | NIKHEF | 0 |  | NIKHEF | 0 |  | NIKHEF | 23 | 23
inner | NIKHEF | 3 | good | innerNIKHEF | 2002-12-02 |  |  | 171 |  |  | 97 |  |  | 121 | 389
inner | Freiburg | 6 | good | innerFreiburg | 2002-12-18
outer | Geneva | 5 | good | outerGeneva | 2002-12-18
outer | Melbourne | 5 | good | outerMelbourne | 2002-12-18
outer | UK | 4 | good | outerUK | 2002-12-18
outer | Valencia | 4 | good | outerValencia | 2002-12-18
outer | UK | 2 | good | outerUK | 2003-01-27
outer | Geneva | 2 | good | outerGeneva | 2002-02-14
outer | UK | 3 | good | outerUK | 2003-03-06 |  | All made so far (ok)
outer | Geneva | 8 | good | outerGeneva | 2003-04-03 |  | Outer |  |  | Middle |  |  | inner |  | all
outer | Valencia | 9 | good | outerValencia | 2003-04-03 |  |  | 318 |  |  | 195 |  |  | 145 | 658
outer | Melbourne | 4 | good | outerMelbourne | 2003-04-03 |  | with washer | 248 |  | with washer | 88 |  | with washer | 67 | 403
middle | MPI | 24 | good | middleMPI | 2003-01-01
outer | Melbourne | 2 | good | outerMelbourne | 2003-04-16
outer | Geneva | 6 | good | outerGeneva | 2003-06-03 |  | Still at IHEP |  | 2003-06-12
middle | Valencia | 6 | good | middleValencia | 2003-06-18 |  | outer | 0
outer | Geneva | -6 | good | outerGeneva | 2003-05-20 | bad return | middle | 0
middle | MPI | 6 | good | middleMPI | 2003-06-27 |  | inner | 0
outer | UK | 3 | good | outerUK | 2003-07-01
outer | Geneva | -2 | good | outerGeneva | 2003-07-03 | bad return
outer | Geneva | 5 | good | outerGeneva | 2003-07-03
inner | NIKHEF | 6 | good | innerNIKHEF | 2003-08-19
middle | Valencia | 5 | good | middleValencia | 2003-08-26
outer | UK | 10 | good | outerUK | 2003-09-29
inner | Freiburg | 10 | good | innerFreiburg | 2003-09-05 | 990003498
outer | Geneva | 5 | good | outerGeneva | 2003-09-05 | 990003514
outer | Geneva | -2 | good | outerGeneva | 2003-09-09 | 990003570
outer | Geneva | 2 | good | outerGeneva | 2003-09-23 | 990003849
outer | UK | 2 | good | outerUK | 2003-09-23 | 990003850
outer | UK | 4 | good | outer UK | 2003-09-24 | 990003937
middle | UK | 8 | good | middleUK | 2003-09-24 | 990003909 | 990003941
outer | UK | -6 | good | outerUK | 2003-09-24 | bad, return
inner | NIKHEF | 10 | good | innerNIKHEF | 2003-09-24 | 990003910
middle | Valencia | 5 | good | middleValencia | 2003-09-24 | 990003907
middle | Valencia | 12 | good | middleValencia | 2003-09-24 | 990003907
middle | MPI | 12 | good | middleMPI | 2003-09-24 | 990003908
outer | Geneva | 3 | good | outerGeneva | 2003-10-21 | 990004043
outer | Melbourne | 5 | good | outerMelbourne | 2003-10-21 | 990004044
inner | NIKHEF | 4 | good | innerNIKHEF | 2003-10-30 | return of bad ones
outer | UK | 10 | good | outerUK | 2003-11-05 | 990004142
outer | Geneva | 6 | good | outerGeneva | 2003-11-07
middle | Valencia | -2 | good | middleValencia | 2003-12-03 | return of bad ones
outer | UK | -1 | good | outerUK | 2003-12-03 | return of bad ones
outer | Geneva | 3 | good | outerGeneva | 2003-12-05 | 990004361
outer | Geneva | 47 | good | outerGeneva | 2003-12-08 | 990004368
inner | NIKHEF | 15 | good | innerNIKHEF | 2003-12-08 | 990004373
inner | Freiburg | 19 | good | innerFreiburg | 2003-12-08 | 990004375
middle | Valencia | 14 | good | middleValencia | 2003-12-09
middle | MPI | 15 | good | middleMPI | 2003-12-09
outer | UK | 18 | good | outerUK | 2003-12-11
outer | Geneva | -11 | good | outer Geneva | 2004-01-30 | return of bad ones
outer | UK | 16 | good | outerUK | 2004-01-30
middle | Valencia | 12 | good | middleValencia | 2004-01-30
outer | UK | 14 | good | outerUK | 2004-02-20
outer | Geneva | 18 | good | outerGeneva | 2004-03-01 | 990004910

## qualification+preparation
SCT Endcap Module Components required for Site Qualification, and its preparation
2002-10-15 | [LF]
(D) means "dummy component" (see below)
component | hybrids | [5 empty] | detectors (sets) | [11 empty] | spines | [5 empty] | fanins (sets) | [11 empty] | washer | cond. | box |  |  | target delivery date
type | mechan. |  | 1-dead |  | perfect |  | I (D) |  | I |  | M (D) |  | M |  | O (D) |  | O |  | I |  | M |  | O |  | I (D) |  | I |  | M (D) |  | M |  | O (D) |  | O |  | (set) | glue | I | M | O
required/delivered | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | r | d | [5 empty] | dummy | real
UK | 2 |  | 8 |  | 5 | [17 empty] | 15 | [9 empty] | 6 |  | 9 |  |  | 26 |  |  | 17 | asap | 2002-11-02
Valencia | 2 |  | 3 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3 |  | 15 |  | 20 | 25 | 0 | 0 | 20 | asap | 2002-12-02
Geneva/CERN | 2 |  | 8 |  | 5 | [17 empty] | 15 | [9 empty] | 10 |  | 5 |  | 15 | 20 |  |  | 15 | 2002-12-02 | 2002-01-03
Melbourne | 1 |  | 3 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 |  | 0 |  | 0 |  | 10 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3 |  | 5 |  | 10 | 12 | 0 | 0 | 0 | asap | 2002-01-03
Freiburg | 1 |  | 3 |  | 5 |  | 6 |  | 5 | 5 | [8 empty] | 15 | [5 empty] | 5 |  | 5 | [9 empty] | 15 | 30 | 15 |  |  | asap | 2002-01-03
Munich/Prague | 2 |  | 3 |  | 5 | [15 empty] | 10 | [7 empty] | 5 |  | 5 | [5 empty] | 10 | 20 |  | 10 |  | 2002-11-02
NIKHEF | 1 |  | 1 |  | 5 |  | 0 |  | 6 | 6 | 0 |  | 0 |  | 0 |  | 0 |  | 7 |  | 0 |  | 0 |  | 3 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7 | 0 | 7 | 0 | 0 | asap | 2002-11-02
total | 11 | 0 | 29 | 0 | 35 | 0 | 6 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 22 | 0 | 10 | 0 | 58 | 0 | 8 | 0 | 10 | 0 | 5 | 0 | 5 | 0 | 22 | 0 | 34 | 0 | 77 | 133 | 22 | 10 | 52
hybrids:
mechanical: reject flex on Al substrate with SMD and dummy chips, delivered by Freiburg
1-dead: good hybrid with 1-dead-channel chips, delivered by Freiburg or industry, partly through the hybrid QA sites
perfect: perfect, delivered by Freiburg or industry, through the hybrid QA sites
detectors:
listed in this table are those detectors which are not locally on stock, delivery in the usual way
dummy: rejects from production
spines:
delivered by MPI Munich, with fanin spacer attached (far end washer attached ?)
since no distinction is made between dummy and real the delivery should start at the "target delivery date" for dummies
fan-ins:
delivered by CNM Barcelona
dummy: rejects from production with some open/short lines or other small imperfections
washers:
delivered by Manchester
conductive glue:
in units of packs
delivered by Valencia
boxes:
delivery to be agreed

## preseries
Outer
20220990158084 | N122 03-03 | fmSpineOut | CERN
20220990158089 | N120 03-03 | fmSpineOut | CERN
20220990158083 | N123 03-03 | fmSpineOut | Manchester
20220990158099 | N118 03-03 | fmSpineOut | Geneva
20220990158101 | N93 03-03 | fmSpineOut | CERN
20220990158098 | N113 03-03 | fmSpineOut | CERN
20220990158095 | N119 03-03 | fmSpineOut | Manchester
20220990158096 | N110 03-03 | fmSpineOut | CERN
20220990158093 | N108 03-03 | fmSpineOut | Manchester
20220990158088 | N100 03-03 | fmSpineOut | Geneva
20220990158081 | N105 03-03 | fmSpineOut | Geneva
20220990158104 | N112 03-03 | fmSpineOut | Geneva
Middle
20220990032331 | N01 15-05-02 | fmSpineMidL | Munich MPI
20220990032346 | N02 14-05-02 | fmSpineMidL | Munich MPI
20220990032332 | N03 14-05-02 | fmSpineMidL | Munich MPI
20220990032333 | N04 15-05-02 | fmSpineMidL | Munich MPI
20220990032334 | N05 15-05-02 | fmSpineMidL | Munich MPI
20220990032335 | N07 14-05-02 | fmSpineMidL | Munich MPI
20220990032336 | N08 15-05-02 | fmSpineMidL | Munich MPI
20220990032343 | N10 01-06-02 | fmSpineMidL | Munich MPI
20220990107576 | N13 30-09-02 | fmSpineMidL | Munich MPI
20220990107575 | N14 30-09-02 | fmSpineMidL | Valencia
20220990107496 | N15 30-09-02 | fmSpineMidL | Munich MPI
20220990107497 | N16 30-09-02 | fmSpineMidL | Munich MPI
20220990107498 | N17 30-09-02 | fmSpineMidL | Munich MPI
20220990107499 | N18 30-09-02 | fmSpineMidL | Valencia
20220990107500 | N19 30-09-02 | fmSpineMidL | Valencia
20220990107501 | N20 30-09-02 | fmSpineMidL | Munich MPI
20220990107502 | N21 30-09-02 | fmSpineMidL | Valencia
20220990107503 | N22 30-09-02 | fmSpineMidL | Munich MPI
20220990107504 | N23 30-09-02 | fmSpineMidL | Valencia
20220990107505 | N24 30-09-02 | fmSpineMidL | Munich MPI
20220990107577 | N25 05-10-02 | fmSpineMidL | Valencia
20220990107578 | N26 05-10-02 | fmSpineMidL | Munich MPI
20220990107579 | N27 05-10-02 | fmSpineMidL | Munich MPI
20220990107580 | N28 05-10-02 | fmSpineMidL | Munich MPI
20220990107581 | N29 05-10-02 | fmSpineMidL | Munich MPI
20220990158078 | N30 06-12-02 | fmSpineMidL | Munich MPI
20220990158077 | N31 06-12-02 | fmSpineMidL | Munich MPI
20220990158076 | N32 06-12-02 | fmSpineMidL | Munich MPI
20220990158075 | N33 06-12-02 | fmSpineMidL | Munich MPI
20220990158074 | N34 06-12-02 | fmSpineMidL | Munich MPI
20220990158073 | N35 06-12-02 | fmSpineMidL | Munich MPI
inners
20220990032347 | N13 01-06-02 | fmSpineInn | NIKHEF
20220990032348 | N11 01-06-02 | fmSpineInn | Freiburg
20220990032349 | N10 01-06-02 | fmSpineInn | Freiburg
20220990032350 | N04 01-06-02 | fmSpineInn
20220990107506 | N16 30-09-02 | fmSpineInn | NIKHEF
20220990107507 | N17 30-09-02 | fmSpineInn
20220990107508 | N18 30-09-02 | fmSpineInn
20220990107509 | N19 30-09-02 | fmSpineInn
20220990107510 | N20 30-09-02 | fmSpineInn
20220990107550 | N23 30-09-02 | fmSpineInn | Freiburg
20220990107551 | N24 30-09-02 | fmSpineInn | Freiburg
20220990107552 | N25 30-09-02 | fmSpineInn | Freiburg
20220990107553 | N26 30-09-02 | fmSpineInn | Freiburg
20220990107554 | N27 30-09-02 | fmSpineInn | Freiburg
20220990107555 | N28 30-09-02 | fmSpineInn | Freiburg
20220990107556 | N29 30-09-02 | fmSpineInn | Freiburg
20220990107557 | N30 30-09-02 | fmSpineInn | Freiburg
20220990107558 | N31 30-09-02 | fmSpineInn | Freiburg
20220990107559 | N32 30-09-02 | fmSpineInn | Freiburg
20220990107560 | N33 30-09-02 | fmSpineInn | Freiburg
20220990107561 | N34 30-09-02 | fmSpineInn | Freiburg
20220990107562 | N35 30-09-02 | fmSpineInn | Freiburg
20220990107563 | N36 30-09-02 | fmSpineInn
20220990107564 | N37 30-09-02 | fmSpineInn | Freiburg
20220990107565 | N38 30-09-02 | fmSpineInn | Munich MPI
20220990107566 | N39 30-09-02 | fmSpineInn | Munich MPI
20220990107567 | N40 30-09-02 | fmSpineInn | Munich MPI
20220990107568 | N41 30-09-02 | fmSpineInn | Munich MPI
20220990107569 | N42 30-09-02 | fmSpineInn | Munich MPI
20220990107570 | N43 30-09-02 | fmSpineInn
20220990107571 | N44 30-09-02 | fmSpineInn | NIKHEF
20220990107572 | N21 30-09-02 | fmSpineInn | Freiburg
20220990107573 | N22 30-09-02 | fmSpineInn | Freiburg
20220990107574 | N15 30-09-02 | fmSpineInn | Freiburg

## outer spine stock
Serial Number | Mfr Serial No | Type | Current Location | Assembled? | tag
20220990012266 | N14-30-04-02 Out | fmSpineOut | Munich MPI | NO | Munich MPINO |  | with washer
20220990032351 | N15 26-05-02 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990032352 | N16 26-05-02 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990032353 | N17 26-05-02 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer
20220990032354 | N19 26-05-02 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer
20220990032355 | N21 26-05-02 | fmSpineOut | Munich MPI | NO | Munich MPINO |  | with washer
20220990290445 | N22 | fmSpineOut | Manchester | NO | ManchesterNO
20220990032356 | N23 26-05-02 | fmSpineOut | Geneva | NO | GenevaNO |  | with washer
20220990032357 | N24 26-05-02 | fmSpineOut | Melbourne | NO | MelbourneNO |  | with washer
20220990032358 | N25 26-05-02 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990032359 | N26 26-05-02 | fmSpineOut | Valencia | OK | ValenciaOK
20220990107486 | N32 30-09-02 | fmSpineOut | Check Assembly Tree | YES | Check Assembly TreeYES |  | with washer
20220990107487 | N38 30-09-02 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990107488 | N40 30-09-02 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990107489 | N39 30-09-02 | fmSpineOut | Check Assembly Tree | YES | Check Assembly TreeYES |  | with washer
20220990107490 | N37 30-09-02 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990107491 | N34 30-09-02 | fmSpineOut | Valencia | YES | ValenciaYES |  | with washer
20220990107492 | N27 30-09-02 | fmSpineOut | Manchester | NO | ManchesterNO |  | with washer
20220990107493 | N31 30-09-02 | fmSpineOut | Manchester | NO | ManchesterNO |  | with washer
20220990107494 | N35 30-09-02 | fmSpineOut | Valencia | YES | ValenciaYES |  | with washer
20220990107495 | N28 30-09-02 | fmSpineOut | Check Assembly Tree | YES | Check Assembly TreeYES |  | with washer
20220990107582 | N41 05-10-02 | fmSpineOut | Melbourne | YES | MelbourneYES |  | with washer
20220990107583 | N42 05-10-02 | fmSpineOut | Geneva | NO | GenevaNO |  | with washer
20220990107584 | N43 05-10-02 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer
20220990107585 | N44 05-10-02 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer
20220990107586 | N45 05-10-02 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer
20220990107587 | N46 05-10-02 | fmSpineOut | Manchester | NO | ManchesterNO |  | with washer
20220990107633 | N29 30-09-02 | fmSpineOut | Melbourne | NO | MelbourneNO |  | with washer
20220990107634 | N30 30-09-02 | fmSpineOut | Melbourne | YES | MelbourneYES |  | with washer
20220990107635 | N33 30-09-02 | fmSpineOut | Melbourne | NO | MelbourneNO |  | with washer
20220990107636 | N36 30-09-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990107637 | N47 05-10-02 | fmSpineOut | Melbourne | YES | MelbourneYES |  | with washer
20220990107638 | N48 05-10-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990107639 | N49 05-10-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990107640 | N50 05-10-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990107641 | N51 05-10-02 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer
20220990107642 | N53 05-10-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990107643 | N54 05-10-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990107644 | N55 05-10-02 | fmSpineOut | Valencia | NO | ValenciaNO |  | with washer
20220990107645 | N56 05-10-02 | fmSpineOut | Valencia | bow | Valenciabow |  | with washer
20220990107646 | N57 05-10-02 | fmSpineOut | Valencia | rejected | Valenciarejected |  | with washer
20220990107647 | N58 05-10-02 | fmSpineOut | Valencia | YES | ValenciaYES | ok | with washer
20220990288258 | N59 05-10-02 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990157983 | N60 06-12-02 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 02B05 | middle wing repaired
20220990157984 | N66 06-12-02 | fmSpineOut | CERN | trashed | CERNtrashed |  | with washer |  | will be repaired
20220990157988 | No67 06-12-02 | fmSpineOut | Melbourne | YES | MelbourneYES |  | with washer
20220990130141 | N68 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990130142 | N69 | fmSpineOut | CERN | trashed | CERNtrashed |  | TPG crack, to be returned
20220990130140 | N71 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990157986 | No72 06-12-02 | fmSpineOut | Melbourne | YES | MelbourneYES | ok | with washer
20220990157985 | N73 | fmSpineOut | Melbourne | YES | MelbourneYES | ok | with washer
20220990157998 | N76 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990157999 | N75 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990158000 | N74 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990158001 | N78 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990158003 | N79 | fmSpineOut | Manchester | YES | ManchesterYES |  | washer displaced
20220990158005 | N81 | fmSpineOut | CERN | trashed | CERNtrashed |  | washer displaced | 0 | to replace washer
20220990157989 | N82 | fmSpineOut | Valencia | NO | ValenciaNO |  | with washer
20220990157990 | N83 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990157991 | N84 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990157992 | N85 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990157993 | N86 | fmSpineOut | Valencia | NO | ValenciaNO |  | with washer
20220990157994 | N87 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990157995 | N88 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990288304 | N89 06-12-02 | fmSpineOut | Geneva | YES | GenevaYES |  | washer displaced
20220990235889 | N90 01-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer | was returned from Manchester and repaired
20220990157996 | No91 01-03 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990157997 | No92 01-03 | fmSpineOut | Valencia | trashed | Valenciatrashed |  | with washer
20220990158101 | N93 03-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer |  | new washer
20220990158102 | N94 03-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 02B05 | washer re-glued | rejected by Geneva before repair
20220990185633 | N95 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1 | new washer
20220990185636 | N96 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1
20220990185634 | N97 05-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | 1
20220990185637 | N98 05-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | 1 | to be glued
20220990158086 | N99 03-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer |  | washer and AlN replaced
20220990158088 | N100 03-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer |  | preseries washer
20220990185632 | N101 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1 | bow fixed
20220990158085 | N102 03-03 | fmSpineOut | CERN | trashed | CERNtrashed | ok | with washer | 02B05 | washer repaire | AlN crack, to be returned
20220990158082 | N103 03-03 | fmSpineOut | Geneva | trashed | Genevatrashed |  | with washer |  | AlN broken
20220990158090 | N104 03-03 | fmSpineOut | Manchester | NO | ManchesterNO |  | with washer | ok | washer replaced
20220990158081 | N105 03-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer |  | preseries washer
20220990185638 | N106 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1 | AlN repaired
20220990185635 | N107 05-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | 1 | to be glued
20220990158093 | N108 03-03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer |  | preseries washer
20220990158097 | N109 03-03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer | 02B05 | Aln cracked
20220990158096 | N110 03-03 | fmSpineOut | CERN | trashed | CERNtrashed |  | with washer |  | no repair
20220990158103 | N111 03-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | washer repaired |  | 02B05
20220990158104 | N112 03-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer |  | preseries washer
20220990158098 | N113 03-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer |  | crack in AlN | where is it
20220990158092 | N114 03-03 | fmSpineOut | Melbourne | YES | MelbourneYES | to Melbourne | with washer
20220990158094 | N115 03-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | washer repaired |  | 02B05
20220990158091 | N116 03-03 | fmSpineOut | Melbourne | trashed | Melbournetrashed | to Melbourne | broken V-groove
20220990158100 | N117 03-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer |  | D4,D5 replaced, bow fixed
20220990158099 | N118 03-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer |  | preseries washer
20220990158095 | N119 03-03 | fmSpineOut | CERN | bow | CERNbow |  | with washer |  | preseries washer | to be returned
20220990158089 | N120 03-03 | fmSpineOut | CERN | NO | CERNNO | ok | with washer |  | repaired | where is it
20220990158087 | N121 03-03 | fmSpineOut | CERN | ? | CERN? |  | with washer |  | replace washer
20220990158084 | N122 03-03 | fmSpineOut | CERN | ? | CERN? |  | with washer |  | replace washer
20220990158083 | N123 03-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer |  | repaired
20220990185558 | N124 05-03 | fmSpineOut | CERN | ? | CERN? |  | with washer |  | to be repaired
20220990185559 | N125 05-03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer
20220990185560 | N126 05-03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer |  | AlN broken, used for dummy module
20220990185561 | N127 05-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | 1
20220990185562 | N128 05-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | 1
20220990185563 | N129 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1
20220990185564 | N130 05-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer | 1
20220990185565 | N131 05-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer | 1
20220990185566 | N132 05-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer | 1
20220990185567 | N133 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1
20220990185568 | N134 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1
20220990185569 | N135 05-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer | 1
20220990262564 | N141 09 03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer | ok | TPG cut (displaced TPG)
20220990262565 | N142 09 03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | ok | TPG cut (displaced TPG)
20220990262566 | N143 09-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | ok | TPG cut (displaced TPG)
20220990262567 | N144 09-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | ok | TPG cut (displaced TPG)
20220990288257 | N147 30-08 | fmSpineOut | Manchester | NO | ManchesterNO |  | with washer
20220990284598 | N148 10-03 | fmSpineOut | Melbourne | NO | MelbourneNO | ok | with washer
20220990262568 | N149 09-03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer | ok | TPG cut (displaced TPG)
20220990262569 | N150 09-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | ok | TPG cut (displaced TPG)
20220990284585 | N151 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990268765 | N152 09-03 | fmSpineOut | Manchester | YES | ManchesterYES |  | with washer | ok | TPG cut (displaced TPG)
20220990284586 | N153 10-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990284587 | N154 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990284588 | N155 10-03 | fmSpineOut | CERN | YES | CERNYES | ok | with washer
20220990284589 | N156 10-03 | fmSpineOut | CERN | NO | CERNNO |  | with washer |  | middle wing to be repaired
20220990284590 | N157 10-03 | fmSpineOut | CERN | trashed | CERNtrashed |  | with washer |  | crack in AlN
20220990284591 | N158 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990284592 | N159 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990284593 | N160 10-03 | fmSpineOut | Melbourne | YES | MelbourneYES | ok | with washer
20220990284594 | N161 10-03 | fmSpineOut | CERN | trashed | CERNtrashed |  | with washer |  | crack in AlN
20220990268764 | N162 09-03 | fmSpineOut | Geneva | YES | GenevaYES |  | with washer | ok | TPG cut (displaced TPG)
20220990284595 | N163 10-03 | fmSpineOut | Melbourne | NO | MelbourneNO | ok | with washer
20220990284596 | N164 10-03 | fmSpineOut | Melbourne | NO | MelbourneNO | ok | with washer
20220990284597 | N165 10-03 | fmSpineOut | Melbourne | YES | MelbourneYES | ok | with washer
20220990288426 | N166 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288427 | N167 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
| N168 | fmSpineOut | CERN | NO | CERNNO | ok | with washer
20220990288428 | N169 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288244 | N170 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288429 | N171 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288430 | N172 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288431 | N173 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288432 | N174 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990290446 | N175 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288433 | N176 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288245 | N177 10-03 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288246 | N178 10-03 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288247 | N179 10-03 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288248 | N180 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288249 | N181 10-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288324 | N182 11-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288250 | N183 10-03 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288251 | N184 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer |  | washer repaired ?
20220990288252 | N185 10-03 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288253 | N186 10-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288273 | N187 10-03 | fmSpineOut | Manchester | cracked | Manchestercracked | ok | with washer |  | to be returned from Manchester
20220990288254 | N188 10-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288272 | N189 10-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288271 | N190 10-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288270 | N191 10-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288255 | N192 10-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288256 | N193 10-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288269 | N194 10-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer |  | low glue coverage
20220990288268 | N195 10-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288267 | N196 10-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288266 | N197 10-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288264 | N198 10-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288265 | N199 10-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288325 | N200 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288326 | N201 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288327 | N202 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990288328 | N205 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288329 | N206 11-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288330 | N203 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288331 | N204 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288332 | N207 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288333 | N208 11-03 | fmSpineOut | CERN | defect | CERNdefect | washer displaced | with washer |  | returned by Geneva
20220990288363 | N209 11-03 | fmSpineOut | Manchester | YES | ManchesterYES | ok | with washer
20220990288334 | N210 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990288375 | N211 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288376 | N212 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288364 | N213 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288377 | N214 11-03 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288335 | N215 11-03 | fmSpineOut | CERN | defect | CERNdefect | washer displaced | with washer
20220990288336 | N216 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288378 | N217 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288337 | N218 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288338 | N219 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288339 | N220 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990288379 | N221 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990288340 | N222 11-03 | fmSpineOut | CERN | NO | CERNNO | washer displaced | with washer
20220990288341 | N223 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288365 | N224 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288366 | N225 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288380 | N226 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288344 | N227 11-03 | fmSpineOut | Manchester | OK | ManchesterOK | ok | with washer |  | returned by Geneva |  | repaired
20220990288381 | N228 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288345 | N229 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990288367 | N230 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288346 | N231 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288347 | N232 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990288368 | N233 11-03 | fmSpineOut | CERN | defect | CERNdefect | defect | with washer |  | returned by Geneva
20220990290641 | N234 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288369 | N235 11-03 | fmSpineOut | CERN | defect | CERNdefect | ok | with washer |  | returned by Geneva
20220990288370 | N236 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290642 | N237 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288371 | N238 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288348 | N239 11-03 | fmSpineOut | CERN | defect | CERNdefect | washer displaced | with washer
20220990288349 | N240 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288372 | N241 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288350 | N242 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288351 | N243 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288352 | N244 11-03 | fmSpineOut | CERN | defect | CERNdefect | washer displaced | with washer |  | returned by Geneva
20220990288373 | N245 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288374 | N246 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288505 | N247 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288506 | N248 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288353 | N249 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288507 | N250 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288508 | N251 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288509 | N252 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288510 | N253 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288354 | N254 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288355 | N255 11-03 | fmSpineOut | Manchester | defect | Manchesterdefect | washer displaced | with washer
20220990290706 | N256 | fmSpineOut | CERN | OK | CERNOK |  | with washer
20220990288356 | N257 11-03 | fmSpineOut | Manchester | defect | Manchesterdefect | washer displaced | with washer
20220990288357 | N258 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288511 | N259 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288358 | N260 11-03 | fmSpineOut | Geneva | YES | GenevaYES | ok | with washer
20220990288359 | N261 11-03 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288360 | N262 11-03 | fmSpineOut | Geneva | trashed | Genevatrashed | AlN crack | with washer | discovered by Geneva
20220990288361 | N263 11-03 | fmSpineOut | Geneva | YES | GenevaYES | AlN crack | with washer | discovered by Geneva
20220990288362 | N264 11-03 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990288512 | N265 | fmSpineOut | CERN | NO | CERNNO | washer displaced | with washer |  | had washer displaced!
20220990288513 | N266 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288514 | N267 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990288515 | N268 | fmSpineOut | CERN | defect | CERNdefect | AlN crack | with washer
20220990288516 | N269 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990290643 | N270 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290644 | N272 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290645 | N273 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290447 | N274 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990290448 | N276 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990290449 | N277 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990290450 | N278 | fmSpineOut | Manchester | NO | ManchesterNO | ok | with washer
20220990290451 | N279 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290456 | N280 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290457 | N281 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290458 | N282 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290459 | N283 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290460 | N284 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290461 | N285 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290462 | N286 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290463 | N287 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290464 | N288 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290465 | N289 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290466 | N290 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290467 | N291 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290468 | N292 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290469 | N293 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290470 | N294 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290471 | N295 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290472 | N296 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290473 | N297 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290474 | N298 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290475 | N299 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290476 | N300 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290477 | N301 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290478 | N302 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290479 | N303 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290480 | N304 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290481 | N305 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290482 | N306 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290483 | N307 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290484 | N308 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290485 | N309 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290486 | N310 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290487 | N311 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290488 | N312 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290489 | N313 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290490 | N314 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290491 | N315 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290492 | N316 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290493 | N317 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290494 | N318 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290495 | N319 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290496 | N320 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290497 | N321 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290498 | N322 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290499 | N323 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290500 | N324 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290501 | N325 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290502 | N326 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290503 | N327 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290504 | N328 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290505 | N329 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290506 | N330 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290507 | N331 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290508 | N332 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290509 | N333 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290510 | N334 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290511 | N335 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290512 | N336 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290513 | N337 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290514 | N338 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290515 | N339 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290516 | N340 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290517 | N341 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290518 | N342 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290519 | N343 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290520 | N344 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290521 | N345 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290522 | N346 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290523 | N347 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290524 | N348 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290525 | N349 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290526 | N350 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290527 | N351 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290528 | N352 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290529 | N353 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290530 | N354 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290531 | N355 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290532 | N356 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290533 | N357 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290534 | N358 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290535 | N359 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290536 | N360 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290537 | N361 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290538 | N362 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290539 | N363 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290540 | N364 | fmSpineOut | Geneva | NO | GenevaNO | ok | with washer
20220990290541 | N365 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290542 | N366 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290543 | N367 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290544 | N368 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290545 | N369 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290546 | N370 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290547 | N371 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290548 | N372 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290549 | N373 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290550 | N374 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290551 | N375 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290552 | N376 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290553 | N377 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290554 | N378 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290555 | N379 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290556 | N380 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290557 | N381 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290558 | N382 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290559 | N383 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290560 | N384 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290561 | N385 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290562 | N386 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290563 | N387 | fmSpineOut | CERN | NO | CERNNO | ok
20220990290564 | N388 | fmSpineOut | CERN | NO | CERNNO | ok

## middle spine stock
Serial Number | Mfr Serial No | Type | Current Location | Assembled? | tag |  |  |  | washer batch
20220990032331 | N01 15-05-02 | fmSpineMidL | Munich MPI | OLD | Munich MPIOLD | N01 | old design
20220990032346 | N02 14-05-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N02
20220990032332 | N03 14-05-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N03
20220990032333 | N04 15-05-02 | fmSpineMidL | Munich MPI | OLD | Munich MPIOLD | N04 | old design
20220990032334 | N05 15-05-02 | fmSpineMidL | Munich MPI | OLD | Munich MPIOLD | N05 | old design
20220990032335 | N07 14-05-02 | fmSpineMidL | Munich MPI | OLD | Munich MPIOLD | N07 | old design
20220990032336 | N08 15-05-02 | fmSpineMidL | Munich MPI | OLD | Munich MPIOLD | N08 | old design
20220990032343 | N10 01-06-02 | fmSpineMidL | Munich MPI | OLD | Munich MPIOLD | N10 | old design
20220990185682 | N100 06-03 | fmSpineMidL | Valencia | YES | ValenciaYES | N100 | ok | with washer | 02B05
20220990185683 | N101 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N101 | ok | with washer | 02B05
20220990185684 | N102 06-03 | fmSpineMidL | Manchester | NO | ManchesterNO | N102 | ok | with washer | 02B05
20220990185685 | N103 06-03 | fmSpineMidL | Manchester | YES | ManchesterYES | N103 | ok | with washer | 02B05
20220990185686 | N104 06-03 | fmSpineMidL | Manchester | NO | ManchesterNO | N104 | ok | with washer | 02B05
20220990185687 | N105 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N105 | ok | with washer | 02B05
20220990185691 | N106 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N106 | ok | with washer | 02B03
20220990185690 | N107 06-03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N107 | ok | with washer | 02B03
20220990185689 | N108 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N108 | ok | with washer | 02B03
20220990185688 | N109 06-03 | fmSpineMidL | Valencia | YES | ValenciaYES | N109 | ok | with washer | new | AlN 5 repaired
20220990185692 | N110 06-03 | fmSpineMidL | CERN | NO | CERNNO | N110
20220990185693 | N111 06-03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N111 | ok | with washer | 02B03
20220990185694 | N112 06-03 | fmSpineMidL | Manchester | YES | ManchesterYES | N112 | bow | with washer | 02B05 | N3
20220990185695 | N113 06-03 | fmSpineMidL | CERN | NO | CERNNO | N113
20220990107576 | N13 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N13 |  | P005
20220990107575 | N14 30-09-02 | fmSpineMidL | Valencia | YES | ValenciaYES | N14
20220990107496 | N15 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N15
20220990107497 | N16 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N16 |  | P004
20220990107498 | N17 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N17 |  | P003
20220990107499 | N18 30-09-02 | fmSpineMidL | Valencia | NO | ValenciaNO | N18
20220990107500 | N19 30-09-02 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N19
20220990107501 | N20 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N20 |  | 12
20220990107502 | N21 30-09-02 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N21
20220990107503 | N22 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N22 |  | P002
20220990107504 | N23 30-09-02 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N23
20220990107505 | N24 30-09-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N24 | ok | P001 | preseries, fixed
20220990107577 | N25 05-10-02 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N25
20220990107578 | N26 05-10-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N26
20220990107579 | N27 05-10-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N27 | ok | with washer | preseries, fixed
20220990107580 | N28 05-10-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N28 | ok | with washer | preseries, fixed
20220990107581 | N29 05-10-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N29 |  | DS02
20220990158078 | N30 06-12-02 | fmSpineMidL | Munich MPI | bow | Munich MPIbow | N30 | bow
20220990158077 | N31 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N31 | ok | with washer | preseries, fixed
20220990158076 | N32 06-12-02 | fmSpineMidL | Munich MPI | bow | Munich MPIbow | N32 | bow
20220990158075 | N33 06-12-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N33 | ok | with washer | preseries, fixed
20220990158074 | N34 06-12-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N34 | ok | with washer | preseries, fixed
20220990158073 | N35 06-12-02 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N35 | ok | with washer | preseries, fixed
20220990158079 | N36 06-12-02 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N36 | ok | with washer
20220990158080 | N37 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N37 | ok | with washer | 02B03
20220990158112 | N38 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N38 | ok | with washer
20220990158113 | N39 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N39 | ok | with washer
20220990185643 | N40 05-03 | fmSpineMidL | CERN | NO | CERNNO | N40
20220990158114 | N41 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N41
20220990185644 | N42 05-03 | fmSpineMidL | Manchester | YES | ManchesterYES | N42 | ok | with washer | 02B05
20220990158108 | N43 06-12-02 | fmSpineMidL | Manchester | YES | ManchesterYES | N43 | ok | with washer | 02B05
20220990158109 | N44 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N44 | ok | with washer | 02B05
20220990158110 | N45 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N45 | ok | with washer | 02B05
20220990158111 | N46 06-12-02 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N46 | ok | with washer | 02B05
20220990185641 | N47 05-03 | fmSpineMidL | Valencia | NO | ValenciaNO | N47 | ok | with washer | 02B05
20220990185639 | N48 05-03 | fmSpineMidL | Valencia | YES | ValenciaYES | N48 | ok | with washer | 02B05
20220990185645 | N49 05-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N49 | ok | with washer | 02B05
20220990185642 | N50 05-03 | fmSpineMidL | Valencia | NO | ValenciaNO | N50 | ok | with washer | new
20220990185640 | N51 05-03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N51 | ok | with washer | 02B05
20220990158115 | N52 | fmSpineMidL | Munich MPI | YES | Munich MPIYES | N52 | ok | with washer | 02B05 | N3
20220990158116 | N53 | fmSpineMidL | Manchester | YES | ManchesterYES | N53 | ok | with washer | 02B05
20220990158117 | N54 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N54 | ok | with washer | new
20220990158127 | N55 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N55 | ok | with washer | 02B05
20220990158126 | N56 | fmSpineMidL | Manchester | YES | ManchesterYES | N56 | ok | with washer | 02B05
20220990158125 | N57 | fmSpineMidL | Manchester | NO | ManchesterNO | N57 | ok | with washer | 02B05
20220990158124 | N58 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N58 | ok | with washer | 02B05
20220990158123 | N59 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N59 | ok | with washer | 02B05
20220990158122 | N60 | fmSpineMidL | Valencia | YES | ValenciaYES | N60 | ok | with washer | 02B03
20220990158121 | N61 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N61 | ok | with washer | 02B03
20220990158120 | N62 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N62 | ok | with washer | 02B05
20220990158119 | N63 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N63 | ok | with washer | 02B03
20220990158118 | N64 0x | fmSpineMidL | CERN | NO | CERNNO | N64
20220990158269 | N65 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N65 | ok | with washer | 02B05
20220990158271 | N66 05 03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N66 | ok | with washer | 02B05 | N3
20220990158272 | N67 05 03 | fmSpineMidL | Valencia | OK | ValenciaOK | N67 |  | with washer | 02B03 | bowed
20220990158266 | N68 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N68 | ok | with washer | 02B03
20220990158267 | N69 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N69 | ok | with washer | 02B03
20220990158268 | N70 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N70 | ok | with washer | new
20220990158265 | N71 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N71 | ok | with washer | new | twist corrected
20220990158270 | N72 05 03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N72 | ok | with washer | 02B05 | N3
20220990158263 | N73 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N73 | ok | with washer | 02B03
20220990158264 | N74 05 03 | fmSpineMidL | Valencia | NO | ValenciaNO | N74 | ok | with washer | new
20220990158254 | N75 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N75 | ok | with washer | 02B05
20220990158255 | N76 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N76 | ok | with washer | 02B05
20220990158252 | N77 05 03 | fmSpineMidL | CERN | NO | CERNNO | N77
20220990158253 | N78 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N78 | ok | with washer | 02B05
20220990158258 | N79 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N79 | ok | with washer | 02B05
20220990158259 | N80 05 03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N80 | ok | with washer | 02B05
20220990185668 | N81 06-03 | fmSpineMidL | Valencia | YES | ValenciaYES | N81 | ok | with washer | 02B05 | N3
20220990185669 | N82 06-03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N82 | ok | with washer | 02B05
20220990185670 | N83 06-03 | fmSpineMidL | Manchester | YES | ManchesterYES | N83 | bow | with washer | 02B05
20220990185671 | N84 06-03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N84 | ok | with washer | 02B05
20220990185672 | N85 06-03 | fmSpineMidL | Valencia | NO | ValenciaNO | N85 | ok | with washer | 02B05
20220990185673 | N86 06-03 | fmSpineMidL | Valencia | NO | ValenciaNO | N86 | ok | with washer | 02B05
20220990158260 | N87 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N87 | ok | with washer
20220990185674 | N88 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N88 | ok | with washer | 02B03
20220990185675 | N89 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N89 | ok | with washer | 02B05
20220990185676 | N90 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N90 | ok | with washer | 02B05
20220990185677 | N91 06-03 | fmSpineMidL | Valencia | YES | ValenciaYES | N91 | ok | with washer | 02B05
20220990185678 | N92 06-03 | fmSpineMidL | Valencia | OK | ValenciaOK | N92 |  | with washer | 02B05 | bowed
20220990158261 | N93 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N93 | ok | with washer | 02B05
20220990158257 | N94 05 03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N94 | ok | with washer | new
20220990158256 | N95 05 03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N95 | ok | with washer | n
20220990158262 | N96 05 03 | fmSpineMidL | Valencia | YES | ValenciaYES | N96 | ok | with washer | 02B03
20220990185679 | N97 06-03 | fmSpineMidL | Valencia | YES | ValenciaYES | N97 | ok | with washer | 02B05
20220990185680 | N98 06-03 | fmSpineMidL | Valencia | trashed | Valenciatrashed | N98 | ok | with washer | 02B05
20220990185681 | N99 06-03 | fmSpineMidL | Munich MPI | NO | Munich MPINO | N99 | ok | with washer | 02B05
20220990290425 | N114 | fmSpineMidL | Valencia | NO | ValenciaNO | N114 | ok | with washer | 02B05
20220990290426 | N115 | fmSpineMidL | Valencia | NO | ValenciaNO | N115 | ok | with washer | 02B05
20220990290427 | N116 | fmSpineMidL | Valencia | NO | ValenciaNO | N116 | ok | with washer | 02B05
20220990290428 | N117 | fmSpineMidL | Valencia | NO | ValenciaNO | N117 | ok | with washer | 02B05
20220990290429 | N118 | fmSpineMidL | Valencia | NO | ValenciaNO | N118 | ok | with washer | 02B05
20220990290430 | N119 | fmSpineMidL | Valencia | NO | ValenciaNO | N119 | ok | with washer | 02B05
20220990290431 | N120 | fmSpineMidL | Valencia | NO | ValenciaNO | N120 | ok | with washer | 02B05
20220990290432 | N121 | fmSpineMidL | Valencia | NO | ValenciaNO | N121 | ok | with washer | 02B05
20220990290433 | N122 | fmSpineMidL | Valencia | NO | ValenciaNO | N122 | ok | with washer | 02B05
20220990290434 | N123 | fmSpineMidL | Valencia | NO | ValenciaNO | N123 | ok | with washer | 02B05
20220990290565 | N124 | fmSpineMidL | CERN | NO | CERNNO | N124 | ok
20220990290566 | N125 | fmSpineMidL | CERN | NO | CERNNO | N125 | ok
20220990290567 | N126 | fmSpineMidL | CERN | NO | CERNNO | N126 | ok
20220990290568 | N127 | fmSpineMidL | CERN | NO | CERNNO | N127 | ok
20220990290569 | N128 | fmSpineMidL | CERN | NO | CERNNO | N128 | ok
20220990290570 | N129 | fmSpineMidL | CERN | NO | CERNNO | N129 | ok
20220990290571 | N130 | fmSpineMidL | CERN | NO | CERNNO | N130 | ok
20220990290572 | N131 | fmSpineMidL | CERN | NO | CERNNO | N131 | ok
20220990290573 | N132 | fmSpineMidL | CERN | NO | CERNNO | N132 | ok
20220990290574 | N133 | fmSpineMidL | CERN | NO | CERNNO | N133 | ok
20220990290575 | N134 | fmSpineMidL | CERN | NO | CERNNO | N134 | ok
20220990290576 | N135 | fmSpineMidL | CERN | NO | CERNNO | N135 | ok
20220990290577 | N136 | fmSpineMidL | CERN | NO | CERNNO | N136 | ok
20220990290578 | N137 | fmSpineMidL | CERN | NO | CERNNO | N137 | ok
20220990290579 | N138 | fmSpineMidL | CERN | NO | CERNNO | N138 | ok
20220990290580 | N139 | fmSpineMidL | CERN | NO | CERNNO | N139 | ok
20220990290581 | N140 | fmSpineMidL | CERN | NO | CERNNO | N140 | ok
20220990290582 | N141 | fmSpineMidL | CERN | NO | CERNNO | N141 | ok
20220990290583 | N142 | fmSpineMidL | CERN | NO | CERNNO | N142 | ok
20220990290584 | N143 | fmSpineMidL | CERN | NO | CERNNO | N143 | ok
20220990290585 | N144 | fmSpineMidL | CERN | NO | CERNNO | N144 | ok
20220990290586 | N145 | fmSpineMidL | CERN | NO | CERNNO | N145 | ok
20220990290587 | N146 | fmSpineMidL | CERN | NO | CERNNO | N146 | ok
20220990290588 | N147 | fmSpineMidL | CERN | NO | CERNNO | N147 | ok
20220990290589 | N148 | fmSpineMidL | CERN | NO | CERNNO | N148 | ok
20220990290590 | N149 | fmSpineMidL | CERN | NO | CERNNO | N149 | ok
20220990290591 | N150 | fmSpineMidL | CERN | NO | CERNNO | N150 | ok
20220990290592 | N151 | fmSpineMidL | CERN | NO | CERNNO | N151 | ok
20220990290593 | N152 | fmSpineMidL | CERN | NO | CERNNO | N152 | ok
20220990290594 | N153 | fmSpineMidL | CERN | NO | CERNNO | N153 | ok
20220990290595 | N154 | fmSpineMidL | CERN | NO | CERNNO | N154 | ok
20220990290596 | N155 | fmSpineMidL | CERN | NO | CERNNO | N155 | ok
20220990290597 | N156 | fmSpineMidL | CERN | NO | CERNNO | N156 | ok
20220990290598 | N157 | fmSpineMidL | CERN | NO | CERNNO | N157 | ok
20220990290599 | N158 | fmSpineMidL | CERN | NO | CERNNO | N158 | ok
20220990290600 | N159 | fmSpineMidL | CERN | NO | CERNNO | N159 | ok
20220990290601 | N160 | fmSpineMidL | CERN | NO | CERNNO | N160 | ok
20220990290602 | N161 | fmSpineMidL | CERN | NO | CERNNO | N161 | ok
20220990290603 | N162 | fmSpineMidL | CERN | NO | CERNNO | N162 | ok
20220990290604 | N163 | fmSpineMidL | CERN | NO | CERNNO | N163 | ok
20220990290605 | N164 | fmSpineMidL | CERN | NO | CERNNO | N164 | ok
20220990290606 | N165 | fmSpineMidL | CERN | NO | CERNNO | N165 | ok
20220990290607 | N166 | fmSpineMidL | CERN | NO | CERNNO | N166 | ok
20220990290608 | N167 | fmSpineMidL | CERN | NO | CERNNO | N167 | ok

## inner spine stock
Serial Number | Mfr Serial No | Type | Current Location | Assembled? | tag | inspected | washer | washer batch | jig
20220990032347 | N13 01-06-02 | fmSpineInn | NIKHEF | NO | NIKHEFNO
20220990032348 | N11 01-06-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990032349 | N10 01-06-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990032350 | N04 01-06-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107506 | N16 30-09-02 | fmSpineInn | NIKHEF | NO | NIKHEFNO
20220990107507 | N17 30-09-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107508 | N18 30-09-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107509 | N19 30-09-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107510 | N20 30-09-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107550 | N23 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107551 | N24 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107552 | N25 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107553 | N26 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107554 | N27 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107555 | N28 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107556 | N29 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107557 | N30 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107558 | N31 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107559 | N32 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107560 | N33 30-09-02 | fmSpineInn | Freiburg | YES | FreiburgYES
20220990107561 | N34 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107562 | N35 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107563 | N36 30-09-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107564 | N37 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107565 | N38 30-09-02 | fmSpineInn | Munich MPI | NO | Munich MPINO
20220990107566 | N39 30-09-02 | fmSpineInn | Munich MPI | NO | Munich MPINO
20220990107567 | N40 30-09-02 | fmSpineInn | Munich MPI | NO | Munich MPINO
20220990107568 | N41 30-09-02 | fmSpineInn | Munich MPI | NO | Munich MPINO
20220990107569 | N42 30-09-02 | fmSpineInn | Munich MPI | NO | Munich MPINO
20220990107570 | N43 30-09-02 | fmSpineInn | Check Assembly Tree | YES | Check Assembly TreeYES
20220990107571 | N44 30-09-02 | fmSpineInn | NIKHEF | NO | NIKHEFNO
20220990107572 | N21 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107573 | N22 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990107574 | N15 30-09-02 | fmSpineInn | Freiburg | NO | FreiburgNO
20220990232724 | N45 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232725 | N46 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232726 | N47 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | new
20220990232727 | N48 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232728 | N49 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232729 | N50 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | new
20220990232730 | N51 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | new
20220990232731 | N52 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | new
20220990232732 | N53 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232733 | N54 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232734 | N55 7-03 | fmSpineInn | CERN | NO | CERNNO | ok | with washer | 02B05
20220990232735 | N56 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232736 | N57 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232737 | N58 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232738 | N61 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232739 | N62 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 03B05
20220990232740 | N63 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232741 | N64 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232742 | N66 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B05
20220990232743 | N67 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | 02B05
20220990232744 | N68 7-03 | fmSpineInn | CERN | trash | CERNtrash |  | with washer | glue coverage
20220990232745 | N69 7-03 | fmSpineInn | CERN | NO | CERNNO | ok | with washer | 02B05
20220990232746 | N70 7-03 | fmSpineInn | NIKHEF | YES | NIKHEFYES | ok | with washer | 02B05
20220990232747 | N71 7-03 | fmSpineInn | NIKHEF | YES | NIKHEFYES | ok | with washer | 02B05
20220990232748 | N72 7-03 | fmSpineInn | NIKHEF | YES | NIKHEFYES | ok | with washer | 02B05
20220990232749 | N73 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new | AlN replaced
20220990232750 | N74 7-03 | fmSpineInn | CERN | NO | CERNNO
20220990232751 | N75 7-03 | fmSpineInn | CERN | YES | CERNYES | ok | with washer | 02B05
20220990232752 | N76 7-03 | fmSpineInn | CERN | trash | CERNtrash |  | with washer | high resistivity
20220990232753 | N77 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990232754 | N78 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | 02B03
20220990232755 | N79 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | 02B03
20220990232756 | N80 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B03
20220990232757 | N81 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | 02B03
20220990232758 | N82 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232759 | N83 7-03 | fmSpineInn | CERN | NO | CERNNO
20220990232760 | N84 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232761 | N86 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232762 | N87 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232763 | N88 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232764 | N89 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232765 | N90 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232766 | N92 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232767 | N93 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232768 | N94 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232769 | N95 7-03 | fmSpineInn | NIKHEF | YES | NIKHEFYES | ok | with washer | new
20220990232770 | N97 7-03 | fmSpineInn | NIKHEF | YES | NIKHEFYES | ok | with washer | new
20220990232771 | N98 7-03 | fmSpineInn | CERN | trash | CERNtrash |  | with washer | glue coverage
20220990232772 | N99 7-03 | fmSpineInn | Freiburg | NO | FreiburgNO | ok | with washer | new
20220990232773 | N100 7-03 | fmSpineInn | CERN | trash | CERNtrash |  | with washer | glue coverage
20220990232774 | N101 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer | new
20220990232775 | N102 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO |  | with washer
20220990232776 | N103 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990232777 | N104 7-03 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288406 | N106 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288407 | N107 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288408 | N108 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288409 | N110 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990290707 | N111 | fmSpineInn | CERN | NO | CERNNO | ok | with washer
20220990288410 | N112 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288411 | N113 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288412 | N115 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288413 | N117 | fmSpineInn | NIKHEF | NO | NIKHEFNO | ok | with washer
20220990288274 | N118 10-03 | fmSpineInn | CERN | NO | CERNNO | ok
20220990288275 | N60 10-03 | fmSpineInn | CERN | NO | CERNNO | ok
20220990288276 | N116 10-03 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290609 | N65 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290610 | N119 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290611 | N120 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290612 | N121 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290613 | N122 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290614 | N123 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290615 | N124 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290616 | N125 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290617 | N126 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290618 | N127 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290619 | N128 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290620 | N129 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290621 | N130 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290622 | N131 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290623 | N132 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290624 | N133 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290625 | N134 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290626 | N135 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290627 | N136 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290628 | N137 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290629 | N138 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290630 | N139 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290631 | N140 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290632 | N141 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290633 | N142 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290634 | N143 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290635 | N144 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290636 | N145 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290637 | N146 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290638 | N147 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290639 | N148 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290640 | N149 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290726 | N150 | fmSpineInn | CERN | NO | CERNNO | ok
20220990290708 | N151 | fmSpineInn | CERN | NO | CERNNO | ok | with washer
20220990290709 | N152 | fmSpineInn | CERN | NO | CERNNO | ok | with washer
20220990290710 | N153 | fmSpineInn | CERN | NO | CERNNO | ok | with washer
20220990290711 | N154 | fmSpineInn | CERN | NO | CERNNO | ok | with washer
20220990290712 | N155 | fmSpineInn | CERN | NO | CERNNO | ok | with washer
20220990290713 | N156 | fmSpineInn | CERN | NO | CERNNO | ok | with washer