## Sheet1
type | site | make per week | make per day | have at site | days of prod | run out date | working days till nov 1 | required to keep going till nov 1 | max at site, including next delivery | days of prod | next delivery lasts them until
middle | MPI | 12 | 2.4 | 26 | 10.8333 | 2004-10-07 | 16 | 38.4 | 26 | 10.8333 | 2004-10-21
middle | Man | 12 | 2.4 | 29 | 12.0833 | 2004-10-11 | 14 | 33.6 | 27 | 11.25 | 2004-10-26
inner | Fre | 5 | 1 | 20 | 20 | 2004-10-21 | 6 | 6 | 88 | 88 | 2005-03-02
outer | Gen | 12 | 2.4 | 15 | 6.25 | 2004-10-01 | 20 | 48 | 112 | 46.6667 | 2004-12-06
outer | Val | 6 | 1.2 | 16 | 13.3333 | 2004-10-12 | 13 | 15.6 | 57 | 47.5 | 2004-12-16
outer | Mel | 4 | 0.8 | 0 | 0 |  |  | this shows us what is required from sept. shipment |  |  | this shows us when they run out after next delivery (assume types below)
|  | stock | next delivery | total by nov 1 | required | diff
| outer | 68 | 113 | 181 | 63.6 | 117.4
| middle | 32 | 22 | 54 | 72 | -18
| inner | 25 | 50 | 75 | 6 | 69
so fall 20 short in middles
if next delivery doesn’t arrive then can keep going until
|  | max can have | days of prod | last until
middle | MPI | 16 | 6.6667 | 2004-10-15
middle | Man | 16 | 6.6667 | 2004-10-19
inner | Fre | 25 | 25 | 2004-11-25
outer | Gen | 45 | 18.75 | 2004-10-27
outer | Val | 23 | 19.1667 | 2004-11-08
this is the date that production stops if next delivery doesn’t happen
note:
ASSUMED 100% yeild - this is NOT the case
Freiburg to make 192 inners in total, done 57 therefore make another 135
Manchester to make 192 middles in total, done 90, therefore make another 102
Manchester to make 192 inners in total, done 0, therefore make another 192
required spines
site | type | required spines to make remaining modules |  | total still needed | add 10% | (10%-have) | modules made | to make | left to make
Manchester | middle | 76 | outer | 558 | 613.8 | 442.8 | 86 | 192 | 106
| inner | 147 | middle | 405 | 445.5 | 397.5
Valencia | outer | 92 | inner | 270 | 324 | 246 | 51 | 125 | 102
Geneva | outer | 341 | total |  |  | 1086.3
NIKHEF | inner | 0
Freiburg | inner | 123 |  |  |  |  | 20 | 192 | 172
Melbourne | outer | 125
MPI | middle | 329 |  |  |  |  | 166 | 480 | 347
total at cern 27/09/2004
on way at moscow
|  |  | outer | 58 | 113
|  |  | middle | 26 | 22
|  |  | inner | 28 | 50
TPG required
to date 29/09/2004
NIITAP data on TPG used
long plates only
plates left = 300
received TPG plates = 1900-90 = 1810
used TPG plates = 1810 - 300 = 1510
spines ordered = 1672 (outer = 1021, middle = 651)
TPG still to make = 509 (outer = 348, middle = 161)
TPG still to process = 1672 -509 = 1163
So taken 1510 plates to make 1163 spines
yeild = 1163/1510 = 0.77
call it 0.75
So will require 509/0.75 = 679 TPG plates to make 509 spines
therefore need 679 - 300 - 130 = 249 plates
Required to order 250 more long TPG plates
ask for extra 10% increase = 275 plates
new spines order |  | TPG required |  | TPG required |  | Total TPG | at 52USD
outer | 49 | 65.3333 | long | 266.6667 |  | 550 | 28600
middle | 151 | 201.3333 | short | 200 |  | 200 | 5000
inner | 200 | 200
anatoli says 57000USD for 400 spines
no shipping costs
shipping to be paid for via ISTC agreement which will have to be funded
no TPG price included
NIITAP says need 570 long plates to finish ISTC
For extra 400 spines: 260 long and 200 short
there are 150 need long plates still to come
AlN required for 400 extra
45 plates 0.5mm thick, 20 plates 0.225mm thick
cost 1694.5 Euros
1kg of paralyne
cost 1400 Euros
Need to include cost of customs
(anatoli thinks about 800USD)

## from IHEP
What we require
Type | INTAS | 229 | ISTC | Total Spines produced | Type | spines needed to make modules | spines (modules + 10%) | required to make | difference from order | new order
Outer | 100 | 230 | 412 (113) | 742 (855)
Middle | 95 | 0 | 383 (21) | 478 (499) | Outer | 558 | 613.8 | 442.8 | 172.8 | 49
Inner | 95 | 0 | 244 (50) | 339 (389) | Middle | 405 | 445.5 | 397.5 | 270.5 | 151
Total | 290 | 230 | 1039 (184) | 1559 (1743) | Inner | 270 | 324 | 246 | 263 | 200
[5 empty] | Total | 1233 | 1383.3 | 1086.3 | 706.3 | 400
ISTC order
Type | Ordered | Made | % made | Still to make |  | numbers from required spines spreadsheet
Outer | 1021 | 751 | 73.56% | 270 | as of 2_12_2004
Middle | 651 | 524 | 80.49% | 127 |  | modules started | total to make | to make | spines needed | spines - at cern | left | after new order
Inner | 349 | 366 | 104.9% | -17 | Outer | 697 | 1124 | 427 | 469.7 | 279.7 | 9.7 | -39.3
Total | 2021 | 1223 | 60.51% | 798 | Middle | 373 | 768 | 395 | 434.5 | 292.5 | 165.5 | 14.5 | Problem!!!!
[5 empty] | Inner | 222 | 480 | 258 | 283.8 | 175.8 | 175.8 | -24.2
751 |  | 525 | 150 | 76
523 |  | 404 | 19 | 100
362 |  | 294 | 44 | 24
1223