# Protvino meeting – March 31st 2004

## Present:

Mike Tyndel, RAL

Alex Vorobiev, IHEP

Anatoli Kholodenko, IHEP

Inna Grigorieva, NIIGraphite

Alexandre Antanov, NIIGraphite

Larissa Pilavova, NIITAP

Boris Troisley, NIITAP

Hans-Guenther Moser, MPI

Phil Allport, Liverpool

Richard Bates, Glasgow

## Agenda

1: Spine quality and methods to improve yield

2: Agree a schedule for an accelerated production rate

3: Costs and new contracts

## Discussion

### Spine Quality

The quality of the spines has been improving.

AlN cracks on the whole have been due to the transport boxes. This has been improved recently with a lot of effort employed on the side of those at CERN to assure safe spine packaging. The number of AlN cracks has been reduced but there is still room for improvement. Further steps are to be taken to avoid damage in transport with a view to redesigned the boxes.

The need for the transport boxes to be returned was raised. TPG bow is due to thermally induced stress in the raw pyrographite where some bowing is unavoidable. The annealing procedure can be tailored to improve the bowing; however the highly annealed material with less of a bow is mechanically weaker. The best compromise should be to increase the annealing temperature to 3000o C. This has been introduced recently. NIITAP claims that this new material has better properties and needs no flattening.

The bowed spines need to be recorded on the flyer sheet and in the database.

A discussion of why the bow appears later in the spine production cycle was entered into. The need for a record of which spines had a bow and has been flattened is required for the lifetime of the spine to aid in the understanding of the bowing. Rapid feedback to IHEP of the bowing is needed.

Spacer thickness was discussed. HGM present data as:

Thickness top to top of 110 recent outer spines

Average = 1.225mm

RMS      = 0.040mm

Within +/- 50um = 76%

Dispersion (max difference between left, middle right)

> 50 micron: 54%

> 100 micron: 10%

The spacer gluing will be investigated by HGM and AK during this visit and corrective actions sought.

### Schedule

The number of spines delivered to CERN to date, was agreed as:

Inner	Middle		Outer		total

INTAS		95	95		100		290

Extra					229		229

ISTC		44	72		54		170

Total		139	167		382		689

IHEP have produced more than this number of spines but they are still at IHEP not at CERN. Therefore they are not delivered and cannot be counted as produced spines.

After some discussion it was agreed that:

The spines are required two months before they are required for module production.

And:

Needed for module production (to be produced, available are already subtracted)

April	May	June	July	Aug	Sep

Inner	61	44	33	110	44	55

Middle	140	84	49	66	115	107

Outer	115	126	100	70	77	144

It was clear that improved bookkeeping is needed by the SCT to understand the number of good spines used already, the number on hold pending rework and the number available to be used at CERN and at the assembly sites and the number remaining to be delivered.

TPG production at NIIGraphite:

1020 plates for spines have been produced under the ISTC contract (in addition to the ones used for the 229 ‘extra’). Yield at NIITAP is 80%, so this should be good for ~816 spines.

The present rate is about 150 plates per months (150 at maximum). This can be increased to 200 after some investments, after about two months lead time.

Total number to be produced should be increased from 2500 to 2800. It should be possible to accomplish this by November 2004 (with extra costs).

Details for an ideal production profile were discussed and will be detailed in the new contract.

Details of the additional work and associated costs to reach the new production rates are attached at the end of his document. In summary $18500 is required to improve furnace cooling, and to employ extra technicians. This will accelerate the TPG plate rate from 100/month to ~250/month.

TPG and AlN processing at NIITAP:

The steps in the TPG and AlN processing were presented (as according to the ISTC contract) and details of difficult areas and bottle necks discussed. The processes as NIITAP include polishing, machining and coating of the TPG. The yield is 80-85% due to the fragility of the recessed sections and the tight thickness tolerances.

Reviewing some of the processing stages:

TPG polishing: final polishing is done by hand by one person with one set of tooling. This is limited to a rate of 6/day per person. However, NIITAP said that 150/months could only be achieved at present by working overtime. Further increase needs a second workplace and person, plus training, which will take at least 3 month to achieve. NIITAP will pursue the purchase of the equipment and the employment of a new person. The cost for this will be included in a new contract with IHEP. MT and RLB will look into the possibility of performing these processes elsewhere.

It was stated that 550 spines have been polished to date for the ISTC contract.

TPG profiling: no problem. However, the thin machined TPG ends have been a cause of a low yield at the Parylene coating stage. If the thickness of the machined sections could be increased by 20um then the yield should increase.

Laser cutting of TPG: this is at present under control but this could become an issue if a 2nd laser cutter, ordered and paid for but not yet delivered by ISTC, is delayed still further. It was noted that the laser cutting could also be done at CERN.

Parylene coating: ok now, after changed to a St. Petersburg firm. Capacity available to cope with the accelerated production schedule, but they need the schedule one month in advance. Capacity is 60 pieces in a 6h run.

Ceramic pieces: in general this is under control, however there were two issues:

AlN pieces: Only bottleneck is the metallization. Need additional equipment to coat these at the required higher rate.

AlN laser cutting: could be a problem is the 2nd laser is delayed significantly; this could be done at MPI if required. However, it is not possible to perform the profiling of the AlN pieces at MPI.

It was decided that 5 spines will be produced that have an increase of 20um in the TPG thickness at the machined ends.

Assembly at IHEP:

The assembly of all the parts into a final spine at IHEP was not a bottleneck.

The need for a budget for spare components was raised. These are required to fix broken spines at CERN. This stage was not included in the original contract and therefore not budgeted for. Extra tooling and personnel are required to meet the accelerated production rate. This was costed at $22000 of which it was agreed that $7500 could come from the SCT and the remaining $14500 will be provided by IHEP.

The washer assembly must continue beyond July, the date at present that the arrangement of a IHEP technician at CERN ends. This technical support at CERN must be extended by a further 8 months from mid July. It was requested that IHEP provide this support.

## Addition costs

The additional costs to accelerate the production rate were presented by the three parties:

NIIGraphite:	10k$ for modifications of reactors, cooling

+8.5k$ as more reactors and people are needed (to finish in November)

NITAP: 	24.3 k$ for equipment and workplace to increase polishing rate

IHEP:              $11914 for additional transport boxes, additional shift for spine assembly

+ $10047 for additional ceramics and TPG sets required for repair.

Total:		$65361

## Actions

1) RLB – Improve book keeping of spines. To include the number of good spines used already, the number on hold pending rework and the number available to be used at CERN and the assembly sites and the number remaining to be delivered

2) RLB & AK – Discuss issues of the transport box

3) AK – Record which spines are flattened at Protvino before shipping to CERN

4) RLB – Record which spines are flattened at CERN before shipping to module construction sites

5) RLB – look at data from above to understand the nature of the bowing during transport from Protvino to CERN and transport from CERN to module production sites

6) RLB – fast feedback data on module bow to Protvino

7) RLB – remind production sites to ship back spine transport boxes to CERN

8) AK – Visit spacer control – thickness and gluing accuracy

9) HGM – give a specification for the dispersion of spacer position

10) HGM & AK – check tooling for spacer gluing

11) RLB – to invite Didier and Alan Clark to Protvino

12) RLB – Investigate options for a company that can grind and polish the TPG spines

13) LP – Investigate the purchase of a second set of polishing equipment and produce a quote

14) LP – Pursue the doubling of the TPG spine production rate via the hiring of extra people.

15) HGM – Enquire about the possibility of Laser cutting of AlN at Munich, due to the delay in the delivery of the second laser to NIITAP

16) MT – Talk to ISTC contact to speed up laser delivery

17) PA – Pursue a relaxation in the TPG thickness specifications, and increase in TPG thickness by 20um in the machined areas.

18) AK & HGM – Reduce glue thickness by 20um to compensate for increase in TPG thickness in the machined areas.

19) IG – Quote for increased TPG production rate.

20) LP – Obtain costing and deliverables for increased metallization rate of ALN pieces

21) LP – Quote and deliverable date for the jigging for paralyne coating to go to 60 per batch

22) RLB – Talk to S. Roe regarding the importing of items by hard at Geneva customs, in relation to hand transport of spines from Protvino.

23) MT – Talk to Zaitsev to continue technician at CERN for washer gluing until the end of the project.

24) PA – Draft contract with IHEP; to include ~$24000 for a second set of tooling and to employ a second person at NIITAP, and $22,000 ($7500 from SCT and $14500 from IHEP) to manufacture the spine assembly tooling, employ extra people and purchase spares to keep up with the accelerated spine production at IHEP.

25) AV – Obtain agreement with Zaitsev for the provision of the above $14500 from IHEP.

26) MT - Agree IHEP funding with Zaitsev

27) MT - Get draft of K-contract to Markus. Any modifications to be agreed by Phil Allport

28) AV – Extended, by ~8months from mid July, the technical support based at CERN for spine acceptance QA, washer gluing and spine measurements.

29) HGM – Set-up new MPI/NIGraphite contract

30) RLB – Start regular phone meetings with all concerned in the spine production line.

31) MT - Help NIGraphite via Koulberg to get funding sorted

## Details of extra work and associated costs for accelerated TPG production at NIIGraphite

1: Modification of the cooling system for current collectors of the press

$5000

2: Equipping an additional cooling table

$1000

3: Production of 3 additional reactors for annealing under pressure

$900

4: Labour – 1 man for annealing under pressure + 2 technicians. Training for the 4th class of electrical safety and annealing technology

$8900

5: Additional lathe, labour and installation of air cleaning system

$600

6: additional labour for polishing pistons, cutting and cleaning of TPG

$900

7: additional service and repair of the annealing system and test equipment

$600

8: additional pyrographite and graphite moulds for training and for the waste increase due to the new staff

$1200