ATLAS AGREEMENT No. XXX/YY

Accelerated Production of Spines to Achieve Overall Delivery at CERN by 1st December 2004

BETWEEN

The ATLAS Collaboration

Represented by the ATLAS SCT Project Leader,

on the one hand,

AND

The Institute of High Energy Physics, Protvino, Russia, hereinafter referred to as IHEP

Represented by the SCT Group Leader,

on the other hand.

CONSIDERING THAT:

- the ATLAS LHC experiment, as approved by CERN Director-General on 31 January 1996, contains a Inner Detector sub-system named "Silicon Tracker" (SCT);

- the Government of the Russian Federation and CERN have signed a “Protocol to the 1993 Co-operation Agreement between CERN and the Government of the Russian Federation concerning Participation in the Large Hadron Collider (LHC)”;

- IHEP has signed the “Memorandum of Understanding for Collaboration in the Construction of the ATLAS Detector” (MoU, ATLAS RRB-D 98-44 rev.);

-	IHEP has entered into an ISTC partner project agreement Nro “2731p” (hereafter referred to as “ISTC contract”) for the production of 2021 spines as part of its MoU contributions;

-	IHEP has entered into an INTAS contract “INTAS 99/249’ (hereafter referred to as “INTAS contract”) with INTAS for the production of 450 spines as part of its MoU contributions;

-	IHEP has entered into “ATLAS Agreement No. 130/03” (hereafter referred to as “ATLAS 130/03”) with ATLAS for the “Production of Additional Spines and Assembly of Washers for the ATLAS SCT Sub-system”;

-	IHEP has also committed to the MoU item ‘Endcap module components’ by 6.9% of a CORE value of 1070 kCHF which equals to 73.8 kCHF and MoU item ‘Endcap Engineering’ by 4.2% of a CORE value 2460 kCHF which equals 104 kCHF;

IT IS AGREED AS FOLLOWS:

ARTICLE 1	Scope of the Agreement

1.1	The scope of the present Agreement is the acceleration of spine delivery above the 127 per month (ISTC) described in Appendix 2 of ATLAS 130/03 to >200 good spines per month delivered at CERN and the additional payments from within the project that would be employed to achieve this.

Article 2	OBLIGATIONS OF THE PARTIES

2.1.1	 IHEP agrees to organize the additional resources required to meet the ATLAS schedule requirements shown in Appendix 1 of this document and to contribute 14,400 USD towards the additional costs.

2.1.2 	IHEP agrees to continue to provide a dedicated technician, beyond mid-July 2004 for a period of at least 6 months, to ensure completion of the assembly of 2,500 washers to the spines, using the jigs provided by the ATLAS SCT Collaboration on the basis outlined in ATLAS 130/03.

    - IHEP will pay all additional costs for any customs duties, or indirect or sales taxes that may appear during the execution of this Agreement. These payments will be accounted further as IHEP contribution to the ATLAS Project.

    - The ATLAS SCT Collaboration provides the IHEP technician at CERN with the jigs (15 units), washers, glue, and consumables and working area for assembly along with a detailed task and job description.

    - ATLAS (SCT Funding agencies other than IHEP) agrees to pay 7,500 USD at the start of this agreement towards additional tooling and will additionally pay 3000 USD for every month in which >200 good spines are delivered to CERN up to a grand total of 7,500 + 8 х 3,000 USD =  31,500 USD (including start-up costs). The acceptance at CERN is carried out by the SCT collaboration, led and represented by R.Bates. It is further understood that the minimum delivery per month of 127 good spines of Appendix 2 (ISTC) in ATLAS 130/03 be maintained throughout this period. Completion of the contract to the totals listed in Appendix 1 of this document, below, by 1st January 2005 will also guarantee full payment of the 31,500 USD from ATLAS SCT Funding Agencies other than IHEP.

    - The ATLAS SCT Collaboration provides the contract with Atomgraph (NIIGraphite) to create the necessary facilities to increase their production rate for TPG plates to be used for the SCT spine production and to increase the total number eventually needed. The costs for this are 19100 USD. The Max-Planck-Institut für Physik will sign and execute this contract with ATOMGRAPH on behalf of the SCT collaboration.

The payment will be divided in three installments:

Advance payment of 5000 USD, due May 1st,   2004

2nd installment of 7050 USD, due August 1st   2004

3rd installment of 7050 USD, due December 15, 2004,

The payments of the 2nd and 3rd installment will be made if the production has reached the level defined in Appendix 2.

ARTICLE 3	RECOGNITION OF THE CONTRIBUTIONS

3.1	The 45,900 USD agreed to achieve this accelerated production rate is to be provided by the Collaboration through 31,500 USD from SCT Funding Agencies other than IHEP and 14,400 USD from IHEP.

3.2 	The 19100 USD described in paragraph 2.1.6 is provided by the SCT collaboration and the payment is executed by Max-Planck Institut für Physik

3.3	The IHEP contribution, of 14,400 USD is to be offset against the 104 kCHF contribution to the MoU item line ‘Endcap Egineering’.

3.4	The value of the IHEP manpower contribution is recognized at 4,170 CHF per month, over 8 months following the schedule in appendix 1, and is also to be counted as part of the uncovered Russian MOU item relating to ‘Endcap Engineering’.

ARTICLE 4	DELIVERY SCHEDULE

4.1	The production of the spines is to meet the ATLAS requirements listed Appendix 1 with >200 spines per month and the delivery completed by 1st December 2004. The 316 required in April and 253 required in May reflect additional start up delays for which components are currently in production. As of 1st April 2004, 170 of the 2021 spines of the ISTC contract (start date October 2003) have already been delivered to CERN. The 229 Series Spines of ATLAS 130/03 Appendix 2 have also been delivered and most have been accepted.

4.2	IHEP is responsible to deliver the spines from Protvino to CERN in time       and in the good shape. The distribution of the spines between the modules production sites is the responsibility of  SCT-ATLAS.

ARTICLE 5	DURATION OF THE AGREEMENT

5.1	This Agreement is valid until 31.12.2004. It can, however, be extended in duration by mutual consent of both parties through the appropriate Memorandum.

ARTICLE 6	COORDINATION AND ADDRESSES FOR CORRESPONDANCE

6.1	All documents concerning this agreement shall bear the reference: ATLAS Agreement No. 130/03”.

6.2	The performance of this Agreement shall be co-ordinated by the following persons:

For ATLAS SCT: M. Tyndel, RAL, Chilton, UK-Didcot, OX11 OQX, UNITED KINGDOM

For IHEP: A. Vorobiev, IHEP, 1. Pobeda Street, 142281 Protvino, RUSSIA

ARTICLE 7	ARBRITRATION

7.1	Any differences arising during the execution of this agreement will be submitted to the Spokesperson of ATLAS who will propose solutions in the best interest of the Collaboration.

Signed in Geneva,

(M. Tyndel)		(A. Vorobiev)

ATLAS SCT Project Manager	SCT Group Leader, IHEP

(M. Nordberg)		(A. Zaitsev)

ATLAS Resources Coordinator	IHEP Group Leader

APPENDIX 1. SPINE DELIVERY SCHEDULE REQUIRED FOR ATLAS SCT FORWARD MODULE PRODUCTION

| Type | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outer | 115 | 126 | 100 | 70 | 77 | 144 | 66 | 54 |  |
| Middle | 140 | 84 | 49 | 66 | 115 | 107 | 66 | 30 |  |
| Inner | 61 | 44 | 33 | 110 | 44 | 55 | 66 | 30 |  |
| Total | 316 | 253 | 182 | 245 | 236 | 306 | 198 | 114 |  |
| Running Total | 316 | 570 | 752 | 997 | 1233 | 1539 | 1737 | 1851 |  |

APPENDIX 2. TPG DELIVERY SCHEDULE REQUIRED FOR ATLAS SCT FORWARD MODULE PRODUCTION

| Production months | Long plates | Short plates |
| --- | --- | --- |
| May | 140 | 30 |
| June | 240 | 80 |
| August | 220 | 80 |
| September | 220 | 80 |
| October | 216 | 50 |
| November | 94 | 30 |
| Total | 1130 | 350 |