|  | GridPP Project Management Board |
| --- | --- |

Resource Report

October 2002

|  | Document identifier : | GridPP-PMB-12-Resources |
| --- | --- | --- |
|  | Date: | 03/10/2002 |
|  | Version: | 0.1 |
|  | Document status: | DRAFT |
|  | Author | D. Britton |

# Overview

The following pie-chart shows the planned distribution of GridPP resources between the five major areas presented at the previous Oversight Committee meeting. The only change is a £0.04m transfer from the Operations to the Tier-1/A category. This arose as a better understanding of some costs (primarily the cost of Globus Support) freed up money to increase the support for Tier-1/A staff between April and September 2004.

The planned breakdown by financial year is shown in the table below. There has been a shift of about £1.0m from FY2002 into FY2003 (£0.4) and FY2004 (£0.6). This arises from changes in the CERN spending plans and due to the capping of UK hardware spending in FY2002. These will be discussed in more detail in the sections that follow.

# Actual Spend in FY2001

The actual spend in FY2001 is the combination of three numbers:

- Money Transferred to CERN: No funds were transferred to CERN during this period.

- Grants Paid by PPARC: The exact amount paid in Grants is subject to the method of calculation: According to the PPARC grant-issues dates, a total of £0.527m could have been spent in FY2001. However, using the real starting date of the grant-holders, the actual sum (used in the ProjectPlan) is estimated to be £0.390m. The difference between these two numbers reflects the sum of all the delays between issuing the grants and filling the positions.

- Money spent on the SLA via RAL:  The actual GridPP funds spent on the RAL SLA in FY2001 was £1.522m. This is lower than the planned number by £0.109m primarily due to the VAT on the hardware purchase slipping into FY02. This is detailed in the RAL SLA section below.

The total actual spend in FY2001 was therefore £0.390m + £1.522m = £1.912m compared to £2.015m in the planning table above.

# CERN

No money has yet actually been transferred to CERN. Appointments have been made for all the staff posts and many have already started. The staff cost profile in the table below represents the current estimate based on actual or intended starting dates.

The GridPP PMB recently approve a proposal from CERN to fund the purchase of tape drives and associated equipment at the level of £0.43m in place, partly, of the £0.30m initially allocated for the purchase of CPU and disks in FY2002. Although the tapes will be purchased in FY2002, CERN will bill PPARC in FY2003, thus assisting with the cash-flow problem. The purchases originally planned for FY2003 have been allowed to slip into FY2004, at least for billing purposes. These changes are reflected by the hardware line  in the table below.

# DataGrid

The table below shows the cost (Column-1) to GridPP of  DataGrid effort since the last oversight committee meeting (“Q6”  is April-June 2002), together with the planned (Column-2) and actual (Column-3) GridPP funded effort. The total Q6 effort in Column-4 includes EU funded and other non-GridPP funded effort. The cumulative cost in Column-5 shows the total expenditure by GridPP to the end of Q6; the last column shows the cumulative fraction of the contracted effort that has been delivered (GridPP and Non-GridPP funded) by the UK. More details are given in the DataGrid Q6 and draft Q7 Quarterly Reports.

The under-delivery of WP3 effort in Q6 was due to a redirection of the effort into WP4

.

# Tier-1/A

The table below shows the planned spending on staff and hardware on the Tier-1/A centre, according to financial year. The actual outturn from the RAL SLA for FY01 has recently been received and is presented under the RAL SLA section below. The planning below will be updated after the Oversight Committee has been presented with the comparison ( the main difference is that the actual hardware spend in FY01 is lower than planned because the VAT on the FY01 purchases has been carried forward into FY02).

The table below shows one significant change in planning from that presented previously: At the request of PPARC, the hardware expenditure in FY2002 has been capped at £400,000 and the balance of the original £775,000 has been shifted to FY2003. Once the outturn from FY01 has been included, the actual under-spend on hardware in FY01 will be shifted into FY04.

# Applications/Experiments

The table below presents a picture of the GridPP financial commitments from the perspective of the experiments in terms of both the Application posts and the WP8 DataGrid posts. There are very minor modifications to the table presented previously due to the inclusion of actual start-dates. The reporting back of this effort via the EB-reporting mechanism has been established for the last quarter, however this information was not available in time to include in this report. The intention in the future is to report on planned and actual effort in the latest period as for the DataGrid in the section above.

# Operations

The “Operations” category summarises commitments related to the running of the GridPP project. These are shown in the table below and are primarily the cost of GridPP Management posts and Travel. The Miscellaneous category is dominated by expenditure on travel and effort that occurred prior to the start of GridPP in September 2001. As noted earlier, there has been a slight reduction in the operational costs due to establishing the actual cost of Globus support. The FY01 travel has not yet been adjusted for the actual outturn (see RAL SLA section below).

# RAL SLA

The two tables below show summaries of the GridPP funds that are spent via the RAL SLA. The first table show the planned expenditure. The second table is an update that reflects the actual spend in FY01 and a suggested revision to planning for FY02-4. This arises because RAL reports (and bills) the actual staff effort on projects. A number of explanatory notes are given below.

Notes:

- There has been a significant increase in the average staff cost for FY01. This is mainly due to the average seniority of GridPP staff being higher than the departmental average. As more junior people join the project, this is expected to decline. A smaller effect is due to a different method of calculating and assigning overhead charges to SLA projects. This effect also contributes a small (less than 1%) increase to the average staff cost predicted for future years.

- The “Existing Staff Effort” in FY01 was higher than planned by 0.24SY. This is the combination of a number of changes but, most significantly, the addition of J.Jensen to work on WP5 (0.25SY).

- The hardware spend in FY01 is significantly lower than planned because the VAT (about £128K) has slipped into FY02. This will have to come out of the £400K available in FY02.

- The revised planning for FY02-04 presented in the second table above is an estimate/suggestion by RAL and GridPP may choose to adjust the exact profiles when the ProjectPlan is updated.

# Issues

The capping of funds available for hardware purchases in FY02 has reduced the planned expenditure from £0.775m to £0.400m. This problem is compounded by the fact that the VAT on FY01 purchases has slipped into FY02 and thus about £0.128m of the money available is already committed. GridPP will have to carefully monitor commitments to BaBar Tier-A development.

# Appendix – Travel

The figure below show the travel spend by GridPP for the current financial year (2002/03) up to the 23rd September 2002. It should be noted that a) the spend for August is light owing to the holiday season and b) the figures are as yet incomplete for September. Thus ignoring recent fluctuations, the spend is on track to come in within budget (£220k) by the end of the financial year.