## Sheet1
GridPP/CS bids for EU DataGrid Unfunded Posts at PPARC/Core
| WP1 |  |  | WP2 |  |  | WP3 |  |  | WP4 |  |  | WP5 |  |  | WP6 |  |  | WP7 |  |  | WP8 | [14 empty] | TOTAL |  |  | Status Oct'01
| B | A | F | B | A | F | B | A | F | B | A | F | B | A | F | B | A | F | B | A | F | ALICE |  |  | ATLAS |  |  | CMS |  |  | LHCb |  |  | CDF
Birmingham | [21 empty] | 0.5 |  |  | 0.5 | [11 empty] | 1 | 0 | 0 | ==
Bristol | [15 empty] | 0.5 |  | 0.5 | [9 empty] | 0.5 |  | 0.5 | [6 empty] | 1 | 0 | 1 | Appointed : starting end of 2001
Brunel | [6 empty] | 1 | [29 empty] | 1 | 0 | 0 | ==
Cambridge | [24 empty] | 1 | 0.5 | [10 empty] | 1 | 0.5 | 0 | Agreement on funding of other 0.5 FTE
CLRC | [9 empty] | 0.5 |  |  | 1 | 1 |  | 0.5 | 1 | [19 empty] | 2 | 2 | 0 | Preparing advert (close early Nov)
Edinburgh | [30 empty] | 1 | [5 empty] | 1 | 0 | 0 | ==
Edinburgh CS | [11 empty] | 1 | [24 empty] | 1 | 0 | 1 | Alexander Holt from 1st August
Glasgow |  |  |  | 0.5 | 0.5 | 1 | [9 empty] | 0.5 | [20 empty] | 1 | 0.5 | 1 | Gavin McCance started 1st Sept 01 (1FTE for 3 yrs), Will Bell starts 1st Nov (1FTE for 2 yrs)
IC |  |  | 0.5 | [14 empty] | 0.5 | [9 empty] | 1 | 1 | [7 empty] | 1 | 1 | 1 | Dave Colling from 1st Oct (WP1&6), Phillip Lewis from 1st Oct (WP8)
Lancaster |  |  |  | 0.5 | [8 empty] | 0.5 |  |  | 0.5 | [8 empty] | 0.5 | [11 empty] | 2 | 0 | 0 | ==
Liverpool | [11 empty] | 0.5 |  |  | 0.5 | [21 empty] | 0 | 0 | 1 | Michael George starts 1st Oct
Manchester | [15 empty] | 1 | 1 |  |  |  | 1 | [15 empty] | 1 | 1 | 1 | Advertised (closed 1st Sept)
Oxford | [15 empty] | 0.5 | [14 empty] | 1 | 1 |  | 0.5 |  |  | 2 | 1 | 0 | Advertised (closed 21st Sept)
QMUL | [6 empty] | 1 | 1 | [7 empty] | 1 | [20 empty] | 2 | 1 | 0 | Advertising (closing 1st November)
RHUL | [15 empty] | 0.5 | [8 empty] | 1 | 1 | [10 empty] | 1.5 | 1 | 0 | Advertising (closing 1st October)
Sheffield | [12 empty] | 0.5 | [11 empty] | 0.5 | [11 empty] | 1 | 0 | 0 | ==
UCL | [18 empty] | 0.5 |  | 1 |  |  |  | 0.5 | [11 empty] | 1 | 0 | 1 | Paul Mealor started 1st July
[22 empty] | 0.5 | 0 | 0 | 4 | 1.5 | 0 | 1.5 | 1 | 0.5 | 2 | 1 | 0 | 0.5 | 0 | 0
TOTAL | 0 | 0 | 0.5 | 1 | 0.5 | 1 | 2 | 1 | 0 | 0.5 | 0 | 1.5 | 2 | 1 | 0.5 | 5 | 2 | 1 | 0.5 | 0 | 2 | [6 empty] | 8.5 | 3.5 | 0.5 | [6 empty] | 19.5 | 8 | 7
Target | 0.5 |  |  | 1.5 |  |  | 1.8 |  |  | 0.5 |  |  | 1.5 |  |  | 3 |  |  | 2 | [8 empty] | 4 | [8 empty] | 14.8
Allocated | 0.5 |  |  | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 3 |  |  | 2 | [8 empty] | 4 | [8 empty] | 15
Required | 0 |  |  | 0 |  |  | 0.8 |  |  | -1 |  |  | 0 |  |  | 0 |  |  | 0 | [8 empty] | 0 | [8 empty] | -0.2
EU Funded | 0 |  |  | 0 |  |  | 3 |  |  | 0 |  |  | 1 |  |  | 0 |  |  | 0 | [8 empty] | 1 | [8 empty] | 5 |  |  | WP3 : Antony Wilson & Laurence Field in post
3rd post under offer
B = Bid for 2nd round | [39 empty] | WP5 : advertise, meanwhile use agency/short term staff
A = Allocated in 2nd round | [39 empty] | WP8 : Stephen Burke starts 1st Nov
F = Funded in 1st round
CS funded by PPARC and or Core programme
e-Science students:
| student: |  |  |  | supervisor: |  |  |  |  | area:
Bristol | Marc Kelly |  |  |  | Fergus Wilson |  |  |  |  | BaBar
Edinburgh | Alisdair Earl |  |  |  | Steve Playfer |  |  |  |  | WP2?
Glasgow | David Cameron |  |  |  | Tony Doyle |  |  |  |  | WP2
Liverpool | D. Jones |  |  |  | Themis Bowcock |  |  |  |  | WP4?
UCL | Y-T Li |  |  |  | Pete Clarke |  |  |  |  | WP7