## MasterMap
GridPP Goal
To develop and deploy a large scale science Grid
in the UK for the use of the Particle Physics community
| 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  |  | 7
CERN |  |  |  | DataGrid |  |  |  | Applications |  |  |  | Infrastructure |  |  |  | Interoperability |  |  |  | Dissemination |  |  |  |  | Resources
|  | 1 | 1 |  |  | 2 | 1 |  |  | 3 | 1 |  |  | 4 | 1 |  |  | 5 | 1 |  |  | 6 | 1 |  |  |  | 7 | 1
[9 empty] | ATLAS/LHCb | [7 empty] | International |  |  |  | Presentation |  |  |  |  | Deployment of
| LCG Creation |  |  |  | WP1 |  |  |  | GANGA/Gaudi |  |  |  | Tier-A Centre |  |  |  | Standards |  |  |  | of GridPP |  |  |  |  | resources
|  | 1 | 2 |  |  | 2 | 2 |  |  | 3 | 2 |  |  | 4 | 2 |  |  | 5 | 2 |  |  | 6 | 2 |  |  |  | 7 | 2
[9 empty] | CMS | [7 empty] | Open Source |  |  |  | Participation in |  |  |  |  | Monitoring of
| Applications |  |  |  | WP2 |  |  |  | Monte Carlo |  |  |  | Tier-1 Centre |  |  |  | Implementation |  |  |  | related areas |  |  |  |  | resources
System
|  | 1 | 3 |  |  | 2 | 3 |  |  | 3 | 3 |  |  | 4 | 3 |  |  | 5 | 3 |  |  | 6 | 3 |  |  |  | 7 | 3
[9 empty] | BaBar | [7 empty] | Worldwide |  |  |  | Engagement |  |  |  |  | Attract new
| Computing Fabric |  |  |  | WP3 |  |  |  | Data Analysis |  |  |  | Tier-2 Centres |  |  |  | Particle Physics |  |  |  | of UK groups |  |  |  |  | resources
Integration
|  | 1 | 4 |  |  | 2 | 4 |  |  | 3 | 4 |  |  | 4 | 4 |  |  | 5 | 4
[9 empty] | CDF/D0 | [7 empty] | UK e-Science
| Grid Technology |  |  |  | WP4 |  |  |  | SAM Framework |  |  |  | UK Testbed |  |  |  | Integration
MasterMap
|  | 1 | 5 |  |  | 2 | 5 |  |  | 3 | 5 |  |  | 4 | 5 | [8 empty] | Click on body of boxes to
[9 empty] | UKQCD | [14 empty] | reveal substructure.
| Grid Deployment |  |  |  | WP5 |  |  |  | QCD Application |  |  |  | UK Grid Rollout
[6 empty] | 2 | 6 |  |  | 3 | 6 |  |  | 4 | 6
Other
[5 empty] | WP6 |  |  |  | Applications |  |  |  | Data Challenges
[6 empty] | 2 | 7
WP7

## AttributeMap
GridPP Goal
To develop and deploy a large scale science Grid
in the UK for the use of the Particle Physics community
| 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7
CERN |  |  |  |  | DataGrid |  |  |  |  | Applications |  |  |  |  | Infrastructure |  |  |  |  | Interoperability |  |  |  |  | Dissemination |  |  |  |  | Resources
| J | 1 | 1 | K |  | J | 2 | 1 | K |  | J | 3 | 1 | K |  | J | 4 | 1 | K |  | J | 5 | 1 | K |  | J | 6 | 1 | K |  | J | 7 | 1 | K
| 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 |  | 2.1.1 | 2.1.2 |  |  |  | 3.1.1 | 3.1.2 | 3.1.3 | 3.1.4 |  | 4.1.1 | 4.1.2 | 4.1.3 | 4.1.4 |  | 5.1.1 | 5.1.2 | 5.1.3 |  |  | 6.1.1 | 6.1.2 | 6.1.3 | 6.1.4 |  | 7.1.1 | 7.1.2 | 7.1.3 | 7.1.4
[11 empty] | 3.1.5 | 3.1.6 | 3.1.7 | 3.1.8 |  | 4.1.5 | 4.1.6 | 4.1.7 | 4.1.8 | [6 empty] | 6.1.5
[11 empty] | 3.1.9 |  |  |  |  | 4.1.9
| J | 1 | 2 | K |  | J | 2 | 2 | K |  | J | 3 | 2 | K |  | J | 4 | 2 | K |  | J | 5 | 2 | K |  | J | 6 | 2 | K |  | J | 7 | 2 | K
| 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 |  | 2.2.1 | 2.2.2 | 2.2.3 | 2.2.4 |  | 3.2.1 | 3.2.2 | 3.2.3 | 3.2.4 |  | 4.2.1 | 4.2.2 | 4.2.3 | 4.2.4 |  | 5.2.1 | 5.2.2 | 5.2.3 |  |  | 6.2.1 | 6.2.2 | 6.2.3 |  |  | 7.2.1 | 7.2.2 | 7.2.3
| 1.2.5 | 1.2.6 |  |  |  | 2.2.5 | 2.2.6 | 2.2.7 |  |  | 3.2.5 | 3.2.6 | 3.2.7 | 3.2.8 |  | 4.2.5 | 4.2.6 | 4.2.7
[11 empty] | 3.2.9 | 3.2.10 | 3.2.11
| J | 1 | 3 | K |  | J | 2 | 3 | K |  | J | 3 | 3 | K |  | J | 4 | 3 | K |  | J | 5 | 3 | K |  | J | 6 | 3 | K |  | J | 7 | 3 | K
| 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 |  | 2.3.1 | 2.3.2 | 2.3.3 | 2.3.4 |  | 3.3.1 | 3.3.2 | 3.3.3 | 3.3.4 |  | 4.3.1 | 4.3.2 | 4.3.3 | 4.3.4 |  | 5.3.1 | 5.3.2 | 5.3.3 |  |  | 6.3.1 | 6.3.2 | 6.3.3 | 6.3.4 |  | 7.3.1 | 7.3.2 | 7.3.3 | 7.3.4
| 1.3.5 | 1.3.6 |  |  |  | 2.3.5 | 2.3.6 | 2.3.7 |  |  | 3.3.5 | 3.3.6 | 3.3.7 | 3.3.8 |  | 4.3.5 | [9 empty] | 6.3.5
[11 empty] | 3.3.9 | 3.3.10 | 3.3.11 | 3.3.12
| J | 1 | 4 | K |  | J | 2 | 4 | K |  | J | 3 | 4 | K |  | J | 4 | 4 | K |  | J | 5 | 4 | K
| 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 |  | 2.4.1 | 2.4.2 | 2.4.3 | 2.4.4 |  | 3.4.1 | 3.4.2 | 3.4.3 | 3.4.4 |  | 4.4.1 | 4.4.2 | 4.4.3 | 4.4.4 |  | 5.4.1 | 5.4.2 | 5.4.3 | 5.4.4
| 1.4.5 |  |  |  |  | 2.4.5 | 2.4.6 | 2.4.7 |  |  | 3.4.5 | 3.4.6 | 3.4.7 | 3.4.8 |  | 4.4.5 |  |  |  |  | 5.4.5
[11 empty] | 3.4.9 | 3.4.10 | 3.4.11 | 3.4.12
| J | 1 | 5 | K |  | J | 2 | 5 | K |  | J | 3 | 5 | K |  | J | 4 | 5 | K | [9 empty] | Task complete |  |  |  | 1.1.1
| 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 |  | 2.5.1 | 2.5.2 | 2.5.3 | 2.5.4 |  | 3.5.1 | 3.5.2 | 3.5.3 | 3.5.4 |  | 4.5.1 | 4.5.2 | 4.5.3 | 4.5.4 | [9 empty] | Metric OK |  |  |  | 1.1.1
| 1.5.5 | 1.5.6 | 1.5.7 |  |  | 2.5.5 | 2.5.6 | 2.5.7 |  |  | 3.5.5 | 3.5.6 | [16 empty] | Task due next quarter |  |  |  | 1.1.1
[29 empty] | Metric not OK |  |  |  | 1.1.1
[29 empty] | Task overdue |  |  |  | 1.1.1
[6 empty] | J | 2 | 6 | K |  | J | 3 | 6 | K |  | J | 4 | 6 | K | [9 empty] | Not yet defined |  |  |  | 1.1.1
[6 empty] | 2.6.1 | 2.6.2 | 2.6.3 | 2.6.4 |  | 3.6.1 | 3.6.2 | 3.6.3 |  |  | 4.6.1 | 4.6.2 | 4.6.3 | [10 empty] | No Task or metric
[6 empty] | 2.6.5 | 2.6.6 | 2.6.7 | 2.6.8
[6 empty] | 2.6.9 | [22 empty] | Navigate up |  |  |  | J
[29 empty] | Navigate down |  |  |  | K
[6 empty] | J | 2 | 7 | K
[6 empty] | 2.7.1 | 2.7.2 | 2.7.3 | 2.7.4
[6 empty] | 2.7.5 | 2.7.6 | 2.7.7 | 2.7.8
Note on E14: LCG Creation
Note on E19: LCG Applications
Note on E24: LCG Fabric
Note on E29: Grid Technology
Note on E34: Grid Deployment
Note on J14: WP1
Note on J19: WP2
Note on J24: WP3
Note on J29: WP4
Note on J34: WP5
Note on J39: WP6
Note on J44: WP7
Note on O14: ATLAS/LHCb
Note on O19: CMS
Note on O24: BaBar
Note on O29: CDF/D0 SAM
Note on O34: UKQCD
Note on O39: Other Apps
Note on T14: Tier-A
Note on T19: Tier-1
Note on T24: Tier-2
Note on T29: Testbed
Note on T34: Rollout
Note on T39: Data Challenges
Note on Y14: International Standards
Note on Y19: Open Source Implementation
Note on Y24: Worldwide Particle Physics Integration
Note on Y29: UK e-Science Integration
Note on AD14: Presentation
Note on AD19: Participation
Note on AD24: Engagement
Note on AI14: Deployment
Note on AI19: Monitoring
Note on AI24: New Resources

## 1.1
1.1.1 | UK funding helps seed creation of LCG |  |  |  | DUE | 2001-12-31
Description | Commitment of substantial UK funding helps to seed the creation of a large-scale international
Grid project at CERN.
Metric | Creation of project
Amount of additional funding attracted
Risk and/or | Other countries will not provide funding.
Dependency
Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
1.1.2 | Cross membership of GridPP and LCG |  |  |  | DUE | 2002-03-31
Description | To ensure the close connection of GridPP and LCG cross-membership of the projects is required
at the highest levels.
Metric | Establishment of cross-members on management bodies
Risk and/or
Dependency
Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
1.1.3 | LCG Plans |  |  |  | DUE | 2002-07-01
Description | LCG needs to develop a credible plan. UK should influence this if necessary.
Metric | Planning information publicly available.
Risk and/or
Dependency
Status | In progress | Status Date | 2002-06-05 | Modified Due Date |  | J
1.1.4 | LHC experiments embrace LCG developments |  |  |  | DUE | 2004-12-31
Description | The ultimate metric for success is that the LHC experiments adopt substantial parts of the LCG
product and that this is totally compatible with the developments in the UK.
Metric | ATLAS, CMS, LHCb, (ALICE) use LCG product on UK grid.
Risk and/or
Dependency
Status | Not Started | Status Date | 2002-06-05 | Modified Due Date |  | J

## 1.2
1.2
1 | 1.2.1 | Software Process Infrastructure in place |  |  | DUE | 2002-07-07
| Description | The LCG project requires an agreed software process and appropriate support tools, including
repository, configuration and release management tools. The components of the infrastructure
are to be defined by an RTAG created for this purpose.
| Metric | Agreed services are up and running by due date
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 1.2.2 | Prototype Hybrid Datastore completed |  |  | DUE | 2002-09-08
| Description | First version of hybrid eventstore released. Limited functionality only required and expected to
be used by experts only.
| Metric | Functionality, interfaces and documentation delivered according to requirements set at June
persistency workshop.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 1.2.3 | LCG-1 Applications Environment Defined |  |  | DUE | 2002-11-03
| Description | Each LHC experiment has a distinct application environment and other environment components
have been produced by IT. A common set must be selected to serve as the base for development
and for testing on the LCG prototypes
| Metric | Report from PEB by due date
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 1.2.4 | LCG-1 Applications Environment Software Available |  |  | DUE | 2003-01-05
| Description | Once the different components of the application environment have been defined, they must be
collected and made available centrally.
| Metric | software components identified in 1.1.3 available if software repository of 1.1.1
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 1.2.5 | General Release Hybrid Event Store |  |  | DUE | 2003-06-01
| Description | A more functional and robust (but not yet complete) version of the persistency framework.
This will be a release offering basic hybrid persistency services, properly documented and
packaged for general use by the experiments.
| Metric | Release made by due date.
LHC experiments able to make use of it.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 1.2.6 | Future Milestones |  |  | DUE | 2003-06-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 1.3
1.3
1 | 1.3.1 | Joint LCG/EDG cluster increased to 200 nodes |  |  | DUE | 2002-07-07
| Description | Contributed funding allows the acquisition of additional hardware components (CPU and disk
servers) to increase the size of the LCG/EDG cluster to 200 nodes.
| Metric | 200 Node installed.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 1.3.2 | Joint LCG/EDG Production Testbed Completed |  |  | DUE | 2002-09-08
| Description | The EDG Grid middleware is installed and running on the LCG/EDG cluster of 1.2.1
| Metric | The EDG Grid middleware is installed and running on the LCG/EDG cluster of 1.2.1
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 1.3.3 | LCG-1 Cluster increased to 400 nodes |  |  | DUE | 2003-01-05
| Description | As 1.2.1 for expansion to 400 nodes.
| Metric | 400 nodes installed
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 1.3.4 | LCG-1 Production Cluster Operational |  |  | DUE | 2003-01-26
| Description | The middleware components of 1.3.1 installed and running on the LCG-1 cluster (1.2.3)
| Metric | The middleware components of 1.3.1 installed and running on the LCG-1 cluster (1.2.3)
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 1.3.5 | Cluster Automation Complete |  |  | DUE | 2003-03-30
| Description | Automated tools for installation of LCG-1 cluster available.
Precise set of tools depends on EDG and other developments (c.f. 1.3.1), but tools should adhere
to principles of the EDG WP4 architecture and design document.
| Metric | As above
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 1.3.6 | Future Milestones |  |  | DUE | 2003-06-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 1.4
1.4
1 | 1.4.1 | Middleware Components Defined |  |  | DUE | 2002-10-20
| Description | As for applications environments, there are various competing sources of the different
Grid middleware components. A single set must be defined for LCG use.
| Metric | Single set of components defined.
| Risk and/or | It is hoped that GLUE will produce agreement on middleware
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 1.4.2 | Testing and Validation Process Defined |  |  | DUE | 2002-12-01
| Description | Testing and Validation Process Defined
| Metric | Definition established
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 1.4.3 | Middleware Components Assembled, Tested and Available |  |  | DUE | 2003-02-02
| Description | The middleware components identified in 1.3.1 are available in an agreed location for LCG, e.g.
the repository identified in 1.1.1
| Metric | Middleware Components Assembled, Tested and Available
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 1.4.4 | Full Test Suite Completed |  |  | DUE | 2003-03-30
| Description | Full Test Suite Completed
| Metric | Full Test Suite Completed
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 1.4.5 | Future Milestones |  |  | DUE | 2003-06-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 1.5
1.5
1 | 1.5.1 | Complete Specification of LCG-1 |  |  | DUE | 2002-11-24
| Description | Agreement is reached on the level of resources required for LCG-1 and how these are to be
distributed across at least 5 sites in 3 continents.
| Metric | Specification available
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 1.5.2 | Institutes Fabric Ready to Install |  |  | DUE | 2003-02-02
| Description | Acquisition and installation of agreed hardware.
| Metric | The institutes identified in 1.4.1 have completed the acquisition and installation of the agreed
hardware.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 1.5.3 | Certification Started |  |  | DUE | 2003-02-16
Description
Installation of agreed middleware (1.3.1) on hardware of 1.4.2.
| Metric | Certification Started
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 1.5.4 | Certification and LCG-1 Build and Delivery complete |  |  | DUE | 2003-05-04
Description
All the agreed hardware and software is up and running at each individual LCG-1 site.
| Metric | Certification and LCG-1 Build and Delivery complete
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 1.5.5 | Commissioning Started |  |  | DUE | 2003-05-04
| Description | This is the start of the process to bring the different sites together to form a coherent LCG-1.
| Metric | Commissioning Started
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 1.5.6 | Commissioning Completed |  |  | DUE | 2003-06-01
Description
| Metric | The application software of 1.1.3 runs successfully on the LCG-1 service.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
7 | 1.5.7 | Future Milestones |  |  | DUE | 2003-06-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 2.1
2.1
1 | 2.1.1 | Deliver WP1 Effort |  |  | DUE | on going
| Description | Deliver WP1 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.1.2 | Install and Test |  |  | DUE
| Description | Install and test EDG WP1 software
UK responsibility as part of an EDG-wide effort
| Metric | Working WP1 software in the UK
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J

## 2.2
2.2
1 | 2.2.1 | Deliver WP2 Effort |  |  | DUE | on going
| Description | Deliver WP2 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.2.2 | Technology Assessment |  |  | DUE | 2001-04-30
| Description | D2.1 Report of current technology
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.2.3 | Requirements & Architecture |  |  | DUE | 2001-06-30
| Description | D2.2 Detailed report on requirements, architectural design, and evaluation criteria
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.2.4 | First Project Release |  |  | DUE | 2001-09-30
| Description | D2.3 Components and documentation for the first Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.2.5 | Second Project release |  |  | DUE | 2002-09-30
| Description | D2.4 Components and documentation for the second Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
6 | 2.2.6 | Final Project Release |  |  | DUE | 2003-09-30
| Description | D2.5 Components and documentation for the final Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
7 | 2.2.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D2.6 Final evaluation report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.3
2.3
1 | 2.3.1 | Deliver WP3 Effort |  |  | DUE | on going
| Description | Deliver WP3 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.3.2 | Technology review |  |  | DUE | 2001-12-12
| Description | D3.1 Current Technology Evaluation
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.3.3 | Architecture |  |  | DUE | 2001-09-30
| Description | D3.2 Architecture Design
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.3.4 | First Prototype |  |  | DUE | 2001-09-30
| Description | D3.3 First Prototype
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.3.5 | Second Prototype |  |  | DUE | 2002-09-30
| Description | D3.4 Second Prototype
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
6 | 2.3.6 | Final Prototype |  |  | DUE | 2003-09-30
| Description | D3.5 Final Prototype
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
7 | 2.3.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D3.6 Final Evaluation Report
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.4
2.4
1 | 2.4.1 | Deliver WP4 Effort |  |  | DUE | on going
| Description | Deliver WP4 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.4.2 | Technology review |  |  | DUE | 2001-04-30
| Description | D4.1 Report of current technology
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.4.3 | Architecture |  |  | DUE | 2001-06-30
| Description | D4.2 Architectural design report and evaluation criteria
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.4.4 | First project release |  |  | DUE | 2001-09-30
| Description | D4.3 Components and documentation for the first project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.4.5 | Second project release |  |  | DUE | 2002-09-30
| Description | D4.4 Components and documentation for the second project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
6 | 2.4.6 | Final project release |  |  | DUE | 2003-09-30
| Description | D4.5 Components and documentation for the final project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
7 | 2.4.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D4.6 Final evaluation report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.5
2.5
1 | 2.5.1 | Deliver WP5 Effort |  |  | DUE | on going
| Description | Deliver WP5 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.5.2 | Technology review |  |  | DUE | 2001-03-31
| Description | D5.1 Report of current technology
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.5.3 | Architecture |  |  | DUE | 2001-06-30
| Description | D5.2 Detailed architectural design report and evaluation criteria
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.5.4 | First Project release |  |  | DUE | 2001-09-30
| Description | D5.3 Components and documentation for the first project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.5.5 | Second Project release |  |  | DUE | 2002-09-30
| Description | D5.4 Components and documentation for the second project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
6 | 2.5.6 | Final Project release |  |  | DUE | 2003-09-30
| Description | D5.5 Components and documentation for the third project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
7 | 2.5.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D5.6 Final evaluation report
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.6
2.6
1 | 2.6.1 | Deliver WP6 Effort |  |  | DUE | on going
| Description | Deliver WP6 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.6.2 | Integration & Operation |  |  | DUE | 2001-04-30
| Description | D6.1 Testbed software integration process, operational policies and procedures report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.6.3 | Policies, evaluation and procedures |  |  | DUE | 2001-06-30
| Description | D6.2 Project release policy, definitions, evaluation targets and procedures
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.6.4 | First project release |  |  | DUE | 2001-09-30
| Description | D6.3 First project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on first project release deliverables from middleware workpackages
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.6.5 | First project release evaluation |  |  | DUE | 2001-12-31
| Description | D6.4 Evaluation of testbed operation
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful deployment of first project release
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
6 | 2.6.6 | Second project release |  |  | DUE | 2002-09-30
| Description | D6.5 Second project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on second project release deliverables from middleware workpackages
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
7 | 2.6.7 | Second project release evaluation |  |  | DUE | 2002-12-31
| Description | D6.6 Evaluation of testbed operation
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful deployment of second project release
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
8 | 2.6.8 | Final project release |  |  | DUE | 2003-09-30
| Description | D6.7 Final project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on final project release deliverables from middleware workpackages
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
9 | 2.6.9 | Final project release evaluation |  |  | DUE | 2003-12-31
| Description | D6.8 Final evaluation of testbed operation
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful deployment of second project release
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.7
2.7
1 | 2.7.1 | Deliver WP7 Effort |  |  | DUE | on going
| Description | Deliver WP7 effort as contracted
Primarily a UK responsibility
| Metric | Man months deviation from plan
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.7.2 | Network infrastructure report |  |  | DUE | 2001-09-30
| Description | D7.1 Report on network infrastructure for Testbed 1
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.7.3 | Deploy monitoring |  |  | DUE | 2001-12-31
| Description | D7.2 Demonstration and deployment of monitoring tools
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.7.4 | Infrastructure & services |  |  | DUE | 2002-06-30
| Description | D7.3 Intermediate report on network infrastructure and services
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
5 | 2.7.5 | Final report |  |  | DUE | 2003-12-31
| Description | D7.4 Final Report on network infrastructure and services
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J
6 | 2.7.6 | Interim security report |  |  | DUE | 2002-03-31
| Description | D7.5 Security Report on first project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.7.7 | Security Design |  |  | DUE | 2003-01-31
| Description | D7.6 Security Design report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
8 | 2.7.8 | Final Security report |  |  | DUE | 2003-12-31
| Description | D7.7 Final security report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 3.1
3.1
1 | 3.1.1 | Requirements, Architecture and Design Definition |  |  | DUE | 2002-06-30
| Description | Document that establishes LHCb requirements for Grid based analysis and MC production.
Document establishes architecture constraints and leads to detailed design definition
| Metric | Document
| Risk and/or | None
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 3.1.2 | Prototype of Grid Interface |  |  | DUE | 2002-09-30
| Description | Command line interface allows simple Gaudi analysis and Monte Carlo production jobs to be
submitted to EDG testbed sites. Job submission scripts automatically generated and some
error handling available.
| Metric | Demonstration of prototype for LHCb and ATLAS in the UK.
| Risk and/or | None
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 3.1.3 | Webpage mock GUI for feedback |  |  | DUE | 2002-09-30
| Description | A simple web-page mock up of the GANGA GUI design to allow user feedback
| Metric | Creation of web-page mock GUI
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 3.1.4 | Remote Grid Mass-Storage Write Capability |  |  | DUE | 2002-09-30
| Description | Demonstration that the EDG RFIO from WP5 works in the LHCb context.
| Metric | Demonstration of basic functionality.
| Risk and/or | Depends on RFIO being produced by EDG WP5
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 3.1.5 | First GANGA Prototype |  |  | DUE | 2003-03-31
| Description | GANGA prototype that includes user interaction regarding resource requests and the ability to
generate the JDL and an interface to MDS. Will also include monitoring tools and checkpointing.
| Metric | LHCb demonstration of defined functionality.
| Risk and/or | EDG WP1 and WP3 tools
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 3.1.6 | User-Controlled Site Configuration |  |  | DUE | 2003-09-30
| Description | Development of syntax of a generic site configuration file.
| Metric | Demonstration of test Gaudi/Athena jobs running on Grid using standard conditions
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
7 | 3.1.7 | Second GANGA Prototype |  |  | DUE | 2004-03-31
| Description | GANGA prototype that includes GUI access to middleware and Gaudi/Athena services.
Functionality includes translation of meta-data into physical files; replica service to optimise location
of data; query facility to estimate resources; monitoring facilities for submitted jobs.
| Metric | Demonstration of prototype with specified functionality.
| Risk and/or | EDG WP1 WP2 WP3 services.
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
8 | 3.1.8 | Interface experiment Grid tools to GANGA |  |  | DUE | 2004-09-30
| Description | Incorporated MC production system into GANGA supporting user-query of environment. Interface to
experiment specific installation tools.
| Metric | Demonstration of prototype with specified functionality.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
9 | 3.1.9 | Final GANGA Version |  |  | DUE | 2004-12-31
| Description | Document and demonstration of final GANGA product.
| Metric | Document and demonstration in LHCb and ATLAS contexts.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 3.2
3.2.1 | Production of CMS Monte Carlo on testbed |  |  | DUE | 2002-11-30
Description | The BOSS and IMPALA programs will be modified to produce the cmkin and cmsim parts
of the MC data samples using the grid testbeds. The data will be staged directly to the SE and
published in the replica catalogue using GDMP.
Metric | 2TB of data produced in a Grid-like way in the UK for CMS data challenge.
Risk and/or | CMS international MC production effort delayed.
Dependency | Stable testbed.
Status | Not started | Status Date | Modified Due Date |  | J
3.2.2 | Prototype Regional Data-Centre |  |  | DUE | 2002-11-30
Description | The RAL Tier-1 facilities will be used to store more than 20TB of CMS simulated data in flat files
and will act as a repository for the CMS collaboration worldwide. All data will be published in a
replica catalogue via GDMP and made available worldwide.
Metric | >20TB of data stored at RAL, published in a replica catalogue and available worldwide.
Risk and/or | GDMP release is not adequate. Storage is not available.
Dependency | Stable testbed; SE support; robust storage facilities; stable GDMP
Status | Not started | Status Date | Modified Due Date |  | J
3.2.3 | External Monitoring of CMS Application |  |  | DUE | 2002-11-30
Description | Using existing sample CMS applications, such as are currently being used for Monte Carlo
analysis, we will produce externally monitored data of CPU load, data transfer rate, queuing times
etc.
Metric | Useful statistical data on CPU load, data transfer rate and queuing times for sample CMS
application.
Risk and/or | Stable testbed.
Dependency
Status | Not started | Status Date | Modified Due Date |  | J
3.2.4 | CMS Monte Carlo Analysis |  |  | DUE | 2003-06-30
Description | Provide a simple job submission framework for ORCA based reconstruction and analysis jobs.
Framework will allow simple job partitioning and aggregation of the output.
Metric | CMS users will be able to submit jobs to testbed with simple job partitioning and aggregation.
Risk and/or | Stable testbed; EDG WP1 implementation of job partitioning. EDG release
Dependency | to ensure a consistent execution environment.
Status | Not started | Status Date | Modified Due Date |  | J
3.2.5 | CMS Web Portal |  |  | DUE | 2003-09-30
Description | Implementation of web portal for MC production and analysis
Metric | CMS users will be able to submit production and analysis jobs to UK testbed via a web interface
Risk and/or | Stable testbed.
Dependency
Status | Not started | Status Date | Modified Due Date |  | J
3.2.6 | Object Persistency |  |  | DUE | 2003-12-31
Description | An important CMS milestone is the Integration of new persistent objects in CMS software.
The UK will need to install and test this development that will be based on the LCG
recommendations.
Metric | CMS software runs in production mode using the LCG common LHC solution to persistent objects
Risk and/or | LCG recommendations; adoption and implementation by CMS
Dependency
Status | Not started | Status Date | Modified Due Date |  | J
3.2.7 | CMS Grid Status Document |  |  | DUE | 2003-12-31
Description | Review of the current functionality of CMS grid-tools for production, monitoring and analysis.
The document will produce recommendations for future higher-level functionality with a focus on
data-handling, scheduling efficiency, and ease of use.
Metric | Document describing current grid-tools and future emphasis.
Risk and/or | CMS grid tools will have to have reached some level of maturity and be
Dependency | widely deployed.
Status | Not started | Status Date | Modified Due Date |  | J
3.2.8 | Internal Monitoring of CMS Applications |  |  | DUE | 2003-12-31
Description | The CMS COBRA framework does not interact directly with the Grid. To enable internal monitoring,
services will need to be attached via a monitoring portal to BOSS. A simple CLI toolkit will be
provided for data analysis with some simple alarms.
Metric | Toolkit provided for simple internal monitoring of CMS analysis jobs and a demonstration
application.
Risk and/or | Stable testbed release. WP1 and WP3 monitoring tools.
Dependency
Status | Not started | Status Date | Modified Due Date |  | J
3.2.9 | Full instrumentation of CMS Applications |  |  | DUE | 2004-06-30
Description | This is the completion of the instrumentation task for application monitoring. It includes the
database server and an interface to the local schedulers.
Metric | Standard CMS software available, fully instrumented with EDG monitoring services.
Risk and/or | Stable testbed release. WP1 and WP3 monitoring tools.
Dependency
Status | Not started | Status Date | Modified Due Date |  | J
3.2.10 | Monitoring Simulation and Analysis Tools |  |  | DUE | 2004-12-31
Description | These tools are to provide a user-friendly interface to the monitoring data obtained from
instrumented CMS applications. They will allow real-time and off-line analysis.
Metric | User-friendly interface to CMS monitoring data made available.
Risk and/or | Stable testbed release. WP1 and WP3 monitoring tools.
Dependency
Status | Not started | Status Date | Modified Due Date |  | J
3.2.11 | CMS Grid |  |  | DUE | 2004-12-31
Description | Final deployment of CMS grid enabled software incorporating functionality identified in 3.2.7.
Metric | Deployment of CMS grid software in the UK.
User documentation and final report.
Risk and/or | Stable testbed.
Dependency
Status | Not started | Status Date | Modified Due Date |  | J

## 3.4
3.4
1 | 3.4.1 | Architecture Design |  |  | DUE | 2002-06-30
| Description | Document describing architecture to be used for the upgrade of SAM
| Metric | Document is produced
| Risk and/or | None
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 3.4.2 | Prototype CDF-SAM Interface |  |  | DUE | 2002-06-30
| Description | A preliminary interface between the CDF analysis framework and SAM including a GUI for large
scale declaration of data-sets to SAM and an interface to the SAM data retrieval system.
| Metric | Demonstration of functionality on UK site.
| Risk and/or | None
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 3.4.3 | Phase-1 SAM Development |  |  | DUE | 2002-09-30
| Description | SAM modified to include GridFTP transport option; Condor-G job submission to a hand-chosen
remote site; decentralised SAM information services.
| Metric | Demonstration of functionality on a UK site.
| Risk and/or | May be problems with interface to GSI.
| Dependency | Depends on Condor-g deployment.
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 3.4.4 | Final CDF-SAM interface |  |  | DUE | 2002-09-30
| Description | Based upon prototype results, final design will be implemented.
| Metric | Demonstration of interface on UK site.
| Risk and/or | Depends on prototype. |  |  | 3.4.2
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 3.4.5 | CDF Monte Carlo Production as a SAM Task. |  |  | DUE | 2002-12-31
| Description | Extend CDF use of SAM from simple file retrieval to fully integrated Monte Carlo production.
| Metric | Demonstration of CDF Monte Carlo production using SAM in the UK
| Risk and/or | Depends on completion of related work within the CDF collaboration to
| Dependency | allow communication with various databases (geometry, calibration, etc).
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 3.4.6 | Prototype SAM Monte Carlo Production system using Resource Broker |  |  | DUE | 2003-03-31
| Description | Extension of SAM functionality to include use of resource broker. Will also include monitoring
services and request interface.
| Metric | Demonstration of SAM prototype with specified functionality in the UK.
| Risk and/or | Depends on D0 architecture definition |  |  | 3.4.1
| Dependency | and development of associated areas within D0
| Status | Not started | Status Date | Modified Due Date |  | J
7 | 3.4.7 | Demonstration of CDF/SAM jobs moving to data. |  |  | DUE | 2003-03-31
| Description | Adaptation of SAM to move jobs to data as an option needs to be integrated into CDF framework.
| Metric | Demonstration of CDF/SAM jobs moving to data in the UK.
| Risk and/or | Depends on development of this SAM functionality by the core SAM team.
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
8 | 3.4.8 | Report on first year SAM/CDF Progress |  |  | DUE | 2003-03-31
| Description | A brief summary document that describes progress in the first year and highlights problems and
issues. This will be used to set/modify targets for the remainder of the project.
| Metric | Document produced
| Risk and/or | None
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
9 | 3.4.9 | Pilot SAM Grid for D0 users. |  |  | DUE | 2003-09-30
| Description | Documentation and demonstration of a limited D0-grid based on SAM capable of providing a service
to 'intelligent users' in the UK. Functionality includes automated submission of Monte Carlo and
analysis jobs.
| Metric | Documented demonstration.
| Risk and/or | Depends on much associated work with core SAM team and D0
| Dependency | collaboration.
| Status | Not started | Status Date | Modified Due Date |  | J
10 | 3.4.10 | Demonstration of SAM as a Data Handling System for CDF |  |  | DUE | 2003-12-31
| Description | Deliver SAM for use on CDF's central analysis facility as the data handling system.
| Metric | Demonstration of SAM for data handling in UK and Fermilab
| Risk and/or | Depends on formal adoption of SAM by CDF
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
11 | 3.4.11 | Robust SAM-based grid service for D0 |  |  | DUE | 2004-03-31
| Description | Demonstration and documentation of a robust SAM-based service for significant D0 physics
production tasks suitable for use by general collaboration members.
| Metric | Documented demonstration
| Risk and/or | Depends on development of SAM and D0 software and by formal
| Dependency | acceptance by the D0 collaboration.
| Status | Not started | Status Date | Modified Due Date |  | J
12 | 3.4.12 | Final Report on SAM/CDF integration |  |  | DUE | 2004-12-31
| Description | A document on the final product for CDF. Issues addressed include the technical success of the
integration of SAM and the degree to which CDF has adopted this for data handling.
| Metric | Document
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 3.5
3.5
1 | 3.5.1 | Develop XLM schema for lattice QCD calculations |  |  | DUE | 2002-06-30
| Description | Develop an XLM schema to define the format of the metadata documents for lattice QCD data files
| Metric | Schema defined.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 3.5.2 | Develop meta-data catalogue for simulation data |  |  | DUE | 2002-06-30
| Description | Develop and XML database server for storing and querying lattice QCD metadata. Access will be
via command-line tools.
| Metric | Demonstration of command line access to meta-data catalogue.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 3.5.3 | Develop browser for meta-data catalogue |  |  | DUE | 2002-09-30
| Description | Develop browser to allow users to query metadata catalogue. Brower will supply a single interface
to the metadata and ultimately the data.
| Metric | Demonstration of browser access to metadata catalogue.
| Risk and/or |  |  |  | 3.5.2
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 3.5.4 | Implement four-site data-storage and access |  |  | DUE | 2002-09-30
| Description | Deployment of a small grid using EG testbed release middleware, allowing all members of UKQCD
access to data at all four sites (via browser and/or line commands at this point).
| Metric | Users can access data in a site-transparent manner.
| Risk and/or | Stable EDG middleware
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 3.5.5 | Prototype web portal for data access and local job submission |  |  | DUE | 2003-03-31
| Description | Develop simple portal to allow data to be gathered from remote site and local analysis jobs to be
submitted
| Metric | Demonstration of functionality
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 3.5.6 | Web-portal allows remote job submission |  |  | DUE | 2003-12-31
| Description | Extension of 3.5.5 to allow remote job submission based on EDG released middleware.
| Metric | Remote job submission possible.
| Risk and/or | Stable EDG release |  |  | 3.5.5
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 3.6
3.6
1 | 3.6.1 | One non-funded application has used UK testbed |  |  | DUE | 2002-09-30
Description
| Metric | One non-funded application has used UK testbed
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 3.6.2 | Two non-funded application have used testbed |  |  | DUE | 2003-09-30
Description
| Metric | Two non-funded application have used testbed
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 3.6.3 | Significant bids for resources by non-funded applications |  |  | DUE | 2004-12-31
| Description | There are significant bids for GridPP resources from applications that were not directly funded by
the GridPP programme.
| Metric | Fraction of resources requested by non-funded applications
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 4.1
4.1
1 | 4.1.1 | 2002 BaBar common fund rebate is agreed. |  |  |  | DUE | 2002-04-01
| Description | BaBar agrees that Tier-A hardware generates common-fund rebate
| Metric | Common fund rebate.
| Risk and/or | BaBar does not agree.
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
2 | 4.1.2 | New Tier-A hardware installed |  |  |  | DUE | 2002-10-01
| Description | New Tier-A hardware installed and demonstrated to meet requirements.
| Metric | Hardware is tested at full capacity and available for use.
Risk and/or
Dependency
| Status | In Progress | Status Date |  | Modified Due Date |  | J
3 | 4.1.3 | BaBar Successfully use Tier-A Hardware |  |  |  | DUE | 2002-12-31
| Description | Tier-A hardware is successfully incorporated into BaBar production.
| Metric | BaBar using more than 80% of hardware reserved for its use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
4 | 4.1.4 | 2003 BaBar common fund rebate is agreed. |  |  |  | DUE | 2003-04-01
| Description | BaBar agrees that new Tier-A hardware generates common-fund rebate
| Metric | Common fund rebate.
| Risk and/or | BaBar does not agree.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
5 | 4.1.5 | New Tier-A hardware installed |  |  |  | DUE | 2003-03-31
| Description | New Tier-A hardware installed and demonstrated to meet requirements.
| Metric | Hardware is tested at full capacity and available for use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
6 | 4.1.6 | BaBar Successfully use Tier-A Hardware |  |  |  | DUE | 2003-09-30
| Description | Tier-A hardware is successfully incorporated into BaBar production.
| Metric | BaBar using more than 80% of hardware reserved for its use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
7 | 4.1.7 | 2004 BaBar common fund rebate is agreed. |  |  |  | DUE | 2004-03-31
| Description | BaBar agrees that new Tier-A hardware generates common-fund rebate
| Metric | Common fund rebate.
| Risk and/or | BaBar does not agree.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
8 | 4.1.8 | New Tier-A hardware installed |  |  |  | DUE | 2004-09-30
| Description | New Tier-A hardware installed and demonstrated to meet requirements.
| Metric | Hardware is tested at full capacity and available for use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 4.1.9 | BaBar Successfully use Tier-A Hardware |  |  |  | DUE | 2004-12-31
| Description | Tier-A hardware is successfully incorporated into BaBar production.
| Metric | BaBar using more than 80% of hardware reserved for its use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.2
4.2
1 | 4.2.1 | 2002 Tier-1 hardware commissioned |  |  | DUE | 2002-10-01
| Description | Hardware installed and demonstrated to meet tender specifications
300 CPUs and 40TB of disk shared with BaBar.
| Metric | Purchase accepted
Hardware available for use.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 4.2.2 | Tier-1 Centre used. |  |  | DUE | 2002-12-31
| Description | Hardware should meet the needs (as far as possible) of the LHC experiments
| Metric | LHC experiments use more than 80% of hardware nominally reserved for their use for
substantial periods.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 4.2.3 | 2003 Tier-1 hardware commissioned |  |  | DUE | 2003-10-01
| Description | Hardware installed and demonstrated to meet tender specifications
| Metric | Purchase accepted
Hardware available for use.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 4.2.4 | Tier-1 Centre used. |  |  | DUE | 2003-12-31
| Description | Hardware should meet the needs (as far as possible) of the LHC experiments
| Metric | LHC experiments use more than 80% of hardware nominally reserved for their use.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 4.2.5 | 2004 Tier-1 hardware commissioned |  |  | DUE | 2004-10-01
| Description | Hardware installed and demonstrated to meet tender specifications
| Metric | Purchase accepted
Hardware available for use.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
6 | 4.2.6 | Tier-1 Centre used. |  |  | DUE | 2004-12-31
| Description | Hardware should meet the needs (as far as possible) of the LHC experiments
| Metric | LHC experiments use more than 80% of hardware nominally reserved for their use.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
7 | 4.2.7 | Tier-1 Centre meets target size. |  |  | DUE | 2004-12-31
| Description | Tier-1 Centre meets target size.
| Metric | Expect 2000 nodes and 500TB in the UK. Approximately 50% in Tier-1.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 4.3
4.3
1 | 4.3.1 | Tier-2 centre preliminary definition established |  |  | DUE | 2002-10-01
| Description | The role and structure of Tier-2 centres is currently being examined by an LCG group. GridPP will
consider this input in establishing a preliminary definition for UK Tier-2 centres.
| Metric | Document specifying Tier-2 centres
| Risk and/or | LCG report delayed
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 4.3.2 | Location of UK Tier-2 centres established |  |  | DUE | 2003-01-01
| Description | GridPP plans to establish about 4 Tier-2 centres in the UK. Once the formal specification is made
discussions with likely candidates will begin with a goal of establishing the location of centres.
| Metric | Formal commitment by four institutions to become Tier-2 centres for at least the remainder of the
current GridPP project.
| Risk and/or | Resources are not available at institutions. |  |  | 4.3.1
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 4.3.3 | Tier-2 architecture and development plan established |  |  | DUE | 2003-07-01
| Description | The identified Tier-2 centres will be engaged in the discussion of how the Tier-2 resources will
evolve to a level where the total UK tier-2 resources are similar to the UK Tier-1 resources (but
without substantial funding from GridPP). Plans for both architecture and development are needed.
| Metric | Agreed plans with each Tier-2 centre on architecture and development over the following 2 years.
| Risk and/or | Tier-2 centres are unable to attract resources
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
4 | 4.3.4 | Tier-2 centers meet preliminary definition specification |  |  | DUE | 2003-10-01
| Description | Tier-2 centres are expected to have met at least the preliminary specifications.
| Metric | Tier-2 centres have resources to match agreed definition.
| Risk and/or |  |  |  | 4.3.1
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
5 | 4.3.5 | Tier-2 centers developed according to plan |  |  | DUE | 2004-12-01
| Description | By the end of the current GridPP project the Tier-2 centres should have developed according to the
plan established in 4.3.3
| Metric | Degree to which Tier-2 centres match planned level of resources.
| Risk and/or | Tier-2 centres fail to attract resources. |  |  | 4.3.3
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 4.4
4.4
1 | 4.4.1 | UK testbed is established |  |  |  | DUE | 2002-05-01
| Description | Initial UK testbed established as a distinct entity separate from EDG testbed.
| Metric | At least 5 members; a single resource broker and replica catalogue.
Simple jobs should run
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
2 | 4.4.2 | BaBar simulation or analysis demonstration |  |  |  | DUE | 2002-10-01
| Description | BaBar simulation or analysis demonstration on the UK testbed
| Metric | Successful submission and completion of BaBar jobs
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
3 | 4.4.3 | Core-sites part of EDG testbed |  |  |  | DUE | 2002-10-01
| Description | The UK testbed core-sites (i.e. with WP6 posts: RAL, ICSTM, Manchester, Bristol) should by this
time be part of the EDG testbed
| Metric | RAL, ICSTM, Manchester, and Bristol members of the EDG testbed.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
4 | 4.4.4 | Testbed demonstration |  |  |  | DUE | 2003-04-01
| Description | Demonstration that the UK testbed has grown to include a mixture of resources.
| Metric | Demonstration of application running across heterogeneous resources such as EDG testbed PLUS
dedicated BaBar resources.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
5 | 4.4.5 | Tier-2 Centre Integration |  |  |  | DUE | 2003-10-01
| Description | By this time at least one Tier-2 centre should be part of the UK testbed
| Metric | Tier-2 centre is part of testbed
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.5
4.5
1 | 4.5.1 | Preliminary Rollout Plan Established |  |  |  | DUE | 2002-05-01
| Description | Initial planning for the Grid rollout in the UK is undertaken.
| Metric | Rollout plan presented to PMB
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
2 | 4.5.2 | Installation Instruction Set Tested |  |  |  | DUE | 2002-09-01
| Description | Preliminary instructions set for joining/using Grid should be tested on three category-2 sites.
| Metric | Tests completed on three sites.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
3 | 4.5.3 | Grid Rolled Out to Category-2 Sites |  |  |  | DUE | 2003-04-01
| Description | All interested category-2 sites should now be involved.
| Metric | Involvement of all interested category-2 sites.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
4 | 4.5.4 | Grid rolled out to category-3 (turn-key) users |  |  |  | DUE | 2004-10-01
| Description | By this time the UK Grid should be available to Turn-Key users according to the developed rollout
plan.
| Metric | Number of institutes in the UK engaged.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.6
4.6
1 | 4.6.1 | One LHC Experiment uses significant UK resources |  |  | DUE | 2002-09-30
| Description | At least one LHC Experiment should have used significant UK resources for a data challenge
| Metric | At least 1TB of data produced in the UK
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
2 | 4.6.2 | Two LHC Experiments using significant UK resources |  |  | DUE | 2003-03-30
| Description | At least two LHC experiments should be using significant UK resources for data challenges.
| Metric | At least 3TB of data produced in the UK in data challenges.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J
3 | 4.6.3 | Three LHC Experiments using significant UK resources |  |  | DUE | 2003-12-31
| Description | Three LHC experiments should be using significant UK resources for data challenges.
| Metric | At least 10 TB of data should have been produced in UK data challenges
At least 20TB of data should be stored and available to worldwide community through catalogue.
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 5.1
5.1
1 | 5.1.1 | GGF Standards |  |  | DUE | on going
| Description | GridPP will make every effort to align with GGF standards in order to ensure interoperability
To help accomplish this GridPP members will attend GGF meetings.
| Metric | Number of GridPP members attending GGF meetings
| Current Total |  | 20
| Current Threshold |  | 10
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 5.1.2 | GGF Standards |  |  | DUE | on going
| Description | GridPP will make every effort to align with GGF standards in order to ensure interoperability
This will be assisted if GridPP members contribute to GGF working groups.
| Metric | Number of GridPP members belonging to formal GGF groups.
| Current Total |  | 2
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 5.1.3 | GGF Standards |  |  | DUE | on going
| Description | GridPP will make every effort to align with GGF standards in order to ensure interoperability
| Metric | Ultimately this is measured by the number of times GGF standards are broken by GridPP.
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 5.2
5.2
1 | 5.2.1 | Open Source Development |  |  | DUE | on going
| Description | GridPP hopes to contribute open source packages to the community
| Metric | Number of packages contributed to the open source community
| Current Total |  | 0
| Current Threshold |  | 0
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 5.2.2 | Open Source Use |  |  | DUE | on going
| Description | GridPP will endeavor to use open source products where possible.
| Metric | Number of external packages used which are not open source.
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 5.2.3 | Open Source Conflict |  |  | DUE | on going
| Description | Number of times when an open source approach is not adhered to by GridPP
| Metric | Number of times when an open source approach is not adhered to by GridPP
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 5.3
5.3
1 | 5.3.1 | InterGrid |  |  | DUE | on going
| Description | GridPP will promote interoperability through the InterGrid project
To help accomplish this GridPP members will be part of the InterGrid technical board.
| Metric | Number of GridPP members of InterGrid Technical Board (HIJTB)
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 5.3.2 | InterGrid |  |  | DUE | on going
| Description | GridPP will promote interoperability through the InterGrid project
To help accomplish this GridPP members will be part of the InterGrid Collaboration Board
| Metric | Number of GridPP members of InterGrid Collaboration Board (HIJCB)
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 5.3.3 | InterGrid |  |  | DUE | on going
| Description | A measure of success is how well GridPP manages to adhere to InterGrid agreements
| Metric | Number of times InterGrid agreements are broken by GridPP
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 5.4
5.4
1 | 5.4.1 | E-Science Centres |  |  | DUE | on going
| Description | A measure of the integration of GridPP with the UK e-Science centres is the number of GridPP
members belonging to the e-Science Centre Technical Boards.
| Metric | Number of GridPP members of e-Science Centre Technical Boards.
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 5.4.2 | E-Science Centres |  |  | DUE | on going
| Description | A measure of the integration of GridPP with the UK e-Science centres is the number of GridPP
members belonging to the e-Science Centre Executive Boards.
| Metric | Number of GridPP members of e-Science Centre Executive Boards.
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 5.4.3 | JISC |  |  | DUE | on going
Description
| Metric | The number of GridPP members belonging to JISC Technical Boards
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
4 | 5.4.4 | JISC |  |  | DUE | on going
Description
| Metric | The number of GridPP members belonging to JISC Executive Boards
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
5 | 5.4.5 | e-Science Support Tools |  |  | DUE | on going
Description
| Metric | The number of e-Science supported tools relevent to GridPP that are not adopted by GridPP.
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 6.1
6.1
1 | 6.1.1 | GridPP Presentations |  |  | DUE | on going
| Description | Dissemination of GridPP work via presentations to other physicists, other scientists, industry,
or the general public.
| Metric | Number of presentations
| Current Total |  | 2
| Current Threshold |  | 2
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 6.1.2 | GridPP Workshops |  |  | DUE | on going
| Description | Dissemination of GridPP work via technical workshops.
| Metric | Number of workshops
| Current Total |  | 2
| Current Threshold |  | 2
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 6.1.3 | GridPP Demonstrations and Posters |  |  | DUE | on going
| Description | Dissemination of GridPP work via demonstrations or posters
| Metric | Number of demonstrations and posters
| Current Demo Total |  | 3 | Current PosterTotal | 5
| Current Threshold |  | 1 | Current Threshold | 3
| Status | Not started | Status Date | 2002-06-05 |  | J
4 | 6.1.4 | GridPP Conference Presentations |  |  | DUE | on going
| Description | Dissemination of GridPP at related conferences
| Metric | Number of presentations
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J
5 | 6.1.5 | GridPP Publications |  |  | DUE | on going
| Description | Dissemination of GridPP work by publication
| Metric | Number of Publications
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 6.2
6.2
1 | 6.2.1 | GridPP Representation at related events |  |  | DUE | on going
| Description | To promote communication, GridPP members will attend related events.
| Metric | Number of interactions
| Current Total |  | 2
| Current Threshold |  | 2
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 6.2.2 | GridPP Involvement with e-Science Centres |  |  | DUE | on going
| Description | To promote communication, GridPP will endeavor to keep the e-Science centres involved by
actively seeking contact.
| Metric | Number of interactions
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 6.2.3 | GridPP Membership of Related Projects |  |  | DUE | on going
| Description | To promote the work of GridPP, members will belong to related projects and will keep these projects
up to date with the work of GridPP
| Metric | Number of members of related projects
| Current Total |  | 3
| Current Threshold |  | 3
| Status | Not started | Status Date | 2002-06-05 |  | J

## 6.3
6.3
1 | 6.3.1 | External use of GridPP Products |  |  | DUE | on going
| Description | Engagement of the community can be measured by the number of non-GridPP funded groups
who make use of GridPP middleware, or technical assistance.
| Metric | Number of external groups
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 6.3.2 | External use of GridPP Infrastructure |  |  | DUE | on going
| Description | Engagement of the community can be measured by the number of non-GridPP funded groups
who make use of the GridPP infrastructure.
| Metric | Number of external Groups
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 6.3.3 | Press Articles |  |  | DUE | on going
| Description | The engagement of outside interest may be measured by the number of articles about GridPP
written by non members.
| Metric | Number of articles in the scientific or general press.
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J
4 | 6.3.4 | GridPP Web-site Hits |  |  | DUE | on going
| Description | The external interest in GridPP can be measured by counting the number of hits on the GridPP
website from external sources.
| Metric | Number of external hits.
| Current Total |  | 10
| Current Threshold |  | 10
| Status | Not started | Status Date | 2002-06-05 |  | J
5 | 6.3.5 | Enquires about GridPP |  |  | DUE | on going
| Description | The external interest in GridPP can be measured by the number of formal enquires about GridPP by
external bodies or individuals.
| Metric | Number of enquires relayed to the Collaboration Chair.
| Current Total |  | 1
| Current Threshold |  | 1
| Status | Not started | Status Date | 2002-06-05 |  | J

## 7.1
7.1
1 | 7.1.1 | Resource Deployment by Area |  |  | DUE | on going
| Description | The fraction of resources deployed according to current planning is a measure of effective
resource management
| Metric | Fraction deployed according to plan
| Current Total |  | 100%
| Current Threshold |  | 95%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 7.1.2 | Lost Effort |  |  | DUE | on going
| Description | Effort lost due to slow hiring is a measure of how effectively the resources are deployed.
| Metric | Number of lost man-months
| Current Total |  | 12
| Current Threshold |  | 6
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 7.1.3 | Hardware Delays |  |  | DUE | on going
| Description | Any delay in hardware purchases beyond planned schedule is a measure of how effectively
the process is managed.
| Metric | Number of months delay
| Current Total |  | 0
| Current Threshold |  | 2
| Status | Not started | Status Date | 2002-06-05 |  | J
4 | 7.1.4 | Travel Budget |  |  | DUE | on going
| Description | The match between the travel spend and the travel budget reflects on how well the travel budget
is managed.
| Metric | Travel overspend
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 7.2
7.2
1 | 7.2.1 | Monitoring Mechanism |  |  | DUE | 2002-05-01
| Description | An easy to use mechanism for monitoring effort in the project on a quarterly basis is required
| Metric | Development of Mechanism
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
2 | 7.2.2 | Monitoring Implementation |  |  | DUE | 2002-09-01
| Description | The monitoring mechanism needs to be implemented and run.
| Metric | First full run of monitoring mechanism completed.
Risk and/or
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J
3 | 7.2.3 | Monitoring information processing |  |  | DUE | 2002-10-01
| Description | A semi-automated mechanism for processing the monitoring information needs to be developed
| Metric | Development of processing system
Risk and/or
Dependency
| Status | In Progress | Status Date | 2002-06-05 |  | J

## 7.3
7.3
1 | 7.3.1 | Non GridPP-funded Effort |  |  | DUE | on going
| Description | UK effort on GridPP (or EDG within the UK context) not funded by GridPP (or the EU).
| Metric | Amount of effort in Man Months
| Current Total |  | 0.05
| Current Threshold |  | 0
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 7.3.2 | Non-GridPP-funded resources at Tier-2 Centres |  |  | DUE | on going
| Description | The resources (hardware and posts) at Tier-2 Centres not funded by GridPP.
Metric
| Current Hardware Total |  | £600,000 | Current Number of FTE Total | 0
| Current Threshold |  | £0 | Current Threshold | 0
| Status | In Progress | Status Date | 2002-06-05 |  | J
3 | 7.3.3 | Other non GridPP-funded resources in the UK |  |  | DUE | on going
| Description | Other hardware resources in the UK dedicated to GridPP usage.
| Metric | Hardware value (purchase cost).
| Current Total |  | £100,000
| Current Threshold |  | £0
| Status | In Progress | Status Date | 2002-06-05 |  | J
4 | 7.3.4 | Additional funding Opportunities |  |  | DUE | on going
| Description | The extension of GridPP due to new funding initiatives such as SR2002 or FW-VI
| Metric | Value of additional funding
| Current Total |  | £0
| Current Threshold |  | £0
| Status | Not started | Status Date | 2002-06-05 |  | J