## MasterMap
GridPP Goal
To develop and deploy a large scale science Grid
in the UK for the use of the Particle Physics community
H | 1 |  | I |  | H | 2 |  | I |  | H | 3 |  |  |  | H | 4 |  |  |  | H | 5 |  |  |  | H | 6 |  |  |  | H | 7
CERN |  |  |  |  | DataGrid |  |  |  |  | Applications |  |  |  |  | Infrastructure |  |  |  |  | Interoperability |  |  |  |  | Dissemination |  |  |  |  | Resources
| K | 1 | 1 | I |  | K | 2 | 1 | I |  | K | 3 | 1 | I |  | K | 4 | 1 | I |  | K | 5 | 1 | I |  | K | 6 | 1 | I |  | K | 7 | 1 | I
| LCG Creation |  |  |  |  | WP1 |  |  |  |  | ATLAS |  |  |  |  | Tier-A Centre |  |  |  |  | International |  |  |  |  | Presentation |  |  |  |  | Deployment of
[21 empty] | Standards |  |  |  |  | of GridPP |  |  |  |  | resources
| K | 1 | 2 | I |  | K | 2 | 2 | I |  | K | 3 | 2 | I |  | K | 4 | 2 | I |  | K | 5 | 2 | I |  | K | 6 | 2 | I |  | K | 7 | 2 | I
I
| Applications |  |  |  |  | WP2 |  |  |  |  | ATLAS/LHCb |  |  |  |  | Tier-1 Centre |  |  |  |  | Open Source |  |  |  |  | Participation in |  |  |  |  | Monitoring of
[11 empty] | GANGA/Gaudi | [9 empty] | Implementation |  |  |  |  | related areas |  |  |  |  | resources
| K | 1 | 3 | I |  | K | 2 | 3 | I |  | K | 3 | 3 | I |  | K | 4 | 3 | I |  | K | 5 | 3 | I |  | K | 6 | 3 | I |  | K | 7 | 3 | I
Worldwide
| Computing Fabric |  |  |  |  | WP3 |  |  |  |  | LHCb |  |  |  |  | Tier-2 Centres |  |  |  |  | Particle Physics |  |  |  |  | Engagement |  |  |  |  | Attract new
[21 empty] | Integration |  |  |  |  | of UK groups |  |  |  |  | resources
| K | 1 | 4 | I |  | K | 2 | 4 | I |  | K | 3 | 4 | I |  | K | 4 | 4 | I |  | K | 5 | 4 | I
CMS
| Grid Technology |  |  |  |  | WP4 |  |  |  |  | Monte Carlo |  |  |  |  | UK Testbed |  |  |  |  | UK e-Science
[11 empty] | System | [9 empty] | Integration
| K | 1 | 5 | I |  | K | 2 | 5 | I |  | K | 3 | 5 | I |  | K | 4 | 5 | I
| Grid Deployment |  |  |  |  | WP5 |  |  |  |  | BaBar |  |  |  |  | UK Grid Rollout
[11 empty] | Data Analysis | [16 empty] | Navigate down |  |  |  | K
[28 empty] | External link |  |  |  | I
[6 empty] | K | 2 | 6 | I |  | K | 3 | 6 | I |  | K | 4 | 6 | I | [8 empty] | Link to goals |  |  |  | H
I
[6 empty] | WP6 |  |  |  |  | CDF/D0 |  |  |  |  | Data Challenges
SAM Framework
[6 empty] | K | 2 | 7 | I |  | K | 3 | 7 | I
[6 empty] | WP7 |  |  |  |  | UKQCD
QCD Application
[6 empty] | K | 2 | 8 | I |  | K | 3 | 8 | I
[6 empty] | WP8 |  |  |  |  | Other
Applications

## AttributeMap
GridPP Goal
To develop and deploy a large scale science Grid
in the UK for the use of the Particle Physics community
H | 1 |  | I |  | H | 2 |  | I |  | H | 3 |  |  |  | H | 4 |  |  |  | H | 5 |  |  |  | H | 6 |  |  |  | H | 7
CERN |  |  |  |  | DataGrid |  |  |  |  | Applications |  |  |  |  | Infrastructure |  |  |  |  | Interoperability |  |  |  |  | Dissemination |  |  |  |  | Resources
| LCG Creation |  |  |  |  | WP1 |  |  |  |  | ATLAS |  |  |  |  | Tier-A |  |  |  |  | Int. Standards |  |  |  |  | Presentation |  |  |  |  | Deployment
| J | 1 | 1 | K |  | J | 2 | 1 | K |  | J | 3 | 1 | K |  | J | 4 | 1 | K |  | J | 5 | 1 | K |  | J | 6 | 1 | K |  | J | 7 | 1 | K
| 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 |  | 2.1.1 | 2.1.2 | 2.1.3 | 2.1.4 |  | 3.1.1 | 3.1.2 | 3.1.3 | 3.1.4 |  | 4.1.1 | 4.1.2 | 4.1.3 | 4.1.4 |  | 5.1.1 | 5.1.2 | 5.1.3 |  |  | 6.1.1 | 6.1.2 | 6.1.3 | 6.1.4 |  | 7.1.1 | 7.1.2 | 7.1.3 | 7.1.4
| 1.1.5 |  |  |  |  | 2.1.5 | 2.1.6 | 2.1.7 | 2.1.8 |  | 3.1.5 | 3.1.6 | 3.1.7 | 3.1.8 |  | 4.1.5 | 4.1.6 | 4.1.7 | 4.1.8 | [6 empty] | 6.1.5
[6 empty] | 2.1.9 |  |  |  |  | 3.1.9 | 3.1.10 |  |  |  | 4.1.9
| Applications |  |  |  |  | WP2 |  |  |  |  | ATLAS/LHCb |  |  |  |  | Tier-1 |  |  |  |  | Open Source |  |  |  |  | Participation |  |  |  |  | Monitoring
| J | 1 | 2 | K |  | J | 2 | 2 | K |  | J | 3 | 2 | K |  | J | 4 | 2 | K |  | J | 5 | 2 | K |  | J | 6 | 2 | K |  | J | 7 | 2 | K
| 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 |  | 2.2.1 | 2.2.2 | 2.2.3 | 2.2.4 |  | 3.2.1 | 3.2.2 | 3.2.3 | 3.2.4 |  | 4.2.1 | 4.2.2 | 4.2.3 | 4.2.4 |  | 5.2.1 | 5.2.2 | 5.2.3 |  |  | 6.2.1 | 6.2.2 | 6.2.3 |  |  | 7.2.1 | 7.2.2 | 7.2.3
| 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 |  | 2.2.5 | 2.2.6 | 2.2.7 |  |  | 3.2.5 | 3.2.6 | 3.2.7 | 3.2.8 |  | 4.2.5 | 4.2.6 | 4.2.7
| 1.2.9 | 1.2.10 | [8 empty] | 3.2.9
| Fabric |  |  |  |  | WP3 |  |  |  |  | LHCb |  |  |  |  | Tier-2 |  |  |  |  | Worldwide Integration |  |  |  |  | Engagement |  |  |  |  | Developing
| J | 1 | 3 | K |  | J | 2 | 3 | K |  | J | 3 | 3 | K |  | J | 4 | 3 | K |  | J | 5 | 3 | K |  | J | 6 | 3 | K |  | J | 7 | 3 | K
| 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 |  | 2.3.1 | 2.3.2 | 2.3.3 | 2.3.4 |  | 3.3.1 | 3.3.2 | 3.3.3 | 3.3.4 |  | 4.3.1 | 4.3.2 | 4.3.3 | 4.3.4 |  | 5.3.1 | 5.3.2 | 5.3.3 |  |  | 6.3.1 | 6.3.2 | 6.3.3 | 6.3.4 |  | 7.3.1 | 7.3.2 | 7.3.3 | 7.3.4
| 1.3.5 | 1.3.6 | 1.3.7 | 1.3.8 |  | 2.3.5 | 2.3.6 | 2.3.7 |  |  | 3.3.5 | 3.3.6 |  |  |  | 4.3.5
| 1.3.9 | 1.3.10 | 1.3.11
| Technology |  |  |  |  | WP4 |  |  |  |  | CMS |  |  |  |  | Testbed |  |  |  |  | UK Integration
| J | 1 | 4 | K |  | J | 2 | 4 | K |  | J | 3 | 4 | K |  | J | 4 | 4 | K |  | J | 5 | 4 | K
| 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 |  | 2.4.1 | 2.4.2 | 2.4.3 | 2.4.4 |  | 3.4.1 | 3.4.2 | 3.4.3 | 3.4.4 |  | 4.4.1 | 4.4.2 | 4.4.3 | 4.4.4 |  | 5.4.1 | 5.4.2 | 5.4.3 | 5.4.4 |  |  |  | Status Date |  |  |  | 2003-10-01
| 1.4.5 | 1.4.6 | 1.4.7 | 1.4.8 |  | 2.4.5 | 2.4.6 | 2.4.7 |  |  | 3.4.5 | 3.4.6 | 3.4.7 | 3.4.8 |  | 4.4.5 | 4.4.6 |  |  |  | 5.4.5
| 1.4.9 | [9 empty] | 3.4.9 | 3.4.10 | [16 empty] | Metric OK |  |  |  | 1.1.1
| Deployment |  |  |  |  | WP5 |  |  |  |  | BaBar |  |  |  |  | Rollout | [12 empty] | Metric not OK |  |  |  | 1.1.1
| J | 1 | 5 | K |  | J | 2 | 5 | K |  | J | 3 | 5 | K |  | J | 4 | 5 | K | [9 empty] | Task complete |  |  |  | 1.1.1
| 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 |  | 2.5.1 | 2.5.2 | 2.5.3 | 2.5.4 |  | 3.5.1 | 3.5.2 | 3.5.3 | 3.5.4 |  | 4.5.1 | 4.5.2 | 4.5.3 | 4.5.4 | [9 empty] | Task overdue |  |  |  | 1.1.1
| 1.5.5 | 1.5.6 | 1.5.7 | 1.5.8 |  | 2.5.5 | 2.5.6 | 2.5.7 |  |  | 3.5.5 | 3.5.6 | 3.5.7 | [15 empty] | Due within |  | 90 | days | 1.1.1
| 1.5.9 | 1.5.10 | [26 empty] | Task not due soon |  |  |  | 1.1.1
[6 empty] | WP6 |  |  |  |  | CDF/DO |  |  |  |  | Data Challenges | [12 empty] | Not Active |  |  |  | 1.1.1
[6 empty] | J | 2 | 6 | K |  | J | 3 | 6 | K |  | J | 4 | 6 | K | [9 empty] | No Task or metric
[6 empty] | 2.6.1 | 2.6.2 | 2.6.3 | 2.6.4 |  | 3.6.1 | 3.6.2 | 3.6.3 | 3.6.4 |  | 4.6.1 | 4.6.2 | 4.6.3
[6 empty] | 2.6.5 | 2.6.6 | 2.6.7 | 2.6.8 |  | 3.6.5 | 3.6.6 | 3.6.7 | 3.6.8 | [14 empty] | Navigate up |  |  |  | J
[6 empty] | 2.6.9 |  |  |  |  | 3.6.9 | 3.6.10 | 3.6.11 | 3.6.12 | [14 empty] | Navigate down |  |  |  | K
[6 empty] | WP7 |  |  |  |  | UKQCD | [17 empty] | External link |  |  |  | I
[6 empty] | J | 2 | 7 | K |  | J | 3 | 7 | K | [14 empty] | Link to goals |  |  |  | H
[6 empty] | 2.7.1 | 2.7.2 | 2.7.3 | 2.7.4 |  | 3.7.1 | 3.7.2 | 3.7.3 | 3.7.4
[6 empty] | 2.7.5 | 2.7.6 | 2.7.7 | 2.7.8 |  | 3.7.5 | 3.7.6
[6 empty] | WP8 |  |  |  |  | Other
[6 empty] | J | 2 | 8 | K |  | J | 3 | 8 | K
[6 empty] | 2.8.1 | 2.8.2 | 2.8.3 | 2.8.4 |  | 3.8.1 | 3.8.2 | 3.8.3
2.8.5

## RiskRegister
ID | Name | GridPP |  |  | LCG |  |  | EDG |  |  | Apps |  |  | Infrast. |  |  | Interop.
|  | Li | Im | Risk | Li | Im | Risk | Li | Im | Risk | Li | Im | Risk | Li | Im | Risk | Li | Im | Risk
R1 | Recruitment/retention difficulties |  |  |  | 1 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 4
R2 | Sudden loss of key staff |  |  |  | 1 | 4 | 4 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 3
R3 | Minimal Contingency | [6 empty] | 1 | 2 | 2 | 2 | 2 | 4 | 1 | 2 | 2
R4 | GridPP deliverables late | [6 empty] | 1 | 3 | 3 | 4 | 2 | 8
R5 | Sub-components not delivered to project | 2 | 4 | 8 | 2 | 3 | 6 | 2 | 3 | 6 |  |  |  | 2 | 3 | 6
R6 | Non take-up of project results |  |  |  | 2 | 1 | 2 | 1 | 4 | 4 | 1 | 4 | 4
R7 | Change in project scope |  |  |  | 1 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 1
R8 | Bad publicity | 2 | 2 | 4 | 1 | 3 | 3 | 1 | 3 | 3
R9 | No publicity | 2 | 1 | 2
R10 | External software dependence |  |  |  | 2 | 4 | 8 | 1 | 4 | 4 | 2 | 3 | 6
R11 | Lack of monitoring of staff |  |  |  | 1 | 2 | 2 | 2 | 2 | 4 | 1 | 3 | 3 | 1 | 2 | 2
R12 | Withdrawal of an experiment | 1 | 4 | 4 | 1 | 4 | 4 | 1 | 2 | 2
R13 | Lack of cooperation between Tier centres |  |  |  | 1 | 4 | 4 | [6 empty] | 1 | 2 | 2
R14 | Scalablity problems |  |  |  | 3 | 3 | 9 | 2 | 3 | 6 |  |  |  | 1 | 3 | 3
R15 | Software maintainability problems |  |  |  | 3 | 2 | 6 | 1 | 3 | 3
R16 | Technology shifts | 1 | 3 | 3 | 1 | 4 | 4 | 1 | 3 | 3
R17 | Repitition of research | 3 | 2 | 6
R18 | Lack of funding to meet LCG PH-1 goals |  |  |  | 1 | 3 | 3
R19 | Adequate persistency solution not ready | [9 empty] | 1 | 3 | 3
R20 | Conflicting software requirements | [9 empty] | 4 | 1 | 4 | 2 | 2 | 4
R21 | Tier-A hardware fails to meet requirements | [9 empty] | 1 | 3 | 3
R22 | Other Hardware fails to meet requirements | [12 empty] | 1 | 1 | 1
R23 | Hardware physical risk (large scale) | [12 empty] | 1 | 4 | 4
R24 | Hardware physical risk (small scale) | [12 empty] | 2 | 2 | 4
R25 | Hardware procurement problems | [12 empty] | 2 | 2 | 4
R26 | LAN Bottlenecks | [12 empty] | 2 | 1 | 2
R27 | Tier-2 organisation fails | [12 empty] | 1 | 2 | 2
R28 | Tier-2 hardware not used as planned | [12 empty] | 2 | 1 | 2
R29 | SYSMAN effort inadequate | [12 empty] | 3 | 3 | 9
R30 | Firewalls interfere with Grid | [12 empty] | 1 | 3 | 3
R31 | Inablility to establish trust relationships | [12 empty] | 2 | 2 | 4
R32 | Security inadequate to operate Grid | [12 empty] | 1 | 3 | 3
R33 | GGF does not establish standards | [15 empty] | 1 | 3 | 3
R34 | Minimal open source code development | [15 empty] | 2 | 2 | 4
R35 | Failure of international cooperation |  |  |  | 1 | 4 | 4 | [9 empty] | 1 | 4 | 4
R36 | e-Science and GridPP divergence | [15 empty] | 2 | 2 | 4
R37 | Institutes do not embrace Grid | 1 | 3 | 3
R38 | Grid is not stable enough for use | 4 | 2 | 8
R39 | Delay of the LHC | 2 | 2 | 4
R40 | Lack of future funding | 2 | 4 | 8 |  |  |  | 2 | 2 | 4
R41 | Network backbone failure | [12 empty] | 0.1 | 4 | 0.4
R42 | Network backbone bottleneck | [12 empty] | 1 | 2 | 2
Alt-i-r

## Links
Target document or Cell | Link Origin
Dummy Entry
$AttributeMap.$H$49 | $MasterMap.$H$49
http://www.gridpp.ac.uk/eb/applications.html | $MasterMap.$K$49
http://ganga/web.cern.ch/ganga/ | $MasterMap.$P$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CMS_milestones.doc | $MasterMap.$P$29
$AttributeMap.$R$39 | $MasterMap.$R$39
$AttributeMap.$C$24 | $MasterMap.$C$24
$AttributeMap.$C$29 | $MasterMap.$C$29
$AttributeMap.$C$34 | $MasterMap.$C$34
$AttributeMap.$H$14 | $MasterMap.$H$14
$AttributeMap.$H$19 | $MasterMap.$H$19
$AttributeMap.$H$24 | $MasterMap.$H$24
$AttributeMap.$H$29 | $MasterMap.$H$29
$AttributeMap.$H$34 | $MasterMap.$H$34
$AttributeMap.$H$39 | $MasterMap.$H$39
$AttributeMap.$H$44 | $MasterMap.$H$44
$AttributeMap.$M$14 | $MasterMap.$M$14
$AttributeMap.$M$19 | $MasterMap.$M$19
$AttributeMap.$M$29 | $MasterMap.$M$29
$AttributeMap.$M$34 | $MasterMap.$M$34
$AttributeMap.$M$39 | $MasterMap.$M$39
$AttributeMap.$R$14 | $MasterMap.$R$14
$AttributeMap.$R$19 | $MasterMap.$R$19
$AttributeMap.$R$24 | $MasterMap.$R$24
$AttributeMap.$R$29 | $MasterMap.$R$29
$AttributeMap.$R$34 | $MasterMap.$R$34
$AttributeMap.$W$14 | $MasterMap.$W$14
$AttributeMap.$W$19 | $MasterMap.$W$19
$AttributeMap.$W$24 | $MasterMap.$W$24
$AttributeMap.$W$29 | $MasterMap.$W$29
$AttributeMap.$AB$14 | $MasterMap.$AB$14
$AttributeMap.$AB$19 | $MasterMap.$AB$19
$AttributeMap.$AB$24 | $MasterMap.$AB$24
$AttributeMap.$AG$14 | $MasterMap.$AG$14
$AttributeMap.$AG$19 | $MasterMap.$AG$19
$AttributeMap.$AG$24 | $MasterMap.$AG$24
$AttributeMap.$M$49 | $MasterMap.$M$49
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_milestones.doc | $MasterMap.$P$14
http://www.cern.ch/lcg/peb/documents/21june02_LCG_planning_status.doc | $MasterMap.$F$14
http://server11.infn.it/workload-grid/ | $MasterMap.$K$14
http://eu-datagrid.web.cern.ch/eu-datagrid/Intranet_Home.htm | $MasterMap.$J$10
http://lhcgrid.web.cern.ch/LHCgrid/ | $MasterMap.$E$10
http://grid-data-management.web.cern.ch/grid-data-management/ | $MasterMap.$K$19
http://hepunx.rl.ac.uk/edg/wp3/ | $MasterMap.$K$24
http://hep-proj-grid-fabric.web.cern.ch/hep-proj-grid-fabric/ | $MasterMap.$K$29
http://proj-datagrid-masstorage.web.cern.ch/proj-datagrid-masstorage/ | $MasterMap.$K$34
http://marianne.in2p3.fr/ | $MasterMap.$K$39
http://www.gridpp.ac.uk/wp7/index.html | $MasterMap.$K$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/BaBar_milestones.doc | $MasterMap.$P$34
$AttributeMap.$M$24 | $MasterMap.$M$24
$AttributeMap.$M$44 | $MasterMap.$M$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/SAM_milestones.doc | $MasterMap.$P$39
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CDF_milestones.doc | $MasterMap.$P$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Gaudi_milestones.doc | $MasterMap.$P$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/LHCb_milestones.doc | $MasterMap.$P$24
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/UKQCD_milestones.doc | $MasterMap.$P$44
http://www.gridpp.ac.uk/open_source.html | $MasterMap.$Z$19
$AttributeMap.$C$14 | $MasterMap.$C$14
$AttributeMap.$C$19 | $MasterMap.$C$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CERN_goals.doc | $MasterMap.$B$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGrid_goals.doc | $MasterMap.$G$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Application_goals.doc | $MasterMap.$L$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Infrastructure_goals.doc | $MasterMap.$Q$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Interoperability_goals.doc | $MasterMap.$V$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Dissemination_goals.doc | $MasterMap.$AA$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Resource_goals.doc | $MasterMap.$AF$10
$'1.2'.$B$62 | $AttributeMap.$E$21
$'1.2'.$B$72 | $AttributeMap.$F$21
$'1.2'.$B$82 | $AttributeMap.$C$22
$'1.2'.$B$92 | $AttributeMap.$D$22
$'1.3'.$B$62 | $AttributeMap.$E$26
$'1.3'.$B$72 | $AttributeMap.$F$26
$'1.3'.$B$82 | $AttributeMap.$C$27
$'1.3'.$B$92 | $AttributeMap.$D$27
$'1.3'.$B$102 | $AttributeMap.$E$27
$'2.8'.$B$2 | $AttributeMap.$K$49
$MasterMap.$H$49 | $AttributeMap.$H$49
$'2.8'.$B$2 | $AttributeMap.$H$50
$'2.8'.$B$12 | $AttributeMap.$I$50
$'2.8'.$B$22 | $AttributeMap.$J$50
$'2.8'.$B$32 | $AttributeMap.$K$50
$'2.8'.$B$42 | $AttributeMap.$H$51
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CERN_goals.doc | $AttributeMap.$B$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGrid_goals.doc | $AttributeMap.$G$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Application_goals.doc | $AttributeMap.$L$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Infrastructure_goals.doc | $AttributeMap.$Q$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Interoperability_goals.doc | $AttributeMap.$V$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Dissemination_goals.doc | $AttributeMap.$AA$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Resource_goals.doc | $AttributeMap.$AF$10
$'3.4'.$B$2 | $AttributeMap.$M$30
$'3.4'.$B$12 | $AttributeMap.$N$30
$'3.4'.$B$22 | $AttributeMap.$O$30
$'3.4'.$B$42 | $AttributeMap.$M$31
$'3.4'.$B$52 | $AttributeMap.$N$31
$'3.4'.$B$62 | $AttributeMap.$O$31
$'3.4'.$B$82 | $AttributeMap.$M$32
$'3.4'.$B$92 | $AttributeMap.$N$32
$'3.4'.$B$72 | $AttributeMap.$P$31
$'3.4'.$B$32 | $AttributeMap.$P$30
$'1.1'.$B$12 | $AttributeMap.$D$15
$'1.1'.$B$22 | $AttributeMap.$E$15
$'1.1'.$B$32 | $AttributeMap.$F$15
$'3.3'.$B$2 | $AttributeMap.$P$24
$'1.1'.$B$2 | $AttributeMap.$F$14
$MasterMap.$R$14 | $AttributeMap.$R$14
$MasterMap.$W$14 | $AttributeMap.$W$14
$MasterMap.$AB$14 | $AttributeMap.$AB$14
$MasterMap.$AG$14 | $AttributeMap.$AG$14
$MasterMap.$AG$19 | $AttributeMap.$AG$19
$MasterMap.$AB$19 | $AttributeMap.$AB$19
$MasterMap.$W$19 | $AttributeMap.$W$19
$MasterMap.$R$19 | $AttributeMap.$R$19
$MasterMap.$C$24 | $AttributeMap.$C$24
$MasterMap.$R$24 | $AttributeMap.$R$24
$MasterMap.$W$24 | $AttributeMap.$W$24
$MasterMap.$AB$24 | $AttributeMap.$AB$24
$MasterMap.$AG$24 | $AttributeMap.$AG$24
$MasterMap.$R$39 | $AttributeMap.$R$39
$'3.2'.$B$2 | $AttributeMap.$P$19
$'4.1'.$B$2 | $AttributeMap.$U$14
$'5.1'.$B$2 | $AttributeMap.$Z$14
$'6.1'.$B$2 | $AttributeMap.$AE$14
$'7.1'.$B$2 | $AttributeMap.$AJ$14
$'7.2'.$B$2 | $AttributeMap.$AJ$19
$'7.3'.$B$2 | $AttributeMap.$AJ$24
$'6.3'.$B$2 | $AttributeMap.$AE$24
$'6.2'.$B$2 | $AttributeMap.$AE$19
$'5.2'.$B$2 | $AttributeMap.$Z$19
$'5.3'.$B$2 | $AttributeMap.$Z$24
$'4.2'.$B$2 | $AttributeMap.$U$19
$'4.3'.$B$2 | $AttributeMap.$U$24
$'4.4'.$B$2 | $AttributeMap.$U$29
$'4.6'.$B$2 | $AttributeMap.$U$39
$'3.4'.$B$2 | $AttributeMap.$P$29
$'3.5'.$B$2 | $AttributeMap.$P$34
$'3.6'.$B$2 | $AttributeMap.$P$39
$'1.2'.$B$2 | $AttributeMap.$F$19
$'1.3'.$B$2 | $AttributeMap.$F$24
$'1.4'.$B$2 | $AttributeMap.$F$29
$MasterMap.$M$19 | $AttributeMap.$M$19
$MasterMap.$C$29 | $AttributeMap.$C$29
$MasterMap.$R$29 | $AttributeMap.$R$29
$'3.6'.$B$2 | $AttributeMap.$M$40
$'3.6'.$B$12 | $AttributeMap.$N$40
$'3.6'.$B$22 | $AttributeMap.$O$40
$'3.6'.$B$32 | $AttributeMap.$P$40
$'3.6'.$B$42 | $AttributeMap.$M$41
$'3.6'.$B$52 | $AttributeMap.$N$41
$'3.6'.$B$62 | $AttributeMap.$O$41
$'3.6'.$B$72 | $AttributeMap.$P$41
$'3.6'.$B$82 | $AttributeMap.$M$42
$'3.6'.$B$92 | $AttributeMap.$N$42
$'3.6'.$B$102 | $AttributeMap.$O$42
$'3.6'.$B$112 | $AttributeMap.$P$42
$'3.2'.$B$2 | $AttributeMap.$M$20
$'3.2'.$B$12 | $AttributeMap.$N$20
$'3.2'.$B$22 | $AttributeMap.$O$20
$'3.2'.$B$32 | $AttributeMap.$P$20
$'3.2'.$B$42 | $AttributeMap.$M$21
$'3.2'.$B$52 | $AttributeMap.$N$21
$'3.2'.$B$62 | $AttributeMap.$O$21
$'3.2'.$B$72 | $AttributeMap.$P$21
$'3.2'.$B$82 | $AttributeMap.$M$22
$'3.7'.$B$2 | $AttributeMap.$M$45
$'3.7'.$B$12 | $AttributeMap.$N$45
$'3.7'.$B$22 | $AttributeMap.$O$45
$'3.7'.$B$32 | $AttributeMap.$P$45
$'3.7'.$B$42 | $AttributeMap.$M$46
$'3.7'.$B$52 | $AttributeMap.$N$46
$'3.8'.$B$2 | $AttributeMap.$M$50
$'3.8'.$B$12 | $AttributeMap.$N$50
$'3.8'.$B$22 | $AttributeMap.$O$50
$'1.5'.$B$2 | $AttributeMap.$F$34
$MasterMap.$C$34 | $AttributeMap.$C$34
$'1.2'.$B$2 | $AttributeMap.$C$20
$'1.2'.$B$12 | $AttributeMap.$D$20
$'1.2'.$B$22 | $AttributeMap.$E$20
$'1.2'.$B$32 | $AttributeMap.$F$20
$'1.2'.$B$42 | $AttributeMap.$C$21
$'1.3'.$B$2 | $AttributeMap.$C$25
$'1.3'.$B$12 | $AttributeMap.$D$25
$'1.3'.$B$22 | $AttributeMap.$E$25
$'1.3'.$B$32 | $AttributeMap.$F$25
$'1.3'.$B$42 | $AttributeMap.$C$26
$'1.4'.$B$2 | $AttributeMap.$C$30
$'1.4'.$B$12 | $AttributeMap.$D$30
$'1.4'.$B$22 | $AttributeMap.$E$30
$'1.4'.$B$32 | $AttributeMap.$F$30
$'1.5'.$B$2 | $AttributeMap.$C$35
$'1.5'.$B$12 | $AttributeMap.$D$35
$'1.5'.$B$22 | $AttributeMap.$E$35
$'1.5'.$B$32 | $AttributeMap.$F$35
$'1.5'.$B$42 | $AttributeMap.$C$36
$'1.5'.$B$52 | $AttributeMap.$D$36
$'4.1'.$B$2 | $AttributeMap.$R$15
$'4.1'.$B$12 | $AttributeMap.$S$15
$'4.1'.$B$22 | $AttributeMap.$T$15
$'4.1'.$B$32 | $AttributeMap.$U$15
$'4.1'.$B$42 | $AttributeMap.$R$16
$'4.1'.$B$52 | $AttributeMap.$S$16
$'4.1'.$B$62 | $AttributeMap.$T$16
$'4.1'.$B$72 | $AttributeMap.$U$16
$'4.1'.$B$82 | $AttributeMap.$R$17
$'4.3'.$B$2 | $AttributeMap.$R$25
$'4.3'.$B$12 | $AttributeMap.$S$25
$'4.3'.$B$22 | $AttributeMap.$T$25
$'4.3'.$B$32 | $AttributeMap.$U$25
$'4.3'.$B$42 | $AttributeMap.$R$26
$'4.2'.$B$2 | $AttributeMap.$R$20
$'4.2'.$B$12 | $AttributeMap.$S$20
$'4.2'.$B$22 | $AttributeMap.$T$20
$'4.2'.$B$32 | $AttributeMap.$U$20
$'4.2'.$B$42 | $AttributeMap.$R$21
$'4.2'.$B$52 | $AttributeMap.$S$21
$'4.2'.$B$62 | $AttributeMap.$T$21
$'4.4'.$B$2 | $AttributeMap.$R$30
$'4.4'.$B$12 | $AttributeMap.$S$30
$'4.4'.$B$22 | $AttributeMap.$T$30
$'4.4'.$B$32 | $AttributeMap.$U$30
$'4.4'.$B$42 | $AttributeMap.$R$31
$'4.6'.$B$2 | $AttributeMap.$R$40
$MasterMap.$W$29 | $AttributeMap.$W$29
$'5.4'.$B$2 | $AttributeMap.$Z$29
$'5.1'.$B$2 | $AttributeMap.$W$15
$'5.1'.$B$12 | $AttributeMap.$X$15
$'5.1'.$B$22 | $AttributeMap.$Y$15
$'5.2'.$B$2 | $AttributeMap.$W$20
$'5.3'.$B$2 | $AttributeMap.$W$25
$'5.4'.$B$2 | $AttributeMap.$W$30
$'6.1'.$B$2 | $AttributeMap.$AB$15
$'6.1'.$B$12 | $AttributeMap.$AC$15
$'6.1'.$B$22 | $AttributeMap.$AD$15
$'6.1'.$B$42 | $AttributeMap.$AB$16
$'6.2'.$B$2 | $AttributeMap.$AB$20
$'6.2'.$B$12 | $AttributeMap.$AC$20
$'6.2'.$B$22 | $AttributeMap.$AD$20
$'6.3'.$B$2 | $AttributeMap.$AB$25
$'6.3'.$B$12 | $AttributeMap.$AC$25
$'6.3'.$B$22 | $AttributeMap.$AD$25
$'6.3'.$B$32 | $AttributeMap.$AE$25
$'7.1'.$B$2 | $AttributeMap.$AG$15
$'7.1'.$B$12 | $AttributeMap.$AH$15
$'7.1'.$B$22 | $AttributeMap.$AI$15
$'7.1'.$B$32 | $AttributeMap.$AJ$15
$'7.2'.$B$2 | $AttributeMap.$AG$20
$'7.2'.$B$12 | $AttributeMap.$AH$20
$'7.2'.$B$22 | $AttributeMap.$AI$20
$'7.3'.$B$2 | $AttributeMap.$AG$25
$'7.3'.$B$12 | $AttributeMap.$AH$25
$'7.3'.$B$22 | $AttributeMap.$AI$25
$'7.3'.$B$32 | $AttributeMap.$AJ$25
$'4.5'.$B$2 | $AttributeMap.$U$34
$MasterMap.$R$34 | $AttributeMap.$R$34
$'4.5'.$B$2 | $AttributeMap.$R$35
$'4.5'.$B$12 | $AttributeMap.$S$35
$'4.5'.$B$22 | $AttributeMap.$T$35
$'4.5'.$B$32 | $AttributeMap.$U$35
$'4.6'.$B$12 | $AttributeMap.$S$40
$'4.6'.$B$22 | $AttributeMap.$T$40
$'5.4'.$B$32 | $AttributeMap.$Z$30
$'5.4'.$B$42 | $AttributeMap.$W$31
$'5.2'.$B$12 | $AttributeMap.$X$20
$'5.2'.$B$22 | $AttributeMap.$Y$20
$'5.3'.$B$12 | $AttributeMap.$X$25
$'5.3'.$B$22 | $AttributeMap.$Y$25
$'5.4'.$B$12 | $AttributeMap.$X$30
$'5.4'.$B$22 | $AttributeMap.$Y$30
$MasterMap.$H$14 | $AttributeMap.$H$14
$MasterMap.$H$19 | $AttributeMap.$H$19
$'2.1'.$B$2 | $AttributeMap.$K$14
$'2.2'.$B$2 | $AttributeMap.$K$19
$'2.3'.$B$2 | $AttributeMap.$K$24
$'2.4'.$B$2 | $AttributeMap.$K$29
$MasterMap.$H$29 | $AttributeMap.$H$29
$'2.5'.$B$2 | $AttributeMap.$K$34
$MasterMap.$H$34 | $AttributeMap.$H$34
$'2.6'.$B$2 | $AttributeMap.$K$39
$MasterMap.$H$39 | $AttributeMap.$H$39
$'2.7'.$B$2 | $AttributeMap.$K$44
$MasterMap.$H$44 | $AttributeMap.$H$44
$'2.2'.$B$2 | $AttributeMap.$H$20
$'2.2'.$B$12 | $AttributeMap.$I$20
$'2.2'.$B$22 | $AttributeMap.$J$20
$'2.3'.$B$2 | $AttributeMap.$H$25
$'2.3'.$B$12 | $AttributeMap.$I$25
$'2.3'.$B$22 | $AttributeMap.$J$25
$'2.4'.$B$2 | $AttributeMap.$H$30
$'2.4'.$B$12 | $AttributeMap.$I$30
$'2.4'.$B$22 | $AttributeMap.$J$30
$'2.5'.$B$2 | $AttributeMap.$H$35
$'2.5'.$B$12 | $AttributeMap.$I$35
$'2.5'.$B$22 | $AttributeMap.$J$35
$'2.6'.$B$2 | $AttributeMap.$H$40
$'2.6'.$B$12 | $AttributeMap.$I$40
$'2.6'.$B$22 | $AttributeMap.$J$40
$'2.7'.$B$2 | $AttributeMap.$H$45
$'2.7'.$B$12 | $AttributeMap.$I$45
$'2.7'.$B$22 | $AttributeMap.$J$45
$'2.2'.$B$32 | $AttributeMap.$K$20
$'2.2'.$B$42 | $AttributeMap.$H$21
$'2.2'.$B$52 | $AttributeMap.$I$21
$'2.2'.$B$62 | $AttributeMap.$J$21
$'2.3'.$B$32 | $AttributeMap.$K$25
$'2.3'.$B$42 | $AttributeMap.$H$26
$'2.3'.$B$52 | $AttributeMap.$I$26
$'2.3'.$B$62 | $AttributeMap.$J$26
$'2.4'.$B$32 | $AttributeMap.$K$30
$'2.4'.$B$42 | $AttributeMap.$H$31
$'2.4'.$B$52 | $AttributeMap.$I$31
$'2.4'.$B$62 | $AttributeMap.$J$31
$'2.5'.$B$32 | $AttributeMap.$K$35
$'2.5'.$B$42 | $AttributeMap.$H$36
$'2.5'.$B$52 | $AttributeMap.$I$36
$'2.5'.$B$62 | $AttributeMap.$J$36
$'2.6'.$B$32 | $AttributeMap.$K$40
$'2.6'.$B$42 | $AttributeMap.$H$41
$'2.6'.$B$52 | $AttributeMap.$I$41
$'2.6'.$B$62 | $AttributeMap.$J$41
$'2.6'.$B$72 | $AttributeMap.$K$41
$'2.6'.$B$82 | $AttributeMap.$H$42
$'2.7'.$B$32 | $AttributeMap.$K$45
$'2.7'.$B$42 | $AttributeMap.$H$46
$'2.7'.$B$52 | $AttributeMap.$I$46
$'2.7'.$B$62 | $AttributeMap.$J$46
$'2.7'.$B$72 | $AttributeMap.$K$46
$'1.2'.$B$52 | $AttributeMap.$D$21
$'1.3'.$B$52 | $AttributeMap.$D$26
$'1.4'.$B$42 | $AttributeMap.$C$31
$'1.5'.$B$62 | $AttributeMap.$E$36
$'6.1'.$B$32 | $AttributeMap.$AE$15
$MasterMap.$H$24 | $AttributeMap.$H$24
$'2.1'.$B$2 | $AttributeMap.$H$15
$'2.1'.$B$12 | $AttributeMap.$I$15
$'2.1'.$B$22 | $AttributeMap.$J$15
$'2.1'.$B$32 | $AttributeMap.$K$15
$'2.1'.$B$42 | $AttributeMap.$H$16
$'2.1'.$B$52 | $AttributeMap.$I$16
$'2.1'.$B$62 | $AttributeMap.$J$16
$'2.1'.$B$72 | $AttributeMap.$K$16
$'2.1'.$B$82 | $AttributeMap.$H$17
$MasterMap.$M$14 | $AttributeMap.$M$14
$'3.1'.$B$2 | $AttributeMap.$P$14
$'3.1'.$B$2 | $AttributeMap.$M$15
$'3.1'.$B$12 | $AttributeMap.$N$15
$'3.1'.$B$22 | $AttributeMap.$O$15
$'3.1'.$B$32 | $AttributeMap.$P$15
$'3.1'.$B$42 | $AttributeMap.$M$16
$'3.1'.$B$52 | $AttributeMap.$N$16
$'3.1'.$B$62 | $AttributeMap.$O$16
$'3.1'.$B$72 | $AttributeMap.$P$16
$'3.1'.$B$82 | $AttributeMap.$M$17
$MasterMap.$M$49 | $AttributeMap.$M$49
$'3.1'.$B$92 | $AttributeMap.$N$17
$'3.8'.$B$2 | $AttributeMap.$P$49
$'3.5'.$B$2 | $AttributeMap.$M$35
$'3.5'.$B$12 | $AttributeMap.$N$35
$'3.5'.$B$22 | $AttributeMap.$O$35
$'3.5'.$B$32 | $AttributeMap.$P$35
$'3.5'.$B$42 | $AttributeMap.$M$36
$'3.5'.$B$52 | $AttributeMap.$N$36
$'3.5'.$B$62 | $AttributeMap.$O$36
$'1.1'.$B$2 | $AttributeMap.$C$15
$'3.3'.$B$2 | $AttributeMap.$M$25
$'3.3'.$B$12 | $AttributeMap.$N$25
$'3.3'.$B$22 | $AttributeMap.$O$25
$MasterMap.$M$24 | $AttributeMap.$M$24
$MasterMap.$M$29 | $AttributeMap.$M$29
$MasterMap.$M$34 | $AttributeMap.$M$34
$MasterMap.$M$39 | $AttributeMap.$M$39
$MasterMap.$M$44 | $AttributeMap.$M$44
$'3.7'.$B$2 | $AttributeMap.$P$44
$'3.3'.$B$32 | $AttributeMap.$P$25
$'3.3'.$B$42 | $AttributeMap.$M$26
$'3.3'.$B$52 | $AttributeMap.$N$26
$'4.4'.$B$52 | $AttributeMap.$S$31
$'1.1'.$B$42 | $AttributeMap.$C$16
$MasterMap.$C$14 | $AttributeMap.$C$14
$MasterMap.$C$19 | $AttributeMap.$C$19
http://lhcgrid.web.cern.ch/LHCgrid/ | $AttributeMap.$E$10
http://eu-datagrid.web.cern.ch/eu-datagrid/Intranet_Home.htm | $AttributeMap.$J$10
$'1.4'.$B$52 | $AttributeMap.$D$31
$'1.4'.$B$62 | $AttributeMap.$E$31
$'1.4'.$B$72 | $AttributeMap.$F$31
$'1.4'.$B$82 | $AttributeMap.$C$32
$'1.5'.$B$72 | $AttributeMap.$F$36
$'1.5'.$B$82 | $AttributeMap.$C$37
$'1.5'.$B$92 | $AttributeMap.$D$37
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R41-INF.doc | $RiskRegister.$R$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R42-INF.doc | $RiskRegister.$R$45
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R26-INF.doc | $RiskRegister.$R$29
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-GridPP.doc | $RiskRegister.$F$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-EDG.doc | $RiskRegister.$L$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R40-EDG.doc | $RiskRegister.$L$43
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R13-INF.doc | $RiskRegister.$R$16
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R30-INF.doc | $RiskRegister.$R$33
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R31-INF.doc | $RiskRegister.$R$34
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R32-INF.doc | $RiskRegister.$R$35
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-INF.doc | $RiskRegister.$R$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R22-INF.doc | $RiskRegister.$R$25
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-INF.doc | $RiskRegister.$R$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-INF.doc | $RiskRegister.$R$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R23-INF.doc | $RiskRegister.$R$26
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R24-INF.doc | $RiskRegister.$R$27
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R33-IOP.doc | $RiskRegister.$U$36
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-LCG.doc | $RiskRegister.$I$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-LCG.doc | $RiskRegister.$I$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-LCG.doc | $RiskRegister.$I$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R6-LCG.doc | $RiskRegister.$I$9
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R7-LCG.doc | $RiskRegister.$I$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R8-LCG.doc | $RiskRegister.$I$11
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R10-LCG.doc | $RiskRegister.$I$13
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-LCG.doc | $RiskRegister.$I$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R12-LCG.doc | $RiskRegister.$I$15
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R13-LCG.doc | $RiskRegister.$I$16
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R14-LCG.doc | $RiskRegister.$I$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R15-LCG.doc | $RiskRegister.$I$18
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R16-LCG.doc | $RiskRegister.$I$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R18-LCG.doc | $RiskRegister.$I$21
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R35-LCG.doc | $RiskRegister.$I$38
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R8-GridPP.doc | $RiskRegister.$F$11
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R9-GridPP.doc | $RiskRegister.$F$12
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R3-INF.doc | $RiskRegister.$R$6
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-INF.doc | $RiskRegister.$R$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R14-INF.doc | $RiskRegister.$R$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R20-INF.doc | $RiskRegister.$R$23
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R25-INF.doc | $RiskRegister.$R$28
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R27-INF.doc | $RiskRegister.$R$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R28-INF.doc | $RiskRegister.$R$31
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R29-INF.doc | $RiskRegister.$R$32
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-APP.doc | $RiskRegister.$O$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-APP.doc | $RiskRegister.$O$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R3-APP.doc | $RiskRegister.$O$6
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R4-APP.doc | $RiskRegister.$O$7
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R6-APP.doc | $RiskRegister.$O$9
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R7-APP.doc | $RiskRegister.$O$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R10-APP.doc | $RiskRegister.$O$13
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-APP.doc | $RiskRegister.$O$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R19-APP.doc | $RiskRegister.$O$22
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R20-APP.doc | $RiskRegister.$O$23
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R21-APP.doc | $RiskRegister.$O$24
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R12-GridPP.doc | $RiskRegister.$F$15
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R16-GridPP.doc | $RiskRegister.$F$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R17-GridPP.doc | $RiskRegister.$F$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R34-IOP.doc | $RiskRegister.$U$37
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R35-IOP.doc | $RiskRegister.$U$38
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R36-IOP.doc | $RiskRegister.$U$39
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R37-GridPP.doc | $RiskRegister.$F$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R39-GridPP.doc | $RiskRegister.$F$42
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R40-GridPP.doc | $RiskRegister.$F$43
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-EDG.doc | $RiskRegister.$L$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R12-EDG.doc | $RiskRegister.$L$15
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R14-EDG.doc | $RiskRegister.$L$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R15-EDG.doc | $RiskRegister.$L$18
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R16-EDG.doc | $RiskRegister.$L$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R38-GridPP.doc | $RiskRegister.$F$41
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-EDG.doc | $RiskRegister.$L$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R3-EDG.doc | $RiskRegister.$L$6
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R4-EDG.doc | $RiskRegister.$L$7
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-EDG.doc | $RiskRegister.$L$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R6-EDG.doc | $RiskRegister.$L$9
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R7-EDG.doc | $RiskRegister.$L$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R8-EDG.doc | $RiskRegister.$L$11
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R10-EDG.doc | $RiskRegister.$L$13
$'6.1.1'.$A$1 | $SL_Summary.$A$4
$'6.1.2'.$A$1 | $SL_Summary.$A$5
$'6.1.3'.$A$1 | $SL_Summary.$A$6
$'6.1.4'.$A$1 | $SL_Summary.$A$7
$'6.1.5'.$A$1 | $SL_Summary.$A$8
$'6.2.1'.$A$1 | $SL_Summary.$A$10
$'6.2.2'.$A$1 | $SL_Summary.$A$11
$'6.2.3'.$A$1 | $SL_Summary.$A$12
$'6.3.1'.$A$1 | $SL_Summary.$A$14
$'6.3.2'.$A$1 | $SL_Summary.$A$15
$'6.3.3'.$A$1 | $SL_Summary.$A$16
$'6.3.4'.$A$1 | $SL_Summary.$A$17
$'6.2.1'.$A$12 | $SL_Summary.$A$19
$'6.2.3'.$A$10 | $SL_Summary.$A$20
$'6.2.3'.$A$17 | $SL_Summary.$A$21
$'6.2.3'.$A$23 | $SL_Summary.$A$22
$'6.2.3'.$A$29 | $SL_Summary.$A$23
$'6.2.3'.$A$35 | $SL_Summary.$A$24
$'6.2.3'.$A$42 | $SL_Summary.$A$25
$'6.2.3'.$A$49 | $SL_Summary.$A$26
$AttributeMap.$C$15 | $'1.1'.$H$10
$AttributeMap.$D$15 | $'1.1'.$H$20
$AttributeMap.$E$15 | $'1.1'.$H$30
$AttributeMap.$F$15 | $'1.1'.$H$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/lcg status 14sep02.ppt | $'1.1'.$C$10
http://lhcgrid.web.cern.ch/LHCgrid/peb/membership.htm | $'1.1'.$C$20
http://www.cern.ch/lcg/peb/documents/21june02_LCG_planning_status.doc | $'1.1'.$C$30
$AttributeMap.$C$16 | $'1.1'.$H$50
http://lcg.web.cern.ch/LCG/PEB/Planning/default.htm | $'1.1'.$K$30
https://wwwlistbox.cern.ch/earchive/project-lcg-peb-apps/msg00336.html | $'1.2'.$J$40
http://www.gridpp.ac.uk/gridpp7/gridpp7_lcg_apps.ppt | $'1.2'.$C$50
$J$60 | $'1.2'.$C$60
http://lcgapp.cern.ch/project/cls/documents/SEAL_Project_Plan_0_1.pdf | $'1.2'.$C$40
$AttributeMap.$C$20 | $'1.2'.$H$10
$AttributeMap.$D$20 | $'1.2'.$H$20
$AttributeMap.$E$20 | $'1.2'.$H$30
$AttributeMap.$F$20 | $'1.2'.$H$40
$AttributeMap.$C$21 | $'1.2'.$H$50
$AttributeMap.$D$21 | $'1.2'.$H$60
$'1.2'.$B$2 | $'1.2'.$G$38
$'1.2'.$B$22 | $'1.2'.$G$39
http://lcgapp.cern.ch/project/spi | $'1.2'.$C$10
http://lcgapp.cern.ch/project/persist | $'1.2'.$C$20
$J$23 | $'1.2'.$C$30
http://seal.web.cern.ch/seal/documents/SEAL_AAM_12_Feb_2003.ppt | $'1.2'.$J$26
http://info.web.cern.ch/info/Press/PressReleases/Releases2003/PR13.03ELCG-1.html | $'1.3'.$C$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/LCG1.3.5.ppt | $'1.3'.$C$50
$AttributeMap.$C$25 | $'1.3'.$H$10
$AttributeMap.$D$25 | $'1.3'.$H$20
$AttributeMap.$E$25 | $'1.3'.$H$30
$AttributeMap.$F$25 | $'1.3'.$H$40
$AttributeMap.$C$26 | $'1.3'.$H$50
$AttributeMap.$D$26 | $'1.3'.$H$60
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/tape drive purchase.doc | $'1.3'.$C$10
$B$22 | $'1.3'.$G$38
$'1.2'.$B$2 | $'1.3'.$G$39
$J$40 | $'1.4'.$C$40
http://lcg.web.cern.ch/LCG/PEB/gdb/WG1/WG1_Postfinal.2.doc | $'1.4'.$C$10
http://lcg.web.cern.ch/LCG/PEB/Planning/default.htm | $'1.4'.$J$3
$J$20 | $'1.4'.$C$20
http://lcg.web.cern.ch/LCG/PEB/gdb | $'1.4'.$J$20
$AttributeMap.$C$30 | $'1.4'.$H$10
$AttributeMap.$D$30 | $'1.4'.$H$20
$AttributeMap.$E$30 | $'1.4'.$H$30
$AttributeMap.$F$30 | $'1.4'.$H$40
$AttributeMap.$C$31 | $'1.4'.$H$50
http://cern.ch/grid-deployment | $'1.4'.$C$30
$AttributeMap.$D$31 | $'1.4'.$H$60
$AttributeMap.$E$31 | $'1.4'.$H$70
$AttributeMap.$F$31 | $'1.4'.$H$80
$AttributeMap.$C$32 | $'1.4'.$H$90
$J$49 | $'1.4'.$C$50
http://www.gridpp.ac.uk/talks/GSC_GridPP1_status3.ppt | $'1.5'.$C$20
http://agenda.cern.ch/askArchive.php?base=agenda&categ=a03923&id=a03923s1t3/transparencies | $'1.5'.$C$30
http://www.cern.ch/grid-deployment/cgi-bin/index.cgi?var-lcg1Status | $'1.5'.$C$40
http://info.web.cern.ch/info/Press/PressReleases/Releases2003/PR13.03ELCG-1.html | $'1.5'.$C$50
$J$10 | $'1.5'.$C$10
http://lcg.web.cern.ch/LCG/PEB/gdb | $'1.5'.$J$10
$AttributeMap.$C$35 | $'1.5'.$H$10
$AttributeMap.$D$35 | $'1.5'.$H$20
$AttributeMap.$E$35 | $'1.5'.$H$30
$AttributeMap.$F$35 | $'1.5'.$H$40
$AttributeMap.$C$36 | $'1.5'.$H$50
$AttributeMap.$D$36 | $'1.5'.$H$60
$AttributeMap.$E$36 | $'1.5'.$H$70
$'1.4'.$B$2 | $'1.5'.$G$28
$'1.5'.$B$12 | $'1.5'.$G$29
$'1.2'.$B$32 | $'1.5'.$G$58
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.2.doc | $'1.5'.$J$12
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.3.doc | $'1.5'.$J$22
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.4.doc | $'1.5'.$J$32
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.5.doc | $'1.5'.$J$42
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.6.doc | $'1.5'.$J$53
$AttributeMap.$F$36 | $'1.5'.$H$80
$AttributeMap.$C$37 | $'1.5'.$H$90
$AttributeMap.$D$37 | $'1.5'.$H$100
$J$70 | $'1.5'.$C$70
$'1.4'.$B$72 | $'1.5'.$G$88
$B$72 | $'1.5'.$G$89
https://edms.cern.ch/file/407025/1/DataGrid-06-D6.7-0124-0-5-UsersGuides.doc | $'2.1'.$C$80
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.1'.$C$70
$AttributeMap.$J$15 | $'2.1'.$H$30
$AttributeMap.$K$15 | $'2.1'.$H$40
$AttributeMap.$H$15 | $'2.1'.$H$10
$AttributeMap.$I$15 | $'2.1'.$H$20
$AttributeMap.$H$17 | $'2.1'.$H$90
$AttributeMap.$K$16 | $'2.1'.$H$80
$AttributeMap.$J$16 | $'2.1'.$H$70
$AttributeMap.$H$16 | $'2.1'.$H$50
$AttributeMap.$I$16 | $'2.1'.$H$60
http://server11.infn.it/workload-grid/docs/DataGrid-01-TED-0102-1_0.doc | $'2.1'.$C$30
http://server11.infn.it/workload-grid/docs/DataGrid-01-D1.2-0112-0-3.doc | $'2.1'.$C$40
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287452&document_id=347151&version=1.0&filename=DataGrid-01-D1.4-0127-1_0.doc | $'2.1'.$C$60
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.1'.$C$50
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGridEffort.txt | $'2.1'.$D$8
https://edms.cern.ch/file/407025/1/DataGrid-06-D6.7-0124-0-5-UsersGuides.doc | $'2.2'.$C$60
$AttributeMap.$H$20 | $'2.2'.$H$10
$AttributeMap.$I$20 | $'2.2'.$H$20
$AttributeMap.$J$21 | $'2.2'.$H$70
$AttributeMap.$I$21 | $'2.2'.$H$60
$AttributeMap.$H$21 | $'2.2'.$H$50
$AttributeMap.$J$20 | $'2.2'.$H$30
$AttributeMap.$K$20 | $'2.2'.$H$40
http://grid-data-management.web.cern.ch/grid-data-management/docs/DataGrid-02-D2.1-0105-2_0.doc | $'2.2'.$C$20
http://grid-data-management.web.cern.ch/grid-data-management/docs/DataGrid-02-D2.2-0103-1_2.doc | $'2.2'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.2'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.2'.$C$50
https://edms.cern.ch/file/407025/1/DataGrid-06-D6.7-0124-0-5-UsersGuides.doc | $'2.3'.$C$60
$AttributeMap.$H$25 | $'2.3'.$H$10
$AttributeMap.$I$25 | $'2.3'.$H$20
$AttributeMap.$J$25 | $'2.3'.$H$30
$AttributeMap.$K$25 | $'2.3'.$H$40
$AttributeMap.$H$26 | $'2.3'.$H$50
$AttributeMap.$I$26 | $'2.3'.$H$60
$AttributeMap.$J$26 | $'2.3'.$H$70
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241263&document_id=332476&version=2-0&filename=DataGrid-03-D3.1-0102-2-0.doc | $'2.3'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241267&document_id=334453&version=4-0&filename=DataGrid-03-D3.2-334453-4-0.pdf | $'2.3'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.3'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.3'.$C$50
https://edms.cern.ch/file/407025/1/DataGrid-06-D6.7-0124-0-5-UsersGuides.doc | $'2.4'.$C$60
$AttributeMap.$H$30 | $'2.4'.$H$10
$AttributeMap.$I$30 | $'2.4'.$H$20
$AttributeMap.$J$30 | $'2.4'.$H$30
$AttributeMap.$K$30 | $'2.4'.$H$40
$AttributeMap.$H$31 | $'2.4'.$H$50
$AttributeMap.$I$31 | $'2.4'.$H$60
$AttributeMap.$J$31 | $'2.4'.$H$70
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241275&document_id=332371&version=1&filename=datagrid-04-d4.1-0101-3_0.doc | $'2.4'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241275&document_id=332393&version=1&filename=datagrid-04-d4.2-0119-2-1.doc | $'2.4'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.4'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.4'.$C$50
https://edms.cern.ch/file/407025/1/DataGrid-06-D6.7-0124-0-5-UsersGuides.doc | $'2.5'.$C$60
$AttributeMap.$H$35 | $'2.5'.$H$10
$AttributeMap.$I$35 | $'2.5'.$H$20
$AttributeMap.$J$35 | $'2.5'.$H$30
$AttributeMap.$K$35 | $'2.5'.$H$40
$AttributeMap.$H$36 | $'2.5'.$H$50
$AttributeMap.$I$36 | $'2.5'.$H$60
$AttributeMap.$J$36 | $'2.5'.$H$70
http://edms.cern.ch/document/336677/ | $'2.5'.$C$20
http://edms.cern.ch/document/336679/ | $'2.5'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.5'.$C$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGridEffort.txt | $'2.5'.$D$8
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.5'.$C$50
https://edms.cern.ch/file/375744/2/D6.6-1.1.doc | $'2.6'.$C$70
https://edms.cern.ch/file/407025/1/DataGrid-06-D6.7-0124-0-5-UsersGuides.doc | $'2.6'.$C$80
$AttributeMap.$H$40 | $'2.6'.$H$10
$AttributeMap.$I$40 | $'2.6'.$H$20
$AttributeMap.$J$40 | $'2.6'.$H$30
$AttributeMap.$J$41 | $'2.6'.$H$70
$AttributeMap.$K$41 | $'2.6'.$H$80
$AttributeMap.$H$42 | $'2.6'.$H$90
$AttributeMap.$I$41 | $'2.6'.$H$60
$AttributeMap.$H$41 | $'2.6'.$H$50
$AttributeMap.$K$40 | $'2.6'.$H$40
http://marianne.in2p3.fr/datagrid/documentation/DataGrid-6-D6.1-0101-3-3.doc | $'2.6'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1242681&document_id=332430&version=1.4.2&filename=DataGrid-06-D6.2-0121-1.4.2-ConfMngmt.doc | $'2.6'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.6'.$C$50
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.6'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.6'.$C$60
$AttributeMap.$H$45 | $'2.7'.$H$10
$AttributeMap.$I$45 | $'2.7'.$H$20
$AttributeMap.$J$45 | $'2.7'.$H$30
$AttributeMap.$K$45 | $'2.7'.$H$40
$AttributeMap.$H$46 | $'2.7'.$H$50
$AttributeMap.$I$46 | $'2.7'.$H$60
$AttributeMap.$J$46 | $'2.7'.$H$70
$AttributeMap.$K$46 | $'2.7'.$H$80
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287475&document_id=347481&version=1.5&filename=DataGrid-07-D7-3-0113-1-5.doc | $'2.7'.$C$40
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287598&document_id=334783&version=2.0&filename=DataGrid-07-D7.1-0109-2-0.doc | $'2.7'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287605&document_id=334883&version=8.1&filename=DataGrid-07-D7-2-0110-8-1.doc | $'2.7'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287617&document_id=340234&version=4.0&filename=DataGrid-07-D7.5-0111-4-0-SecurityReq.doc | $'2.7'.$C$60
https://edms.cern.ch/file/344562/2.0/DataGrid-07-D7.6-0112-2-0-SecurityDesign.pdf | $'2.7'.$C$70
$AttributeMap.$H$50 | $'2.8'.$H$10
$AttributeMap.$I$50 | $'2.8'.$H$20
$AttributeMap.$J$50 | $'2.8'.$H$30
$AttributeMap.$K$50 | $'2.8'.$H$40
$AttributeMap.$H$51 | $'2.8'.$H$50
https://edms.cern.ch/file/375586/1.2/wp8-D8.3-0119-3-1.pdf | $'2.8'.$C$40
https://edms.cern.ch/file/332409/1/datagrid-08-d8.1.a_v2.1.pdf | $'2.8'.$C$20
https://edms.cern.ch/file/334920/3.1/D8.2_3.1.pdf | $'2.8'.$C$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.9NEW2.doc | $'3.1'.$J$84
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.4b.doc | $'3.1'.$J$34
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.6b.doc | $'3.1'.$J$54
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.9d.doc | $'3.1'.$J$85
$AttributeMap.$O$15 | $'3.1'.$Q$30
$B$12 | $'3.1'.$P$28
$AttributeMap.$P$15 | $'3.1'.$Q$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.6.doc | $'3.1'.$J$53
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.4.doc | $'3.1'.$J$33
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.3.doc | $'3.1'.$J$23
$J$30 | $'3.1'.$C$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.9NEW.doc | $'3.1'.$J$83
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_arch_rev.pdf | $'3.1'.$C$10
http://www.gridpp.ac.uk/atlas/Projects/ATLASGridProjects.htm | $'3.1'.$J$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_DC_eval.pdf | $'3.1'.$C$50
$AttributeMap.$M$16 | $'3.1'.$Q$50
$B$22 | $'3.1'.$P$48
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.5NEW.doc | $'3.1'.$J$43
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_milestones.doc | $'3.1'.$J$48
$AttributeMap.$M$17 | $'3.1'.$Q$90
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.9.doc | $'3.1'.$J$82
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_milestones.doc | $'3.1'.$J$91
$AttributeMap.$M$15 | $'3.1'.$H$10
$AttributeMap.$N$15 | $'3.1'.$H$20
$AttributeMap.$O$15 | $'3.1'.$H$30
$AttributeMap.$P$15 | $'3.1'.$H$40
$AttributeMap.$M$16 | $'3.1'.$H$50
$AttributeMap.$N$16 | $'3.1'.$H$60
$AttributeMap.$O$16 | $'3.1'.$H$70
$AttributeMap.$P$16 | $'3.1'.$H$80
$AttributeMap.$M$17 | $'3.1'.$H$90
$AttributeMap.$N$17 | $'3.1'.$H$100
$B$12 | $'3.1'.$G$28
http://www.gridpp.ac.uk/eb/030929/GANGA.doc | $'3.2'.$C$60
http://http://lhcbcvs.cern.ch/cgi-bin/cvsweb.cgi/Ganga/?cvsroot=Gaudi | $'3.2'.$J$49
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/MS-3.2.1a.pdf | $'3.2'.$J$9
$'3.2'.$J$9 | $'3.2'.$C$10
http://ganga.web.cern.ch/ganga/work/index.html | $'3.2'.$J$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/GangaStatus.txt | $'3.2'.$C$40
$'3.2'.$B$12 | $'3.2'.$G$48
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/GangaDeliverableChanges.txt | $'3.2'.$J$27
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/GangaDeliverableChanges.txt | $'3.2'.$J$36
$AttributeMap.$M$20 | $'3.2'.$H$10
$AttributeMap.$N$20 | $'3.2'.$H$20
$AttributeMap.$O$20 | $'3.2'.$H$30
$AttributeMap.$P$20 | $'3.2'.$H$40
$AttributeMap.$M$21 | $'3.2'.$H$50
$AttributeMap.$N$21 | $'3.2'.$H$60
$AttributeMap.$O$21 | $'3.2'.$H$70
$AttributeMap.$P$21 | $'3.2'.$H$80
$AttributeMap.$M$22 | $'3.2'.$H$90
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Ganga3.2.4.doc | $'3.2'.$J$38
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Ganga3.2.2.doc | $'3.2'.$J$13
$J$14 | $'3.2'.$C$20
$J$49 | $'3.2'.$C$50
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LHCb3.3.3.doc | $'3.3'.$J$24
$AttributeMap.$P$25 | $'3.3'.$Q$40
http://www.gridpp.ac.uk/eb/030929/LHCb.doc | $'3.3'.$C$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/LHCb_3.3.2.txt | $'3.3'.$C$20
$AttributeMap.$N$25 | $'3.3'.$Q$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LHCb3.3.2.doc | $'3.3'.$J$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/MS-3.3.1.doc | $'3.3'.$C$10
$AttributeMap.$M$25 | $'3.3'.$H$10
$AttributeMap.$N$25 | $'3.3'.$H$20
$AttributeMap.$O$25 | $'3.3'.$H$30
$AttributeMap.$P$25 | $'3.3'.$H$40
$AttributeMap.$M$26 | $'3.3'.$H$50
$AttributeMap.$N$26 | $'3.3'.$H$60
http://www.gridpp.ac.uk/gridpp8/gridpp8_cms-framework.ppt | $'3.4'.$C$40
http://www.gridpp.ac.uk/gridpp8/gridpp8_cms_status.ppt | $'3.4'.$C$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/CMS3.4.2.doc | $'3.4'.$J$13
http://www.gridpp.ac.uk/gridpp6/gridpp6_cms.ppt | $'3.4'.$J$18
http://www.gridpp.ac.uk/gridpp6/gridpp6_cms.ppt | $'3.4'.$J$9
http://www.gridpp.ac.uk/gridpp6/gridpp6_cms.ppt | $'3.4'.$J$30
http://www.brunel.ac.uk/~eestprh/GRIDPP/task3_4_3.htm | $'3.4'.$C$30
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'3.4'.$C$10
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'3.4'.$J$10
$AttributeMap.$M$30 | $'3.4'.$H$10
$AttributeMap.$N$30 | $'3.4'.$H$20
$AttributeMap.$O$30 | $'3.4'.$H$30
$AttributeMap.$P$30 | $'3.4'.$H$40
$AttributeMap.$M$31 | $'3.4'.$H$50
$AttributeMap.$N$31 | $'3.4'.$H$60
$AttributeMap.$O$31 | $'3.4'.$H$70
$AttributeMap.$P$31 | $'3.4'.$H$80
$AttributeMap.$M$32 | $'3.4'.$H$90
$AttributeMap.$N$32 | $'3.4'.$H$100
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CMS_3.4.2.txt | $'3.4'.$J$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/BaBarReport3.5.3 | $'3.5'.$C$30
$'3.5'.$J$67 | $'3.5'.$C$70
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/BaBar3.5.7.doc | $'3.5'.$J$62
http://www.gridpp.ac.uk/gridpp6/gridpp6_babar.ppt | $'3.5'.$C$10
http://www.gridpp.ac.uk/gridpp6/gridpp6_babar.ppt | $'3.5'.$C$20
$AttributeMap.$N$35 | $'3.5'.$H$20
$AttributeMap.$O$35 | $'3.5'.$H$30
$AttributeMap.$P$35 | $'3.5'.$H$40
$AttributeMap.$M$36 | $'3.5'.$H$50
$AttributeMap.$N$36 | $'3.5'.$H$60
$AttributeMap.$O$36 | $'3.5'.$H$70
$AttributeMap.$M$35 | $'3.5'.$H$10
$'3.5'.$B$2 | $'3.5'.$G$18
$'3.5'.$B$12 | $'3.5'.$G$28
$'3.5'.$B$2 | $'3.5'.$G$38
$'3.5'.$B$12 | $'3.5'.$G$39
$'3.5'.$B$32 | $'3.5'.$G$48
$'3.5'.$B$32 | $'3.5'.$G$58
$'3.5'.$B$42 | $'3.5'.$G$59
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/D03.6.9.doc | $'3.6'.$J$83
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/D03.6.11.doc | $'3.6'.$J$103
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/CDF3.6.5.doc | $'3.6'.$J$43
http://www-d0.fnal.gov/computing/grid/SAMGridManual.htm | $'3.6'.$C$60
http://samadams.fnal.gov:8080/prototype/ | $'3.6'.$J$60
http://www.gridpp.ac.uk/gridpp6/gridpp6_samcdf.ppt | $'3.6'.$C$40
$J$47 | $'3.6'.$C$50
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Status3.6.7.txt | $'3.6'.$C$70
$J$17 | $'3.6'.$C$20
http://www.gridpp.ac.uk/news/1037957446.780947.wlg | $'3.6'.$C$30
http://www.gridpp.ac.uk/news/1037957446.780947.wlg | $'3.6'.$J$70
$AttributeMap.$M$40 | $'3.6'.$H$10
$AttributeMap.$N$40 | $'3.6'.$H$20
$AttributeMap.$O$40 | $'3.6'.$H$30
$AttributeMap.$P$40 | $'3.6'.$H$40
$AttributeMap.$M$41 | $'3.6'.$H$50
$AttributeMap.$N$41 | $'3.6'.$H$60
$AttributeMap.$O$41 | $'3.6'.$H$70
$AttributeMap.$P$41 | $'3.6'.$H$80
$AttributeMap.$M$42 | $'3.6'.$H$90
$AttributeMap.$N$42 | $'3.6'.$H$100
$AttributeMap.$O$42 | $'3.6'.$H$110
$AttributeMap.$P$42 | $'3.6'.$H$120
http://www-d0.fnal.gov/computing/grid/TechnologyReview.doc | $'3.6'.$C$10
$B$2 | $'3.6'.$G$58
$B$12 | $'3.6'.$G$38
$J$100 | $'3.6'.$C$100
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/UKQCD3.7.5b.doc | $'3.7'.$J$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/UKQCD3.7.6.doc | $'3.7'.$J$53
$AttributeMap.$P$45 | $'3.7'.$S$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/UKQCD3.7.4.doc | $'3.7'.$J$33
http://www.gridpp.ac.uk/eb/030318/UKQCD/EBreportQCDgrid_mar03.doc | $'3.7'.$C$40
http://www.w3.org/XML/Schema | $'3.7'.$C$10
http://www.gridpp.ac.uk/gridpp6/gridpp6_qcd.ppt | $'3.7'.$C$20
http://www.gridpp.ac.uk/gridpp6/gridpp6_qcd.ppt | $'3.7'.$C$30
$AttributeMap.$M$45 | $'3.7'.$H$10
$AttributeMap.$N$45 | $'3.7'.$H$20
$AttributeMap.$O$45 | $'3.7'.$H$30
$AttributeMap.$P$45 | $'3.7'.$H$40
$AttributeMap.$M$46 | $'3.7'.$H$50
$'3.7'.$B$42 | $'3.7'.$G$58
$'3.7'.$B$12 | $'3.7'.$G$28
$AttributeMap.$N$46 | $'3.7'.$H$60
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/UKQCD3.7.5.doc | $'3.7'.$J$43
ProjectMapLinks\cm5_mckigney.ppt | $'3.8'.$C$20
$AttributeMap.$M$50 | $'3.8'.$H$10
$AttributeMap.$N$50 | $'3.8'.$H$20
$AttributeMap.$O$50 | $'3.8'.$H$30
http://www.gridpp.ac.uk/gridpp4/ah_experiences.ppt | $'3.8'.$C$10
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.1'.$C$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/INF4.1.5.doc | $'4.1'.$J$43
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.1'.$C$30
$AttributeMap.$R$15 | $'4.1'.$H$10
$AttributeMap.$S$15 | $'4.1'.$H$20
$AttributeMap.$T$15 | $'4.1'.$H$30
$AttributeMap.$U$15 | $'4.1'.$H$40
$AttributeMap.$R$16 | $'4.1'.$H$50
$AttributeMap.$S$16 | $'4.1'.$H$60
$AttributeMap.$T$16 | $'4.1'.$H$70
$AttributeMap.$U$16 | $'4.1'.$H$80
$AttributeMap.$R$17 | $'4.1'.$H$90
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/BaBar_MOU.doc | $'4.1'.$C$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/TierA4.1.4.txt | $'4.1'.$C$40
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.2'.$C$10
$AttributeMap.$R$20 | $'4.2'.$H$10
$AttributeMap.$S$20 | $'4.2'.$H$20
$AttributeMap.$T$20 | $'4.2'.$H$30
$AttributeMap.$U$20 | $'4.2'.$H$40
$AttributeMap.$R$21 | $'4.2'.$H$50
$AttributeMap.$S$21 | $'4.2'.$H$60
$AttributeMap.$T$21 | $'4.2'.$H$70
$J$13 | $'4.2'.$C$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/cpu_usage_groupname-may03.pie | $'4.2'.$J$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/cpu_usage_groupname-weekly-ymay02.bar | $'4.2'.$J$18
http://www.gridpp.ac.uk/docs/gridpp2/GridPP-PMB-17-Tier2_v4.0.doc | $'4.3'.$C$30
$AttributeMap.$R$25 | $'4.3'.$H$10
$AttributeMap.$S$25 | $'4.3'.$H$20
$AttributeMap.$T$25 | $'4.3'.$H$30
$AttributeMap.$U$25 | $'4.3'.$H$40
$AttributeMap.$R$26 | $'4.3'.$H$50
$B$2 | $'4.3'.$G$18
$B$2 | $'4.3'.$G$38
$B$12 | $'4.3'.$G$39
$B$22 | $'4.3'.$G$48
$AttributeMap.$R$30 | $'4.4'.$H$10
$AttributeMap.$S$30 | $'4.4'.$H$20
$AttributeMap.$T$30 | $'4.4'.$H$30
$AttributeMap.$U$30 | $'4.4'.$H$40
$AttributeMap.$R$31 | $'4.4'.$H$50
$AttributeMap.$S$31 | $'4.4'.$H$60
http://ccwp7.in2p3.fr/mapcenter/datagrid-d/graph_Europe.html | $'4.4'.$C$30
$AttributeMap.$R$35 | $'4.5'.$H$10
$AttributeMap.$S$35 | $'4.5'.$H$20
$AttributeMap.$T$35 | $'4.5'.$H$30
$AttributeMap.$U$35 | $'4.5'.$H$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RolloutStatus.txt | $'4.5'.$C$20
http://www.gridpp.ac.uk/docs/oversight/TB-02-UKrollout.doc | $'4.5'.$C$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/lhcb-prod-status.htm | $'4.6'.$C$20
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.6'.$C$10
$AttributeMap.$R$40 | $'4.6'.$H$10
$AttributeMap.$S$40 | $'4.6'.$H$20
$AttributeMap.$T$40 | $'4.6'.$H$30
$AttributeMap.$W$15 | $'5.1'.$H$10
$AttributeMap.$X$15 | $'5.1'.$H$20
$AttributeMap.$Y$15 | $'5.1'.$H$30
$AttributeMap.$W$20 | $'5.2'.$H$10
$AttributeMap.$X$20 | $'5.2'.$H$20
$AttributeMap.$Y$20 | $'5.2'.$H$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/OpenSourceMetrics.doc | $'5.2'.$D$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/OpenSourceMetrics.doc | $'5.2'.$D$18
$AttributeMap.$W$25 | $'5.3'.$H$10
$AttributeMap.$X$25 | $'5.3'.$H$20
$AttributeMap.$Y$25 | $'5.3'.$H$30
$AttributeMap.$W$30 | $'5.4'.$H$10
$AttributeMap.$X$30 | $'5.4'.$H$20
$AttributeMap.$Y$30 | $'5.4'.$H$30
$AttributeMap.$Z$30 | $'5.4'.$H$40
$AttributeMap.$W$31 | $'5.4'.$H$50
$AttributeMap.$AB$16 | $'6.1'.$H$50
$AttributeMap.$AB$15 | $'6.1'.$H$10
$AttributeMap.$AC$15 | $'6.1'.$H$20
$AttributeMap.$AD$15 | $'6.1'.$H$30
$AttributeMap.$AE$15 | $'6.1'.$H$40
$'6.1.1'.$A$1 | $'6.1'.$C$10
$'6.1.2'.$A$1 | $'6.1'.$C$20
$'6.1.3'.$A$1 | $'6.1'.$C$30
$'6.1.4'.$A$1 | $'6.1'.$C$40
$'6.1.5'.$A$1 | $'6.1'.$C$50
$AttributeMap.$AB$20 | $'6.2'.$H$10
$AttributeMap.$AC$20 | $'6.2'.$H$20
$AttributeMap.$AD$20 | $'6.2'.$H$30
$AttributeMap.$AE$25 | $'6.3'.$H$40
$AttributeMap.$AB$25 | $'6.3'.$H$10
$AttributeMap.$AC$25 | $'6.3'.$H$20
$AttributeMap.$AD$25 | $'6.3'.$H$30
$AttributeMap.$AJ$15 | $'7.1'.$H$40
$AttributeMap.$AG$15 | $'7.1'.$H$10
$AttributeMap.$AH$15 | $'7.1'.$H$20
$AttributeMap.$AI$15 | $'7.1'.$H$30
$AttributeMap.$AG$20 | $'7.2'.$H$10
$AttributeMap.$AH$20 | $'7.2'.$H$20
$AttributeMap.$AI$20 | $'7.2'.$H$30
http://www.gridpp.ac.uk/eb/021000/ATLAS/index.html | $'7.2'.$C$20
$J$10 | $'7.2'.$C$10
$AttributeMap.$AJ$25 | $'7.3'.$H$40
$AttributeMap.$AG$25 | $'7.3'.$H$10
$AttributeMap.$AH$25 | $'7.3'.$H$20
$AttributeMap.$AI$25 | $'7.3'.$H$30
http://www.gridpp.ac.uk/talks/ | $'6.1.1'.$B$17
http://www.gridpp.ac.uk/papers/ | $'6.1.5'.$B$17

## OldLinks
Target document or Cell | Link Origin
Dummy Entry
$AttributeMap.$H$49 | $MasterMap.$H$49
http://www.gridpp.ac.uk/eb/applications.html | $MasterMap.$K$49
http://ganga/web.cern.ch/ganga/ | $MasterMap.$P$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CMS_milestones.doc | $MasterMap.$P$29
$AttributeMap.$R$39 | $MasterMap.$R$39
$AttributeMap.$C$24 | $MasterMap.$C$24
$AttributeMap.$C$29 | $MasterMap.$C$29
$AttributeMap.$C$34 | $MasterMap.$C$34
$AttributeMap.$H$14 | $MasterMap.$H$14
$AttributeMap.$H$19 | $MasterMap.$H$19
$AttributeMap.$H$24 | $MasterMap.$H$24
$AttributeMap.$H$29 | $MasterMap.$H$29
$AttributeMap.$H$34 | $MasterMap.$H$34
$AttributeMap.$H$39 | $MasterMap.$H$39
$AttributeMap.$H$44 | $MasterMap.$H$44
$AttributeMap.$M$14 | $MasterMap.$M$14
$AttributeMap.$M$19 | $MasterMap.$M$19
$AttributeMap.$M$29 | $MasterMap.$M$29
$AttributeMap.$M$34 | $MasterMap.$M$34
$AttributeMap.$M$39 | $MasterMap.$M$39
$AttributeMap.$R$14 | $MasterMap.$R$14
$AttributeMap.$R$19 | $MasterMap.$R$19
$AttributeMap.$R$24 | $MasterMap.$R$24
$AttributeMap.$R$29 | $MasterMap.$R$29
$AttributeMap.$R$34 | $MasterMap.$R$34
$AttributeMap.$W$14 | $MasterMap.$W$14
$AttributeMap.$W$19 | $MasterMap.$W$19
$AttributeMap.$W$24 | $MasterMap.$W$24
$AttributeMap.$W$29 | $MasterMap.$W$29
$AttributeMap.$AB$14 | $MasterMap.$AB$14
$AttributeMap.$AB$19 | $MasterMap.$AB$19
$AttributeMap.$AB$24 | $MasterMap.$AB$24
$AttributeMap.$AG$14 | $MasterMap.$AG$14
$AttributeMap.$AG$19 | $MasterMap.$AG$19
$AttributeMap.$AG$24 | $MasterMap.$AG$24
$AttributeMap.$M$49 | $MasterMap.$M$49
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_milestones.doc | $MasterMap.$P$14
http://www.cern.ch/lcg/peb/documents/21june02_LCG_planning_status.doc | $MasterMap.$F$14
http://server11.infn.it/workload-grid/ | $MasterMap.$K$14
http://eu-datagrid.web.cern.ch/eu-datagrid/Intranet_Home.htm | $MasterMap.$J$10
http://lhcgrid.web.cern.ch/LHCgrid/ | $MasterMap.$E$10
http://grid-data-management.web.cern.ch/grid-data-management/ | $MasterMap.$K$19
http://hepunx.rl.ac.uk/edg/wp3/ | $MasterMap.$K$24
http://hep-proj-grid-fabric.web.cern.ch/hep-proj-grid-fabric/ | $MasterMap.$K$29
http://proj-datagrid-masstorage.web.cern.ch/proj-datagrid-masstorage/ | $MasterMap.$K$34
http://marianne.in2p3.fr/ | $MasterMap.$K$39
http://www.gridpp.ac.uk/wp7/index.html | $MasterMap.$K$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/BaBar_milestones.doc | $MasterMap.$P$34
$AttributeMap.$M$24 | $MasterMap.$M$24
$AttributeMap.$M$44 | $MasterMap.$M$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/SAM_milestones.doc | $MasterMap.$P$39
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CDF_milestones.doc | $MasterMap.$P$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Gaudi_milestones.doc | $MasterMap.$P$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/LHCb_milestones.doc | $MasterMap.$P$24
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/UKQCD_milestones.doc | $MasterMap.$P$44
http://www.gridpp.ac.uk/open_source.html | $MasterMap.$Z$19
$AttributeMap.$C$14 | $MasterMap.$C$14
$AttributeMap.$C$19 | $MasterMap.$C$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CERN_goals.doc | $MasterMap.$B$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGrid_goals.doc | $MasterMap.$G$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Application_goals.doc | $MasterMap.$L$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Infrastructure_goals.doc | $MasterMap.$Q$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Interoperability_goals.doc | $MasterMap.$V$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Dissemination_goals.doc | $MasterMap.$AA$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Resource_goals.doc | $MasterMap.$AF$10
$'2.8'.$B$2 | $AttributeMap.$K$49
$MasterMap.$H$49 | $AttributeMap.$H$49
$'2.8'.$B$2 | $AttributeMap.$H$50
$'2.8'.$B$12 | $AttributeMap.$I$50
$'2.8'.$B$22 | $AttributeMap.$J$50
$'2.8'.$B$32 | $AttributeMap.$K$50
$'2.8'.$B$42 | $AttributeMap.$H$51
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CERN_goals.doc | $AttributeMap.$B$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGrid_goals.doc | $AttributeMap.$G$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Application_goals.doc | $AttributeMap.$L$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Infrastructure_goals.doc | $AttributeMap.$Q$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Interoperability_goals.doc | $AttributeMap.$V$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Dissemination_goals.doc | $AttributeMap.$AA$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Resource_goals.doc | $AttributeMap.$AF$10
$'3.4'.$B$2 | $AttributeMap.$M$30
$'3.4'.$B$12 | $AttributeMap.$N$30
$'3.4'.$B$22 | $AttributeMap.$O$30
$'3.4'.$B$42 | $AttributeMap.$M$31
$'3.4'.$B$52 | $AttributeMap.$N$31
$'3.4'.$B$62 | $AttributeMap.$O$31
$'3.4'.$B$82 | $AttributeMap.$M$32
$'3.4'.$B$92 | $AttributeMap.$N$32
$'3.4'.$B$72 | $AttributeMap.$P$31
$'3.4'.$B$32 | $AttributeMap.$P$30
$'1.1'.$B$12 | $AttributeMap.$D$15
$'1.1'.$B$22 | $AttributeMap.$E$15
$'1.1'.$B$32 | $AttributeMap.$F$15
$'3.3'.$B$2 | $AttributeMap.$P$24
$'1.1'.$B$2 | $AttributeMap.$F$14
$MasterMap.$R$14 | $AttributeMap.$R$14
$MasterMap.$W$14 | $AttributeMap.$W$14
$MasterMap.$AB$14 | $AttributeMap.$AB$14
$MasterMap.$AG$14 | $AttributeMap.$AG$14
$MasterMap.$AG$19 | $AttributeMap.$AG$19
$MasterMap.$AB$19 | $AttributeMap.$AB$19
$MasterMap.$W$19 | $AttributeMap.$W$19
$MasterMap.$R$19 | $AttributeMap.$R$19
$MasterMap.$C$24 | $AttributeMap.$C$24
$MasterMap.$R$24 | $AttributeMap.$R$24
$MasterMap.$W$24 | $AttributeMap.$W$24
$MasterMap.$AB$24 | $AttributeMap.$AB$24
$MasterMap.$AG$24 | $AttributeMap.$AG$24
$MasterMap.$R$39 | $AttributeMap.$R$39
$'3.2'.$B$2 | $AttributeMap.$P$19
$'4.1'.$B$2 | $AttributeMap.$U$14
$'5.1'.$B$2 | $AttributeMap.$Z$14
$'6.1'.$B$2 | $AttributeMap.$AE$14
$'7.1'.$B$2 | $AttributeMap.$AJ$14
$'7.2'.$B$2 | $AttributeMap.$AJ$19
$'7.3'.$B$2 | $AttributeMap.$AJ$24
$'6.3'.$B$2 | $AttributeMap.$AE$24
$'6.2'.$B$2 | $AttributeMap.$AE$19
$'5.2'.$B$2 | $AttributeMap.$Z$19
$'5.3'.$B$2 | $AttributeMap.$Z$24
$'4.2'.$B$2 | $AttributeMap.$U$19
$'4.3'.$B$2 | $AttributeMap.$U$24
$'4.4'.$B$2 | $AttributeMap.$U$29
$'4.6'.$B$2 | $AttributeMap.$U$39
$'3.4'.$B$2 | $AttributeMap.$P$29
$'3.5'.$B$2 | $AttributeMap.$P$34
$'3.6'.$B$2 | $AttributeMap.$P$39
$'1.2'.$B$2 | $AttributeMap.$F$19
$'1.3'.$B$2 | $AttributeMap.$F$24
$'1.4'.$B$2 | $AttributeMap.$F$29
$MasterMap.$M$19 | $AttributeMap.$M$19
$MasterMap.$C$29 | $AttributeMap.$C$29
$MasterMap.$R$29 | $AttributeMap.$R$29
$'3.6'.$B$2 | $AttributeMap.$M$40
$'3.6'.$B$12 | $AttributeMap.$N$40
$'3.6'.$B$22 | $AttributeMap.$O$40
$'3.6'.$B$32 | $AttributeMap.$P$40
$'3.6'.$B$42 | $AttributeMap.$M$41
$'3.6'.$B$52 | $AttributeMap.$N$41
$'3.6'.$B$62 | $AttributeMap.$O$41
$'3.6'.$B$72 | $AttributeMap.$P$41
$'3.6'.$B$82 | $AttributeMap.$M$42
$'3.6'.$B$92 | $AttributeMap.$N$42
$'3.6'.$B$102 | $AttributeMap.$O$42
$'3.6'.$B$112 | $AttributeMap.$P$42
$'3.2'.$B$2 | $AttributeMap.$M$20
$'3.2'.$B$12 | $AttributeMap.$N$20
$'3.2'.$B$22 | $AttributeMap.$O$20
$'3.2'.$B$32 | $AttributeMap.$P$20
$'3.2'.$B$42 | $AttributeMap.$M$21
$'3.2'.$B$52 | $AttributeMap.$N$21
$'3.2'.$B$62 | $AttributeMap.$O$21
$'3.2'.$B$72 | $AttributeMap.$P$21
$'3.2'.$B$82 | $AttributeMap.$M$22
$'3.7'.$B$2 | $AttributeMap.$M$45
$'3.7'.$B$12 | $AttributeMap.$N$45
$'3.7'.$B$22 | $AttributeMap.$O$45
$'3.7'.$B$32 | $AttributeMap.$P$45
$'3.7'.$B$42 | $AttributeMap.$M$46
$'3.7'.$B$52 | $AttributeMap.$N$46
$'3.8'.$B$2 | $AttributeMap.$M$50
$'3.8'.$B$12 | $AttributeMap.$N$50
$'3.8'.$B$22 | $AttributeMap.$O$50
$'1.5'.$B$2 | $AttributeMap.$F$34
$MasterMap.$C$34 | $AttributeMap.$C$34
$'1.2'.$B$2 | $AttributeMap.$C$20
$'1.2'.$B$12 | $AttributeMap.$D$20
$'1.2'.$B$22 | $AttributeMap.$E$20
$'1.2'.$B$32 | $AttributeMap.$F$20
$'1.2'.$B$42 | $AttributeMap.$C$21
$'1.3'.$B$2 | $AttributeMap.$C$25
$'1.3'.$B$12 | $AttributeMap.$D$25
$'1.3'.$B$22 | $AttributeMap.$E$25
$'1.3'.$B$32 | $AttributeMap.$F$25
$'1.3'.$B$42 | $AttributeMap.$C$26
$'1.4'.$B$2 | $AttributeMap.$C$30
$'1.4'.$B$12 | $AttributeMap.$D$30
$'1.4'.$B$22 | $AttributeMap.$E$30
$'1.4'.$B$32 | $AttributeMap.$F$30
$'1.5'.$B$2 | $AttributeMap.$C$35
$'1.5'.$B$12 | $AttributeMap.$D$35
$'1.5'.$B$22 | $AttributeMap.$E$35
$'1.5'.$B$32 | $AttributeMap.$F$35
$'1.5'.$B$42 | $AttributeMap.$C$36
$'1.5'.$B$52 | $AttributeMap.$D$36
$'4.1'.$B$2 | $AttributeMap.$R$15
$'4.1'.$B$12 | $AttributeMap.$S$15
$'4.1'.$B$22 | $AttributeMap.$T$15
$'4.1'.$B$32 | $AttributeMap.$U$15
$'4.1'.$B$42 | $AttributeMap.$R$16
$'4.1'.$B$52 | $AttributeMap.$S$16
$'4.1'.$B$62 | $AttributeMap.$T$16
$'4.1'.$B$72 | $AttributeMap.$U$16
$'4.1'.$B$82 | $AttributeMap.$R$17
$'4.3'.$B$2 | $AttributeMap.$R$25
$'4.3'.$B$12 | $AttributeMap.$S$25
$'4.3'.$B$22 | $AttributeMap.$T$25
$'4.3'.$B$32 | $AttributeMap.$U$25
$'4.3'.$B$42 | $AttributeMap.$R$26
$'4.2'.$B$2 | $AttributeMap.$R$20
$'4.2'.$B$12 | $AttributeMap.$S$20
$'4.2'.$B$22 | $AttributeMap.$T$20
$'4.2'.$B$32 | $AttributeMap.$U$20
$'4.2'.$B$42 | $AttributeMap.$R$21
$'4.2'.$B$52 | $AttributeMap.$S$21
$'4.2'.$B$62 | $AttributeMap.$T$21
$'4.4'.$B$2 | $AttributeMap.$R$30
$'4.4'.$B$12 | $AttributeMap.$S$30
$'4.4'.$B$22 | $AttributeMap.$T$30
$'4.4'.$B$32 | $AttributeMap.$U$30
$'4.4'.$B$42 | $AttributeMap.$R$31
$'4.6'.$B$2 | $AttributeMap.$R$40
$MasterMap.$W$29 | $AttributeMap.$W$29
$'5.4'.$B$2 | $AttributeMap.$Z$29
$'5.1'.$B$2 | $AttributeMap.$W$15
$'5.1'.$B$12 | $AttributeMap.$X$15
$'5.1'.$B$22 | $AttributeMap.$Y$15
$'5.2'.$B$2 | $AttributeMap.$W$20
$'5.3'.$B$2 | $AttributeMap.$W$25
$'5.4'.$B$2 | $AttributeMap.$W$30
$'6.1'.$B$2 | $AttributeMap.$AB$15
$'6.1'.$B$12 | $AttributeMap.$AC$15
$'6.1'.$B$22 | $AttributeMap.$AD$15
$'6.1'.$B$42 | $AttributeMap.$AB$16
$'6.2'.$B$2 | $AttributeMap.$AB$20
$'6.2'.$B$12 | $AttributeMap.$AC$20
$'6.2'.$B$22 | $AttributeMap.$AD$20
$'6.3'.$B$2 | $AttributeMap.$AB$25
$'6.3'.$B$12 | $AttributeMap.$AC$25
$'6.3'.$B$22 | $AttributeMap.$AD$25
$'6.3'.$B$32 | $AttributeMap.$AE$25
$'7.1'.$B$2 | $AttributeMap.$AG$15
$'7.1'.$B$12 | $AttributeMap.$AH$15
$'7.1'.$B$22 | $AttributeMap.$AI$15
$'7.1'.$B$32 | $AttributeMap.$AJ$15
$'7.2'.$B$2 | $AttributeMap.$AG$20
$'7.2'.$B$12 | $AttributeMap.$AH$20
$'7.2'.$B$22 | $AttributeMap.$AI$20
$'7.3'.$B$2 | $AttributeMap.$AG$25
$'7.3'.$B$12 | $AttributeMap.$AH$25
$'7.3'.$B$22 | $AttributeMap.$AI$25
$'7.3'.$B$32 | $AttributeMap.$AJ$25
$'4.5'.$B$2 | $AttributeMap.$U$34
$MasterMap.$R$34 | $AttributeMap.$R$34
$'4.5'.$B$2 | $AttributeMap.$R$35
$'4.5'.$B$12 | $AttributeMap.$S$35
$'4.5'.$B$22 | $AttributeMap.$T$35
$'4.5'.$B$32 | $AttributeMap.$U$35
$'4.6'.$B$12 | $AttributeMap.$S$40
$'4.6'.$B$22 | $AttributeMap.$T$40
$'5.4'.$B$32 | $AttributeMap.$Z$30
$'5.4'.$B$42 | $AttributeMap.$W$31
$'5.2'.$B$12 | $AttributeMap.$X$20
$'5.2'.$B$22 | $AttributeMap.$Y$20
$'5.3'.$B$12 | $AttributeMap.$X$25
$'5.3'.$B$22 | $AttributeMap.$Y$25
$'5.4'.$B$12 | $AttributeMap.$X$30
$'5.4'.$B$22 | $AttributeMap.$Y$30
$MasterMap.$H$14 | $AttributeMap.$H$14
$MasterMap.$H$19 | $AttributeMap.$H$19
$'2.1'.$B$2 | $AttributeMap.$K$14
$'2.2'.$B$2 | $AttributeMap.$K$19
$'2.3'.$B$2 | $AttributeMap.$K$24
$'2.4'.$B$2 | $AttributeMap.$K$29
$MasterMap.$H$29 | $AttributeMap.$H$29
$'2.5'.$B$2 | $AttributeMap.$K$34
$MasterMap.$H$34 | $AttributeMap.$H$34
$'2.6'.$B$2 | $AttributeMap.$K$39
$MasterMap.$H$39 | $AttributeMap.$H$39
$'2.7'.$B$2 | $AttributeMap.$K$44
$MasterMap.$H$44 | $AttributeMap.$H$44
$'2.2'.$B$2 | $AttributeMap.$H$20
$'2.2'.$B$12 | $AttributeMap.$I$20
$'2.2'.$B$22 | $AttributeMap.$J$20
$'2.3'.$B$2 | $AttributeMap.$H$25
$'2.3'.$B$12 | $AttributeMap.$I$25
$'2.3'.$B$22 | $AttributeMap.$J$25
$'2.4'.$B$2 | $AttributeMap.$H$30
$'2.4'.$B$12 | $AttributeMap.$I$30
$'2.4'.$B$22 | $AttributeMap.$J$30
$'2.5'.$B$2 | $AttributeMap.$H$35
$'2.5'.$B$12 | $AttributeMap.$I$35
$'2.5'.$B$22 | $AttributeMap.$J$35
$'2.6'.$B$2 | $AttributeMap.$H$40
$'2.6'.$B$12 | $AttributeMap.$I$40
$'2.6'.$B$22 | $AttributeMap.$J$40
$'2.7'.$B$2 | $AttributeMap.$H$45
$'2.7'.$B$12 | $AttributeMap.$I$45
$'2.7'.$B$22 | $AttributeMap.$J$45
$'2.2'.$B$32 | $AttributeMap.$K$20
$'2.2'.$B$42 | $AttributeMap.$H$21
$'2.2'.$B$52 | $AttributeMap.$I$21
$'2.2'.$B$62 | $AttributeMap.$J$21
$'2.3'.$B$32 | $AttributeMap.$K$25
$'2.3'.$B$42 | $AttributeMap.$H$26
$'2.3'.$B$52 | $AttributeMap.$I$26
$'2.3'.$B$62 | $AttributeMap.$J$26
$'2.4'.$B$32 | $AttributeMap.$K$30
$'2.4'.$B$42 | $AttributeMap.$H$31
$'2.4'.$B$52 | $AttributeMap.$I$31
$'2.4'.$B$62 | $AttributeMap.$J$31
$'2.5'.$B$32 | $AttributeMap.$K$35
$'2.5'.$B$42 | $AttributeMap.$H$36
$'2.5'.$B$52 | $AttributeMap.$I$36
$'2.5'.$B$62 | $AttributeMap.$J$36
$'2.6'.$B$32 | $AttributeMap.$K$40
$'2.6'.$B$42 | $AttributeMap.$H$41
$'2.6'.$B$52 | $AttributeMap.$I$41
$'2.6'.$B$62 | $AttributeMap.$J$41
$'2.6'.$B$72 | $AttributeMap.$K$41
$'2.6'.$B$82 | $AttributeMap.$H$42
$'2.7'.$B$32 | $AttributeMap.$K$45
$'2.7'.$B$42 | $AttributeMap.$H$46
$'2.7'.$B$52 | $AttributeMap.$I$46
$'2.7'.$B$62 | $AttributeMap.$J$46
$'2.7'.$B$72 | $AttributeMap.$K$46
$'1.2'.$B$52 | $AttributeMap.$D$21
$'1.3'.$B$52 | $AttributeMap.$D$26
$'1.4'.$B$42 | $AttributeMap.$C$31
$'1.5'.$B$62 | $AttributeMap.$E$36
$'6.1'.$B$32 | $AttributeMap.$AE$15
$MasterMap.$H$24 | $AttributeMap.$H$24
$'2.1'.$B$2 | $AttributeMap.$H$15
$'2.1'.$B$12 | $AttributeMap.$I$15
$'2.1'.$B$22 | $AttributeMap.$J$15
$'2.1'.$B$32 | $AttributeMap.$K$15
$'2.1'.$B$42 | $AttributeMap.$H$16
$'2.1'.$B$52 | $AttributeMap.$I$16
$'2.1'.$B$62 | $AttributeMap.$J$16
$'2.1'.$B$72 | $AttributeMap.$K$16
$'2.1'.$B$82 | $AttributeMap.$H$17
$MasterMap.$M$14 | $AttributeMap.$M$14
$'3.1'.$B$2 | $AttributeMap.$P$14
$'3.1'.$B$2 | $AttributeMap.$M$15
$'3.1'.$B$12 | $AttributeMap.$N$15
$'3.1'.$B$22 | $AttributeMap.$O$15
$'3.1'.$B$32 | $AttributeMap.$P$15
$'3.1'.$B$42 | $AttributeMap.$M$16
$'3.1'.$B$52 | $AttributeMap.$N$16
$'3.1'.$B$62 | $AttributeMap.$O$16
$'3.1'.$B$72 | $AttributeMap.$P$16
$'3.1'.$B$82 | $AttributeMap.$M$17
$MasterMap.$M$49 | $AttributeMap.$M$49
$'3.1'.$B$92 | $AttributeMap.$N$17
$'3.8'.$B$2 | $AttributeMap.$P$49
$'3.5'.$B$2 | $AttributeMap.$M$35
$'3.5'.$B$12 | $AttributeMap.$N$35
$'3.5'.$B$22 | $AttributeMap.$O$35
$'3.5'.$B$32 | $AttributeMap.$P$35
$'3.5'.$B$42 | $AttributeMap.$M$36
$'3.5'.$B$52 | $AttributeMap.$N$36
$'3.5'.$B$62 | $AttributeMap.$O$36
$'1.1'.$B$2 | $AttributeMap.$C$15
$'3.3'.$B$2 | $AttributeMap.$M$25
$'3.3'.$B$12 | $AttributeMap.$N$25
$'3.3'.$B$22 | $AttributeMap.$O$25
$MasterMap.$M$24 | $AttributeMap.$M$24
$MasterMap.$M$29 | $AttributeMap.$M$29
$MasterMap.$M$34 | $AttributeMap.$M$34
$MasterMap.$M$39 | $AttributeMap.$M$39
$MasterMap.$M$44 | $AttributeMap.$M$44
$'3.7'.$B$2 | $AttributeMap.$P$44
$'3.3'.$B$32 | $AttributeMap.$P$25
$'3.3'.$B$42 | $AttributeMap.$M$26
$'3.3'.$B$52 | $AttributeMap.$N$26
$'4.4'.$B$52 | $AttributeMap.$S$31
$'1.1'.$B$42 | $AttributeMap.$C$16
$MasterMap.$C$14 | $AttributeMap.$C$14
$MasterMap.$C$19 | $AttributeMap.$C$19
http://lhcgrid.web.cern.ch/LHCgrid/ | $AttributeMap.$E$10
http://eu-datagrid.web.cern.ch/eu-datagrid/Intranet_Home.htm | $AttributeMap.$J$10
$'1.4'.$B$52 | $AttributeMap.$D$31
$'1.4'.$B$62 | $AttributeMap.$E$31
$'1.4'.$B$72 | $AttributeMap.$F$31
$'1.4'.$B$82 | $AttributeMap.$C$32
$'1.5'.$B$72 | $AttributeMap.$F$36
$'1.5'.$B$82 | $AttributeMap.$C$37
$'1.5'.$B$92 | $AttributeMap.$D$37
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R41-INF.doc | $RiskRegister.$R$44
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R42-INF.doc | $RiskRegister.$R$45
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R26-INF.doc | $RiskRegister.$R$29
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-GridPP.doc | $RiskRegister.$F$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-EDG.doc | $RiskRegister.$L$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R40-EDG.doc | $RiskRegister.$L$43
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R13-INF.doc | $RiskRegister.$R$16
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R30-INF.doc | $RiskRegister.$R$33
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R31-INF.doc | $RiskRegister.$R$34
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R32-INF.doc | $RiskRegister.$R$35
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-INF.doc | $RiskRegister.$R$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R22-INF.doc | $RiskRegister.$R$25
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-INF.doc | $RiskRegister.$R$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-INF.doc | $RiskRegister.$R$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R23-INF.doc | $RiskRegister.$R$26
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R24-INF.doc | $RiskRegister.$R$27
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R33-IOP.doc | $RiskRegister.$U$36
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-LCG.doc | $RiskRegister.$I$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-LCG.doc | $RiskRegister.$I$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-LCG.doc | $RiskRegister.$I$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R6-LCG.doc | $RiskRegister.$I$9
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R7-LCG.doc | $RiskRegister.$I$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R8-LCG.doc | $RiskRegister.$I$11
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R10-LCG.doc | $RiskRegister.$I$13
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-LCG.doc | $RiskRegister.$I$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R12-LCG.doc | $RiskRegister.$I$15
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R13-LCG.doc | $RiskRegister.$I$16
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R14-LCG.doc | $RiskRegister.$I$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R15-LCG.doc | $RiskRegister.$I$18
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R16-LCG.doc | $RiskRegister.$I$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R18-LCG.doc | $RiskRegister.$I$21
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R35-LCG.doc | $RiskRegister.$I$38
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R8-GridPP.doc | $RiskRegister.$F$11
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R9-GridPP.doc | $RiskRegister.$F$12
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R3-INF.doc | $RiskRegister.$R$6
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-INF.doc | $RiskRegister.$R$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R14-INF.doc | $RiskRegister.$R$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R20-INF.doc | $RiskRegister.$R$23
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R25-INF.doc | $RiskRegister.$R$28
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R27-INF.doc | $RiskRegister.$R$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R28-INF.doc | $RiskRegister.$R$31
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R29-INF.doc | $RiskRegister.$R$32
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-APP.doc | $RiskRegister.$O$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R2-APP.doc | $RiskRegister.$O$5
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R3-APP.doc | $RiskRegister.$O$6
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R4-APP.doc | $RiskRegister.$O$7
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R6-APP.doc | $RiskRegister.$O$9
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R7-APP.doc | $RiskRegister.$O$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R10-APP.doc | $RiskRegister.$O$13
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-APP.doc | $RiskRegister.$O$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R19-APP.doc | $RiskRegister.$O$22
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R20-APP.doc | $RiskRegister.$O$23
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R21-APP.doc | $RiskRegister.$O$24
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R12-GridPP.doc | $RiskRegister.$F$15
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R16-GridPP.doc | $RiskRegister.$F$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R17-GridPP.doc | $RiskRegister.$F$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R34-IOP.doc | $RiskRegister.$U$37
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R35-IOP.doc | $RiskRegister.$U$38
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R36-IOP.doc | $RiskRegister.$U$39
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R37-GridPP.doc | $RiskRegister.$F$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R39-GridPP.doc | $RiskRegister.$F$42
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R40-GridPP.doc | $RiskRegister.$F$43
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R11-EDG.doc | $RiskRegister.$L$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R12-EDG.doc | $RiskRegister.$L$15
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R14-EDG.doc | $RiskRegister.$L$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R15-EDG.doc | $RiskRegister.$L$18
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R16-EDG.doc | $RiskRegister.$L$19
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R38-GridPP.doc | $RiskRegister.$F$41
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R1-EDG.doc | $RiskRegister.$L$4
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R3-EDG.doc | $RiskRegister.$L$6
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R4-EDG.doc | $RiskRegister.$L$7
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R5-EDG.doc | $RiskRegister.$L$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R6-EDG.doc | $RiskRegister.$L$9
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R7-EDG.doc | $RiskRegister.$L$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R8-EDG.doc | $RiskRegister.$L$11
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RiskRegister/R10-EDG.doc | $RiskRegister.$L$13
$'6.1.1'.$A$1 | $SL_Summary.$A$4
$'6.1.2'.$A$1 | $SL_Summary.$A$5
$'6.1.3'.$A$1 | $SL_Summary.$A$6
$'6.1.4'.$A$1 | $SL_Summary.$A$7
$'6.1.5'.$A$1 | $SL_Summary.$A$8
$'6.2.1'.$A$1 | $SL_Summary.$A$10
$'6.2.2'.$A$1 | $SL_Summary.$A$11
$'6.2.3'.$A$1 | $SL_Summary.$A$12
$'6.3.1'.$A$1 | $SL_Summary.$A$14
$'6.3.2'.$A$1 | $SL_Summary.$A$15
$'6.3.3'.$A$1 | $SL_Summary.$A$16
$'6.3.4'.$A$1 | $SL_Summary.$A$17
$'6.2.1'.$A$12 | $SL_Summary.$A$19
$'6.2.3'.$A$10 | $SL_Summary.$A$20
$'6.2.3'.$A$17 | $SL_Summary.$A$21
$'6.2.3'.$A$23 | $SL_Summary.$A$22
$'6.2.3'.$A$29 | $SL_Summary.$A$23
$'6.2.3'.$A$35 | $SL_Summary.$A$24
$'6.2.3'.$A$42 | $SL_Summary.$A$25
$'6.2.3'.$A$49 | $SL_Summary.$A$26
$AttributeMap.$C$15 | $'1.1'.$H$10
$AttributeMap.$D$15 | $'1.1'.$H$20
$AttributeMap.$E$15 | $'1.1'.$H$30
$AttributeMap.$F$15 | $'1.1'.$H$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/lcg status 14sep02.ppt | $'1.1'.$C$10
http://lhcgrid.web.cern.ch/LHCgrid/peb/membership.htm | $'1.1'.$C$20
http://www.cern.ch/lcg/peb/documents/21june02_LCG_planning_status.doc | $'1.1'.$C$30
$AttributeMap.$C$16 | $'1.1'.$H$50
http://lcg.web.cern.ch/LCG/PEB/Planning/default.htm | $'1.1'.$K$30
http://lcgapp.cern.ch/project/cls/documents/SEAL_Project_Plan_0_1.pdf | $'1.2'.$C$40
$AttributeMap.$C$20 | $'1.2'.$H$10
$AttributeMap.$D$20 | $'1.2'.$H$20
$AttributeMap.$E$20 | $'1.2'.$H$30
$AttributeMap.$F$20 | $'1.2'.$H$40
$AttributeMap.$C$21 | $'1.2'.$H$50
$AttributeMap.$D$21 | $'1.2'.$H$60
$'1.2'.$B$2 | $'1.2'.$G$38
$'1.2'.$B$22 | $'1.2'.$G$39
http://lcgapp.cern.ch/project/spi | $'1.2'.$C$10
http://lcgapp.cern.ch/project/persist | $'1.2'.$C$20
$J$23 | $'1.2'.$C$30
http://seal.web.cern.ch/seal/documents/SEAL_AAM_12_Feb_2003.ppt | $'1.2'.$J$26
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/LCG1.3.5.ppt | $'1.3'.$C$50
$AttributeMap.$C$25 | $'1.3'.$H$10
$AttributeMap.$D$25 | $'1.3'.$H$20
$AttributeMap.$E$25 | $'1.3'.$H$30
$AttributeMap.$F$25 | $'1.3'.$H$40
$AttributeMap.$C$26 | $'1.3'.$H$50
$AttributeMap.$D$26 | $'1.3'.$H$60
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/tape drive purchase.doc | $'1.3'.$C$10
$B$22 | $'1.3'.$G$38
$'1.2'.$B$2 | $'1.3'.$G$39
http://lcg.web.cern.ch/LCG/PEB/gdb/WG1/WG1_Postfinal.2.doc | $'1.4'.$C$10
http://lcg.web.cern.ch/LCG/PEB/Planning/default.htm | $'1.4'.$J$3
$J$20 | $'1.4'.$C$20
http://lcg.web.cern.ch/LCG/PEB/gdb | $'1.4'.$J$20
$AttributeMap.$C$30 | $'1.4'.$H$10
$AttributeMap.$D$30 | $'1.4'.$H$20
$AttributeMap.$E$30 | $'1.4'.$H$30
$AttributeMap.$F$30 | $'1.4'.$H$40
$AttributeMap.$C$31 | $'1.4'.$H$50
http://cern.ch/grid-deployment | $'1.4'.$C$30
$AttributeMap.$D$31 | $'1.4'.$H$60
$AttributeMap.$E$31 | $'1.4'.$H$70
$AttributeMap.$F$31 | $'1.4'.$H$80
$AttributeMap.$C$32 | $'1.4'.$H$90
$J$49 | $'1.4'.$C$50
$J$10 | $'1.5'.$C$10
http://lcg.web.cern.ch/LCG/PEB/gdb | $'1.5'.$J$10
$AttributeMap.$C$35 | $'1.5'.$H$10
$AttributeMap.$D$35 | $'1.5'.$H$20
$AttributeMap.$E$35 | $'1.5'.$H$30
$AttributeMap.$F$35 | $'1.5'.$H$40
$AttributeMap.$C$36 | $'1.5'.$H$50
$AttributeMap.$D$36 | $'1.5'.$H$60
$AttributeMap.$E$36 | $'1.5'.$H$70
$'1.4'.$B$2 | $'1.5'.$G$28
$'1.5'.$B$12 | $'1.5'.$G$29
$'1.2'.$B$32 | $'1.5'.$G$58
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.2.doc | $'1.5'.$J$12
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.3.doc | $'1.5'.$J$22
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.4.doc | $'1.5'.$J$32
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.5.doc | $'1.5'.$J$42
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LCG1.5.6.doc | $'1.5'.$J$53
$AttributeMap.$F$36 | $'1.5'.$H$80
$AttributeMap.$C$37 | $'1.5'.$H$90
$AttributeMap.$D$37 | $'1.5'.$H$100
$J$70 | $'1.5'.$C$70
$'1.4'.$B$72 | $'1.5'.$G$88
$B$72 | $'1.5'.$G$89
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.1'.$C$70
$AttributeMap.$J$15 | $'2.1'.$H$30
$AttributeMap.$K$15 | $'2.1'.$H$40
$AttributeMap.$H$15 | $'2.1'.$H$10
$AttributeMap.$I$15 | $'2.1'.$H$20
$AttributeMap.$H$17 | $'2.1'.$H$90
$AttributeMap.$K$16 | $'2.1'.$H$80
$AttributeMap.$J$16 | $'2.1'.$H$70
$AttributeMap.$H$16 | $'2.1'.$H$50
$AttributeMap.$I$16 | $'2.1'.$H$60
http://server11.infn.it/workload-grid/docs/DataGrid-01-TED-0102-1_0.doc | $'2.1'.$C$30
http://server11.infn.it/workload-grid/docs/DataGrid-01-D1.2-0112-0-3.doc | $'2.1'.$C$40
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287452&document_id=347151&version=1.0&filename=DataGrid-01-D1.4-0127-1_0.doc | $'2.1'.$C$60
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.1'.$C$50
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGridEffort.txt | $'2.1'.$D$8
$AttributeMap.$H$20 | $'2.2'.$H$10
$AttributeMap.$I$20 | $'2.2'.$H$20
$AttributeMap.$J$21 | $'2.2'.$H$70
$AttributeMap.$I$21 | $'2.2'.$H$60
$AttributeMap.$H$21 | $'2.2'.$H$50
$AttributeMap.$J$20 | $'2.2'.$H$30
$AttributeMap.$K$20 | $'2.2'.$H$40
http://grid-data-management.web.cern.ch/grid-data-management/docs/DataGrid-02-D2.1-0105-2_0.doc | $'2.2'.$C$20
http://grid-data-management.web.cern.ch/grid-data-management/docs/DataGrid-02-D2.2-0103-1_2.doc | $'2.2'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.2'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.2'.$C$50
$AttributeMap.$H$25 | $'2.3'.$H$10
$AttributeMap.$I$25 | $'2.3'.$H$20
$AttributeMap.$J$25 | $'2.3'.$H$30
$AttributeMap.$K$25 | $'2.3'.$H$40
$AttributeMap.$H$26 | $'2.3'.$H$50
$AttributeMap.$I$26 | $'2.3'.$H$60
$AttributeMap.$J$26 | $'2.3'.$H$70
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241263&document_id=332476&version=2-0&filename=DataGrid-03-D3.1-0102-2-0.doc | $'2.3'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241267&document_id=334453&version=4-0&filename=DataGrid-03-D3.2-334453-4-0.pdf | $'2.3'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.3'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.3'.$C$50
$AttributeMap.$H$30 | $'2.4'.$H$10
$AttributeMap.$I$30 | $'2.4'.$H$20
$AttributeMap.$J$30 | $'2.4'.$H$30
$AttributeMap.$K$30 | $'2.4'.$H$40
$AttributeMap.$H$31 | $'2.4'.$H$50
$AttributeMap.$I$31 | $'2.4'.$H$60
$AttributeMap.$J$31 | $'2.4'.$H$70
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241275&document_id=332371&version=1&filename=datagrid-04-d4.1-0101-3_0.doc | $'2.4'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1241275&document_id=332393&version=1&filename=datagrid-04-d4.2-0119-2-1.doc | $'2.4'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.4'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.4'.$C$50
$AttributeMap.$H$35 | $'2.5'.$H$10
$AttributeMap.$I$35 | $'2.5'.$H$20
$AttributeMap.$J$35 | $'2.5'.$H$30
$AttributeMap.$K$35 | $'2.5'.$H$40
$AttributeMap.$H$36 | $'2.5'.$H$50
$AttributeMap.$I$36 | $'2.5'.$H$60
$AttributeMap.$J$36 | $'2.5'.$H$70
http://edms.cern.ch/document/336677/ | $'2.5'.$C$20
http://edms.cern.ch/document/336679/ | $'2.5'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.5'.$C$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/DataGridEffort.txt | $'2.5'.$D$8
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.5'.$C$50
$AttributeMap.$H$40 | $'2.6'.$H$10
$AttributeMap.$I$40 | $'2.6'.$H$20
$AttributeMap.$J$40 | $'2.6'.$H$30
$AttributeMap.$J$41 | $'2.6'.$H$70
$AttributeMap.$K$41 | $'2.6'.$H$80
$AttributeMap.$H$42 | $'2.6'.$H$90
$AttributeMap.$I$41 | $'2.6'.$H$60
$AttributeMap.$H$41 | $'2.6'.$H$50
$AttributeMap.$K$40 | $'2.6'.$H$40
http://marianne.in2p3.fr/datagrid/documentation/DataGrid-6-D6.1-0101-3-3.doc | $'2.6'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1242681&document_id=332430&version=1.4.2&filename=DataGrid-06-D6.2-0121-1.4.2-ConfMngmt.doc | $'2.6'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.6'.$C$50
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287466&document_id=335299&version=1.0&filename=DataGrid-06-Dx.3-335299-1-0-UsersGuides.doc | $'2.6'.$C$40
https://edms.cern.ch/file/368076/2/DataGrid-06-D6.5-368076-0-5-UsersGuides.doc | $'2.6'.$C$60
$AttributeMap.$H$45 | $'2.7'.$H$10
$AttributeMap.$I$45 | $'2.7'.$H$20
$AttributeMap.$J$45 | $'2.7'.$H$30
$AttributeMap.$K$45 | $'2.7'.$H$40
$AttributeMap.$H$46 | $'2.7'.$H$50
$AttributeMap.$I$46 | $'2.7'.$H$60
$AttributeMap.$J$46 | $'2.7'.$H$70
$AttributeMap.$K$46 | $'2.7'.$H$80
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287475&document_id=347481&version=1.5&filename=DataGrid-07-D7-3-0113-1-5.doc | $'2.7'.$C$40
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287598&document_id=334783&version=2.0&filename=DataGrid-07-D7.1-0109-2-0.doc | $'2.7'.$C$20
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287605&document_id=334883&version=8.1&filename=DataGrid-07-D7-2-0110-8-1.doc | $'2.7'.$C$30
http://edmsoraweb.cern.ch:8001/cedar/doc.download?cookie=1287617&document_id=340234&version=4.0&filename=DataGrid-07-D7.5-0111-4-0-SecurityReq.doc | $'2.7'.$C$60
https://edms.cern.ch/file/344562/2.0/DataGrid-07-D7.6-0112-2-0-SecurityDesign.pdf | $'2.7'.$C$70
$AttributeMap.$H$50 | $'2.8'.$H$10
$AttributeMap.$I$50 | $'2.8'.$H$20
$AttributeMap.$J$50 | $'2.8'.$H$30
$AttributeMap.$K$50 | $'2.8'.$H$40
$AttributeMap.$H$51 | $'2.8'.$H$50
https://edms.cern.ch/file/375586/1.2/wp8-D8.3-0119-3-1.pdf | $'2.8'.$C$40
https://edms.cern.ch/file/332409/1/datagrid-08-d8.1.a_v2.1.pdf | $'2.8'.$C$20
https://edms.cern.ch/file/334920/3.1/D8.2_3.1.pdf | $'2.8'.$C$30
$AttributeMap.$O$15 | $'3.1'.$Q$30
$B$12 | $'3.1'.$P$28
$AttributeMap.$P$15 | $'3.1'.$Q$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.6.doc | $'3.1'.$J$53
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.4.doc | $'3.1'.$J$33
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.3.doc | $'3.1'.$J$23
$J$30 | $'3.1'.$C$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.9NEW.doc | $'3.1'.$J$83
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_arch_rev.pdf | $'3.1'.$C$10
http://www.gridpp.ac.uk/atlas/Projects/ATLASGridProjects.htm | $'3.1'.$J$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_DC_eval.pdf | $'3.1'.$C$50
$AttributeMap.$M$16 | $'3.1'.$Q$50
$B$22 | $'3.1'.$P$48
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.5NEW.doc | $'3.1'.$J$43
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_milestones.doc | $'3.1'.$J$48
$AttributeMap.$M$17 | $'3.1'.$Q$90
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Atlas3.1.9.doc | $'3.1'.$J$82
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ATLAS_milestones.doc | $'3.1'.$J$91
$AttributeMap.$M$15 | $'3.1'.$H$10
$AttributeMap.$N$15 | $'3.1'.$H$20
$AttributeMap.$O$15 | $'3.1'.$H$30
$AttributeMap.$P$15 | $'3.1'.$H$40
$AttributeMap.$M$16 | $'3.1'.$H$50
$AttributeMap.$N$16 | $'3.1'.$H$60
$AttributeMap.$O$16 | $'3.1'.$H$70
$AttributeMap.$P$16 | $'3.1'.$H$80
$AttributeMap.$M$17 | $'3.1'.$H$90
$AttributeMap.$N$17 | $'3.1'.$H$100
$B$12 | $'3.1'.$G$28
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/MS-3.2.1a.pdf | $'3.2'.$J$9
$'3.2'.$J$9 | $'3.2'.$C$10
http://ganga.web.cern.ch/ganga/work/index.html | $'3.2'.$J$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/GangaStatus.txt | $'3.2'.$C$40
$'3.2'.$B$12 | $'3.2'.$G$48
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/GangaDeliverableChanges.txt | $'3.2'.$J$27
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/GangaDeliverableChanges.txt | $'3.2'.$J$36
$AttributeMap.$M$20 | $'3.2'.$H$10
$AttributeMap.$N$20 | $'3.2'.$H$20
$AttributeMap.$O$20 | $'3.2'.$H$30
$AttributeMap.$P$20 | $'3.2'.$H$40
$AttributeMap.$M$21 | $'3.2'.$H$50
$AttributeMap.$N$21 | $'3.2'.$H$60
$AttributeMap.$O$21 | $'3.2'.$H$70
$AttributeMap.$P$21 | $'3.2'.$H$80
$AttributeMap.$M$22 | $'3.2'.$H$90
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Ganga3.2.4.doc | $'3.2'.$J$38
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/Ganga3.2.2.doc | $'3.2'.$J$13
$J$14 | $'3.2'.$C$20
$J$49 | $'3.2'.$C$50
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/LHCb_3.3.2.txt | $'3.3'.$C$20
$AttributeMap.$N$25 | $'3.3'.$Q$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/LHCb3.3.2.doc | $'3.3'.$J$14
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/MS-3.3.1.doc | $'3.3'.$C$10
$AttributeMap.$M$25 | $'3.3'.$H$10
$AttributeMap.$N$25 | $'3.3'.$H$20
$AttributeMap.$O$25 | $'3.3'.$H$30
$AttributeMap.$P$25 | $'3.3'.$H$40
$AttributeMap.$M$26 | $'3.3'.$H$50
$AttributeMap.$N$26 | $'3.3'.$H$60
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/CMS3.4.2.doc | $'3.4'.$J$13
http://www.gridpp.ac.uk/gridpp6/gridpp6_cms.ppt | $'3.4'.$J$18
http://www.gridpp.ac.uk/gridpp6/gridpp6_cms.ppt | $'3.4'.$J$9
http://www.gridpp.ac.uk/gridpp6/gridpp6_cms.ppt | $'3.4'.$J$30
http://www.brunel.ac.uk/~eestprh/GRIDPP/task3_4_3.htm | $'3.4'.$C$30
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'3.4'.$C$10
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'3.4'.$J$10
$AttributeMap.$M$30 | $'3.4'.$H$10
$AttributeMap.$N$30 | $'3.4'.$H$20
$AttributeMap.$O$30 | $'3.4'.$H$30
$AttributeMap.$P$30 | $'3.4'.$H$40
$AttributeMap.$M$31 | $'3.4'.$H$50
$AttributeMap.$N$31 | $'3.4'.$H$60
$AttributeMap.$O$31 | $'3.4'.$H$70
$AttributeMap.$P$31 | $'3.4'.$H$80
$AttributeMap.$M$32 | $'3.4'.$H$90
$AttributeMap.$N$32 | $'3.4'.$H$100
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/CMS_3.4.2.txt | $'3.4'.$J$19
$'3.5'.$J$67 | $'3.5'.$C$70
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/BaBar3.5.7.doc | $'3.5'.$J$62
http://www.gridpp.ac.uk/gridpp6/gridpp6_babar.ppt | $'3.5'.$C$10
http://www.gridpp.ac.uk/gridpp6/gridpp6_babar.ppt | $'3.5'.$C$20
$AttributeMap.$N$35 | $'3.5'.$H$20
$AttributeMap.$O$35 | $'3.5'.$H$30
$AttributeMap.$P$35 | $'3.5'.$H$40
$AttributeMap.$M$36 | $'3.5'.$H$50
$AttributeMap.$N$36 | $'3.5'.$H$60
$AttributeMap.$O$36 | $'3.5'.$H$70
$AttributeMap.$M$35 | $'3.5'.$H$10
$'3.5'.$B$2 | $'3.5'.$G$18
$'3.5'.$B$12 | $'3.5'.$G$28
$'3.5'.$B$2 | $'3.5'.$G$38
$'3.5'.$B$12 | $'3.5'.$G$39
$'3.5'.$B$32 | $'3.5'.$G$48
$'3.5'.$B$32 | $'3.5'.$G$58
$'3.5'.$B$42 | $'3.5'.$G$59
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/CDF3.6.5.doc | $'3.6'.$J$43
http://www-d0.fnal.gov/computing/grid/SAMGridManual.htm | $'3.6'.$C$60
http://samadams.fnal.gov:8080/prototype/ | $'3.6'.$J$60
http://www.gridpp.ac.uk/gridpp6/gridpp6_samcdf.ppt | $'3.6'.$C$40
$J$47 | $'3.6'.$C$50
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/Status3.6.7.txt | $'3.6'.$C$70
$J$17 | $'3.6'.$C$20
http://www.gridpp.ac.uk/news/1037957446.780947.wlg | $'3.6'.$C$30
http://www.gridpp.ac.uk/news/1037957446.780947.wlg | $'3.6'.$J$70
$AttributeMap.$M$40 | $'3.6'.$H$10
$AttributeMap.$N$40 | $'3.6'.$H$20
$AttributeMap.$O$40 | $'3.6'.$H$30
$AttributeMap.$P$40 | $'3.6'.$H$40
$AttributeMap.$M$41 | $'3.6'.$H$50
$AttributeMap.$N$41 | $'3.6'.$H$60
$AttributeMap.$O$41 | $'3.6'.$H$70
$AttributeMap.$P$41 | $'3.6'.$H$80
$AttributeMap.$M$42 | $'3.6'.$H$90
$AttributeMap.$N$42 | $'3.6'.$H$100
$AttributeMap.$O$42 | $'3.6'.$H$110
$AttributeMap.$P$42 | $'3.6'.$H$120
http://www-d0.fnal.gov/computing/grid/TechnologyReview.doc | $'3.6'.$C$10
$B$2 | $'3.6'.$G$58
$B$12 | $'3.6'.$G$38
$J$100 | $'3.6'.$C$100
$AttributeMap.$P$45 | $'3.7'.$S$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/UKQCD3.7.4.doc | $'3.7'.$J$33
http://www.gridpp.ac.uk/eb/030318/UKQCD/EBreportQCDgrid_mar03.doc | $'3.7'.$C$40
http://www.w3.org/XML/Schema | $'3.7'.$C$10
http://www.gridpp.ac.uk/gridpp6/gridpp6_qcd.ppt | $'3.7'.$C$20
http://www.gridpp.ac.uk/gridpp6/gridpp6_qcd.ppt | $'3.7'.$C$30
$AttributeMap.$M$45 | $'3.7'.$H$10
$AttributeMap.$N$45 | $'3.7'.$H$20
$AttributeMap.$O$45 | $'3.7'.$H$30
$AttributeMap.$P$45 | $'3.7'.$H$40
$AttributeMap.$M$46 | $'3.7'.$H$50
$'3.7'.$B$42 | $'3.7'.$G$58
$'3.7'.$B$12 | $'3.7'.$G$28
$AttributeMap.$N$46 | $'3.7'.$H$60
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/UKQCD3.7.5.doc | $'3.7'.$J$43
$AttributeMap.$M$50 | $'3.8'.$H$10
$AttributeMap.$N$50 | $'3.8'.$H$20
$AttributeMap.$O$50 | $'3.8'.$H$30
http://www.gridpp.ac.uk/gridpp4/ah_experiences.ppt | $'3.8'.$C$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/ChangeForms/INF4.1.5.doc | $'4.1'.$J$43
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.1'.$C$30
$AttributeMap.$R$15 | $'4.1'.$H$10
$AttributeMap.$S$15 | $'4.1'.$H$20
$AttributeMap.$T$15 | $'4.1'.$H$30
$AttributeMap.$U$15 | $'4.1'.$H$40
$AttributeMap.$R$16 | $'4.1'.$H$50
$AttributeMap.$S$16 | $'4.1'.$H$60
$AttributeMap.$T$16 | $'4.1'.$H$70
$AttributeMap.$U$16 | $'4.1'.$H$80
$AttributeMap.$R$17 | $'4.1'.$H$90
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/BaBar_MOU.doc | $'4.1'.$C$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/TierA4.1.4.txt | $'4.1'.$C$40
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.2'.$C$10
$AttributeMap.$R$20 | $'4.2'.$H$10
$AttributeMap.$S$20 | $'4.2'.$H$20
$AttributeMap.$T$20 | $'4.2'.$H$30
$AttributeMap.$U$20 | $'4.2'.$H$40
$AttributeMap.$R$21 | $'4.2'.$H$50
$AttributeMap.$S$21 | $'4.2'.$H$60
$AttributeMap.$T$21 | $'4.2'.$H$70
$J$13 | $'4.2'.$C$20
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/cpu_usage_groupname-may03.pie | $'4.2'.$J$17
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/cpu_usage_groupname-weekly-ymay02.bar | $'4.2'.$J$18
$AttributeMap.$R$25 | $'4.3'.$H$10
$AttributeMap.$S$25 | $'4.3'.$H$20
$AttributeMap.$T$25 | $'4.3'.$H$30
$AttributeMap.$U$25 | $'4.3'.$H$40
$AttributeMap.$R$26 | $'4.3'.$H$50
$B$2 | $'4.3'.$G$18
$B$2 | $'4.3'.$G$38
$B$12 | $'4.3'.$G$39
$B$22 | $'4.3'.$G$48
$AttributeMap.$R$30 | $'4.4'.$H$10
$AttributeMap.$S$30 | $'4.4'.$H$20
$AttributeMap.$T$30 | $'4.4'.$H$30
$AttributeMap.$U$30 | $'4.4'.$H$40
$AttributeMap.$R$31 | $'4.4'.$H$50
$AttributeMap.$S$31 | $'4.4'.$H$60
http://ccwp7.in2p3.fr/mapcenter/datagrid-d/graph_Europe.html | $'4.4'.$C$30
$AttributeMap.$R$35 | $'4.5'.$H$10
$AttributeMap.$S$35 | $'4.5'.$H$20
$AttributeMap.$T$35 | $'4.5'.$H$30
$AttributeMap.$U$35 | $'4.5'.$H$40
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/RolloutStatus.txt | $'4.5'.$C$20
http://www.gridpp.ac.uk/docs/oversight/TB-02-UKrollout.doc | $'4.5'.$C$10
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/lhcb-prod-status.htm | $'4.6'.$C$20
http://www.gridpp.ac.uk/docs/oversight/PMB-11-Tier1AStatus.doc | $'4.6'.$C$10
$AttributeMap.$R$40 | $'4.6'.$H$10
$AttributeMap.$S$40 | $'4.6'.$H$20
$AttributeMap.$T$40 | $'4.6'.$H$30
$AttributeMap.$W$15 | $'5.1'.$H$10
$AttributeMap.$X$15 | $'5.1'.$H$20
$AttributeMap.$Y$15 | $'5.1'.$H$30
$AttributeMap.$W$20 | $'5.2'.$H$10
$AttributeMap.$X$20 | $'5.2'.$H$20
$AttributeMap.$Y$20 | $'5.2'.$H$30
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/OpenSourceMetrics.doc | $'5.2'.$D$8
http://www.hep.ph.ic.ac.uk/CMS/IC_GridPP/ProjectMapLinks/OpenSourceMetrics.doc | $'5.2'.$D$18
$AttributeMap.$W$25 | $'5.3'.$H$10
$AttributeMap.$X$25 | $'5.3'.$H$20
$AttributeMap.$Y$25 | $'5.3'.$H$30
$AttributeMap.$W$30 | $'5.4'.$H$10
$AttributeMap.$X$30 | $'5.4'.$H$20
$AttributeMap.$Y$30 | $'5.4'.$H$30
$AttributeMap.$Z$30 | $'5.4'.$H$40
$AttributeMap.$W$31 | $'5.4'.$H$50
$AttributeMap.$AB$16 | $'6.1'.$H$50
$AttributeMap.$AB$15 | $'6.1'.$H$10
$AttributeMap.$AC$15 | $'6.1'.$H$20
$AttributeMap.$AD$15 | $'6.1'.$H$30
$AttributeMap.$AE$15 | $'6.1'.$H$40
$'6.1.1'.$A$1 | $'6.1'.$C$10
$'6.1.2'.$A$1 | $'6.1'.$C$20
$'6.1.3'.$A$1 | $'6.1'.$C$30
$'6.1.4'.$A$1 | $'6.1'.$C$40
$'6.1.5'.$A$1 | $'6.1'.$C$50
$AttributeMap.$AB$20 | $'6.2'.$H$10
$AttributeMap.$AC$20 | $'6.2'.$H$20
$AttributeMap.$AD$20 | $'6.2'.$H$30
$AttributeMap.$AE$25 | $'6.3'.$H$40
$AttributeMap.$AB$25 | $'6.3'.$H$10
$AttributeMap.$AC$25 | $'6.3'.$H$20
$AttributeMap.$AD$25 | $'6.3'.$H$30
$AttributeMap.$AJ$15 | $'7.1'.$H$40
$AttributeMap.$AG$15 | $'7.1'.$H$10
$AttributeMap.$AH$15 | $'7.1'.$H$20
$AttributeMap.$AI$15 | $'7.1'.$H$30
$AttributeMap.$AG$20 | $'7.2'.$H$10
$AttributeMap.$AH$20 | $'7.2'.$H$20
$AttributeMap.$AI$20 | $'7.2'.$H$30
http://www.gridpp.ac.uk/eb/021000/ATLAS/index.html | $'7.2'.$C$20
$J$10 | $'7.2'.$C$10
$AttributeMap.$AJ$25 | $'7.3'.$H$40
$AttributeMap.$AG$25 | $'7.3'.$H$10
$AttributeMap.$AH$25 | $'7.3'.$H$20
$AttributeMap.$AI$25 | $'7.3'.$H$30

## NotePad
Changes
| 3.1.9 again | q10
| 3.3.3 | q10 | now complete
| 3.1.4 | q11
| 3.1.6 | q11
| 3.1.9 | q11
| 3.6.9 | q11
| 3.6.11 | q11
| 3.7.5 | q11
| 3.7.6 | q11

## SL_Summary
2003-10-01
Dissemination Metrics Summary
Presentation of GridPP
6.1.1 | 37 | Number of GridPP Presentations
6.1.2 | 7 | Number of Technical Workshops
6.1.3 | 12 | Number of GridPP Demonstrations
6.1.4 | 17 | Number of GridPP Posters
6.1.5 | 84 | Number of GridPP Publications
Participation in Related Areas
6.2.1 | 163 | Number of Attendances at Related Events
6.2.2 | 17 | Number of Interactions with e-Science centres
6.2.3 | 27 | GridPP Membership of Related Projects
Engagement of UK Groups
6.3.1 | 3 | Number of External Groups who use GridPP Middleware
6.3.2 | 3 | Number of External Groups who use GridPP Hardware
6.3.3 | 4 | Number of Press Articles about GridPP
6.3.4 | 171 | GridPP Website Hit Index
5.1.1 | 70 | Number of GridPP members attending GGF meetings
5.1.2 | 4 | Number of GridPP members in charge of formal GGF Working Groups
5.3.1 | 1 | Number of GridPP members of InterGrid Technical Board (HIJTB)
5.3.2 | 3 | Number of GridPP members of InterGrid Collaboration Board (HIJCB)
5.4.1 | 4 | Number of GridPP members of e-Science Centre Technical Boards.
5.4.2 | 2 | Number of GridPP members of e-Science Centre Executive Boards.
5.4.3 | 2 | Number of GridPP members belonging to JISC Technical Boards
5.4.4 | 0 | Number of GridPP members belonging to JISC Executive Boards
Note on A1: Update from SL's dissemination spreadshet as follows: Cut and paste_value from summary sheet in dissemination.xls over the top of this one. Then replace all the individual sheets at the end of this workbook (I think you have to cut and paste over each one)

## 1.1
1.1.1 | UK funding helps seed creation of LCG |  |  |  | DUE | 2001-12-31
Description | Commitment of substantial UK funding helps to seed the creation of a large-scale international
Grid project at CERN.
Metric | Creation of project
Risk and/or | Other countries will not provide funding.
Dependency
Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
1.1.2 | Cross membership of GridPP and LCG |  |  |  | DUE | 2002-03-31
Description | To ensure the close connection of GridPP and LCG cross-membership of the projects is required
at the highest levels.
Metric | Establishment of cross-members on management bodies
Risk and/or
Dependency
Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
1.1.3 | LCG Plans |  |  |  | DUE | 2002-07-01
Description | LCG needs to develop a credible plan. UK should influence this if necessary.
Metric | Planning information publicly available.
Risk and/or
Dependency
Status | Complete | Status Date | 2002-06-21 | Modified Due Date |  | J | See also | http://lcg.web.cern.ch/LCG/PEB/Planning/default.htm
1.1.4 | LHC experiments embrace LCG developments |  |  |  | DUE | 2004-12-31
Description | The ultimate metric for success is that the LHC experiments adopt substantial parts of the LCG
product and that this is totally compatible with the developments in the UK.
Metric | ATLAS, CMS, LHCb, (ALICE) use LCG product on UK grid.
Risk and/or
Dependency
Status | In Progress | Status Date | 2002-09-05 | Modified Due Date |  | J
1.1.5 | Missing Effort |  |  |  | DUE | on going
Description | Number of posts that are not presently filled
Metric | Number of posts that are not presently filled
Current Total |  | 0
Current Threshold |  | -4
Status | Not started | Status Date | 2002-10-01 |  |  | J

## 1.2
1.2
1 | 1.2.1 | Software Process Infrastructure in place |  |  |  | DUE | 2002-07-07
| Description | The LCG project requires an agreed software process and appropriate support tools, including
repository, configuration and release management tools. The components of the infrastructure
are to be defined by an RTAG created for this purpose.
| Metric | Agreed services are up and running by due date
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J
2 | 1.2.2 | Prototype Hybrid Datastore completed |  |  |  | DUE | 2002-11-30
| Description | First version of hybrid eventstore released. Limited functionality only required and expected to
be used by experts only.
| Metric | Functionality, interfaces and documentation delivered according to requirements set at June
persistency workshop.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J
3 | 1.2.3 | LCG-1 Applications Environment Defined |  |  |  | DUE | 2003-03-01
| Description | Each LHC experiment has a distinct application environment and other environment components | [5 empty] | This is roughly equiverlent to 1.1.4.3 in the LCG planning
|  | have been produced by IT. A common set must be selected to serve as the base for development | [5 empty] | (which post dated this ProjectMap definition).
|  | and for testing on the LCG prototypes | [5 empty] | The SEAL project incoporates our milestone. Thus,
| Metric | Report from PEB by due date | [5 empty] | we take the release of SEAL V1 as the completion of
our milestone but we will define future milestones to
| Risk and/or | [6 empty] | include the rest of the SEAL project
Dependency
| Status | Complete | Status Date | 2003-02-27 | Modified Due Date |  | J
4 | 1.2.4 | LCG-1 Applications Environment Software Available |  |  |  | DUE | 2003-07-31
| Description | Once the different components of the application environment have been defined, they must be
collected and made available centrally.
This is part of LCG deliverable M1.1
| Metric | software components identified in 1.2.3 available in software repository of 1.2.1
| Risk and/or |  |  |  |  | 1.2.1
| Dependency |  |  |  |  | 1.2.3
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | See this link also
5 | 1.2.5 | General Release Hybrid Event Store |  |  |  | DUE | 2003-07-01
| Description | A more functional and robust (but not yet complete) version of the persistency framework. | [5 empty] | Complete on June 30th. See P15 of the link to Torre's GridPP7 Talk.
|  | This will be a release offering basic hybrid persistency services, properly documented and | [5 empty] | For more details, see other GridPP7 talks.
packaged for general use by the experiments. This is LCG M1.2 deliverable.
| Metric | Release made by due date.
LHC experiments able to make use of it.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J
6 | 1.2.6 | Future Milestones |  |  |  | DUE | 2003-09-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | Email from TC on 3/Nov/03 has details. Yet to be implemented in ProjectMap

## 1.3
1.3
1 | 1.3.1 | Joint LCG/EDG cluster increased to 200 nodes |  |  |  | DUE | 2002-07-07
| Description | Contributed funding allows the acquisition of additional hardware components (CPU and disk
servers) to increase the size of the LCG/EDG cluster to 200 nodes.
| Metric | 200 Node installed.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | Note: Nodes installed with other funding. Proposal to re-deploy GridPP funding (see link).
2 | 1.3.2 | Joint LCG/EDG Production Testbed Completed |  |  |  | DUE | 2002-11-01
| Description | The EDG Grid middleware is installed and running on the LCG/EDG cluster of 1.3.1
| Metric | The EDG Grid middleware is installed and running on the LCG/EDG cluster of 1.3.1
| Risk and/or | Installation does not scale to 200 nodes.
| Dependency | [6 empty] | Risk was precient! Installation did not scale but the ATLAS/CMS
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | tests were performed so milestone was essentially done.
3 | 1.3.3 | LCG-1 Cluster increased to 400 nodes |  |  |  | DUE | 2003-05-01
| Description | As 1.3.1 for expansion to 400 nodes.
| Metric | 400 nodes installed
| Risk and/or | Scaling problems
| Dependency | SW stability
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | Email from TC on 12/Sep/03
4 | 1.3.4 | LCG-1 Production Cluster Operational |  |  |  | DUE | 2003-07-01
| Description | The middleware components of 1.4.1 installed and running on the LCG-1 cluster (1.3.3)
Aligned with LCG deliverable 1.2.4.2.3 (2.560)
| Metric | The middleware components of 1.4.1 installed and running on the LCG-1 cluster (1.3.3)
| Risk and/or | Depends on cluster |  |  |  | 1.3.3
| Dependency | Depends on middleware components |  |  |  | 1.2.1 |  | Email from TC on 12/Sep/03
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | Link To LCG Press release
5 | 1.3.5 | Cluster Automation Complete |  |  |  | DUE | 2003-03-30
| Description | Automated tools for installation of LCG-1 cluster available.
Precise set of tools depends on EDG and other developments (c.f. 1.3.1), but tools should adhere
to principles of the EDG WP4 architecture and design document.
| Metric | As above
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J
6 | 1.3.6 | Future Milestones |  |  |  | DUE | 2003-09-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | New milestones in email from TC 3/Nov/03. Not yet in ProjectMap

## 1.4
1.4
1 | 1.4.1 | Middleware Components Defined |  |  |  | DUE | 2002-12-01 | Corresponds to the subsequently definded LCG deliverable
| Description | As for applications environments, there are various competing sources of the different | [5 empty] | 1.3.2.8
Grid middleware components. A single set must be defined for LCG use.
| Metric | Single set of components defined.
| Risk and/or | It is hoped that GLUE will produce agreement on middleware
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J
2 | 1.4.2 | Testing and Validation Process Defined |  |  |  | DUE | 2003-02-01
| Description | Testing and Validation Process Defined
| Metric | Definition established
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | CLICK HERE AND THEN LOOK AT WG4 DOCUMENT Sec 2.3
3 | 1.4.3 | Middleware Components Assembled, Tested and Available |  |  |  | DUE | 2003-04-01
| Description | The middleware components identified in 1.3.1 are available in an agreed location for LCG, e.g.
the repository identified in 1.1.1
| Metric | Middleware Components Assembled, Tested and Available
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J
4 | 1.4.4 | Full Test Suite Completed |  |  |  | DUE | 2003-06-01
| Description | Full Test Suite Completed
| Metric | Full Test Suite Completed
Risk and/or
Dependency
| Status | In Progress | Status Date | 2002-09-09 | Modified Due Date |  | J | Tony Cass checking staus (email 3/Nov/03)
5 | 1.4.5 | Future Milestones |  |  |  | DUE | 2003-09-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
| Dependency | [6 empty] | See new milestones below
| Status | Complete | Status Date | 2003-04-22 | Modified Due Date |  | J
6 | 1.4.6 | Draft definition of Middleware to be used for LCG-3 service |  |  |  | DUE | 2003-12-10
| Description | An initial definition of the middleware to be used for LCG-3 is available following discussions with
the participating sites.
This milestone corresponds to milestone 1.3.5.3 of the LCG plan.
Metric
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
7 | 1.4.7 | Final definition of Middleware to be used for LCG-3 service |  |  |  | DUE | 2004-03-01
| Description | Th middleware to be used for the LCG-3 service has been agreed with all partners and the
definition has been published and agreed by SC2.
This milestone corresponds to milestone 1.3.5.5 of the LCG plan.
Metric
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
8 | 1.4.8 | Agreed LCG-3 middleware delivered for deployment |  |  |  | DUE | 2004-06-01
| Description | The middleware of 1.4.7 is available in an agreed location ready for deployment on the
LCG-3 service.
This milestone corresponds to milestone 1.3.5.6 of the LCG plan.
Metric
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 1.4.9 | Updated PASTA Technology Review Complete |  |  |  | DUE | 2004-11-01
| Description | The 2004 version of the PASTA reports has been published.
This milestone corresponds to milestone 1.3.4.4 of the LCG plan.
Metric
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 1.5
1.5
1 | 1.5.1 | Complete Specification of LCG-1 |  |  |  | DUE | 2002-11-24
| Description | Agreement is reached on the level of resources required for LCG-1 and how these are to be
distributed across at least 5 sites in 3 continents.
| Metric | Specification available
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | CLICK HERE AND SEE WG2 DOCUMENT
2 | 1.5.2 | Institutes Fabric Ready to Install |  |  |  | DUE | 2003-05-15 | Click here for changeform
| Description | Acquisition and installation of agreed hardware. | [5 empty] | Date changed to match subsequently
defined LCG milestone
| Metric | The institutes identified in 1.5.1 have completed the acquisition and installation of the agreed
hardware.
Risk and/or
Dependency
| Status | Complete | Status Date | 2003-04-16 | Modified Due Date |  | J | (See LCG Resource slide in the link)
3 | 1.5.3 | Certification Started |  |  |  | DUE | 2003-05-30 | Click here for changeform
| Description | [6 empty] | Date changed to match subsequently
|  | Installation of agreed middleware (1.5.1) on hardware of 1.5.2. | [5 empty] | defined LCG milestone ~1.4.1.4 (4.356)
| Metric | Certification Started
| Risk and/or |  |  |  |  | 1.4.1
| Dependency |  |  |  |  | 1.5.2
| Status | Complete | Status Date | 2003-04-16 | Modified Due Date |  | J | (For LCG-1 status, click dots on map on LCG home page)
4 | 1.5.4 | Certification and LCG-1 Build and Delivery complete |  |  |  | DUE | 2003-06-30 | Click here for changeform
| Description | [6 empty] | Date changed to match subsequently
|  | All the agreed hardware and software is up and running at each individual LCG-1 site. | [5 empty] | defined LCG milestone ~1.4.1.6 (4.956)
| Metric | Certification and LCG-1 Build and Delivery complete
Risk and/or
Dependency
| Status | Complete | Status Date | 2003-04-16 | Modified Due Date |  | J | See Link for 1.5.3 completion
5 | 1.5.5 | Commissioning Started |  |  |  | DUE | 2003-06-30 | Click here for changeform
| Description | This is the start of the process to bring the different sites together to form a coherent LCG-1. | [5 empty] | Date changed to match subsequently
defined LCG milestone ~1.4.1.6 (4.956)
| Metric | Commissioning Started
Risk and/or
Dependency
| Status | Complete | Status Date | 2003-04-16 | Modified Due Date |  | J | See email from TC on 3/Nov/03
6 | 1.5.6 | Commissioning Completed |  |  |  | DUE | 2003-11-24
| Description | [6 empty] | Click here for changeform
Date changed to match subsequently
defined LCG milestone 1.4.1.7 (4.358)
| Metric | The application software of 1.2.4 runs successfully on the LCG-1 service.
| Risk and/or |  |  |  |  | 1.2.4
Dependency
| Status | Not started | Status Date | 2003-04-16 | Modified Due Date |  | J
7 | 1.5.7 | Future Milestones |  |  |  | DUE | 2003-09-01
| Description | Milestones for the remainder of the LCG project are yet to be defined
| Metric | Milestones defined
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-09 | Modified Due Date |  | J | See new milestones below
8 | 1.5.8 | LCG-3 Service Defined |  |  |  | DUE | 2004-02-27
| Description | The LCG-3 service is defined in terms of sites involved, hardware available and performance
criteria.
This milestone corresponds to milestone 1.4.4 of the LCG plan.
Metric
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 1.5.9 | LCG-3 Pilot Available |  |  |  | DUE | 2004-07-01
| Description | An initial LCG-3 service is available in accordance with the plans of 1.5.8.
This milestone corresponds to milestone 1.4.12.1 of the LCG plan.
Metric
| Risk and/or |  |  |  |  | 1.4.8
| Dependency |  |  |  |  | 1.5.8
| Status | Not started | Status Date |  | Modified Due Date |  | J
10 | 1.5.10 | LCG-3 Fulfills Performance Goals |  |  |  | DUE | 2004-12-17
| Description | The LCG-3 service meets the performance goals set in the initial service definition (1.5.8).
This milestone corresponds to milestone 1.4.13 of the LCG plan.
Metric
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 2.1
2.1
1 | 2.1.1 | Deliver WP1 Effort |  |  | DUE | on going
| Description | Deliver WP1 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 215%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.1.2 | Install and Test |  |  | DUE | on going
| Description | Install and test EDG WP1 software
UK responsibility as part of an EDG-wide effort
| Metric | Latest WP1 software working in the UK
(Use 1 for 'yes' and 0 for 'no' in Current Total field below)
| Current Total |  | 1
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2002-06-05 |  | J
3 | 2.1.3 | Technology Assessment |  |  | DUE | 2001-03-31
| Description | D1.1 Report of current technology
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.1.4 | Requirements & Architecture |  |  | DUE | 2001-06-30
| Description | D1.2 Detailed report on requirements, architectural design, and evaluation criteria
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.1.5 | First Project Release |  |  | DUE | 2001-09-30
| Description | D1.3 Components and documentation for the first Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
6 | 2.1.6 | Co-allocation & Parallel Jobs |  |  | DUE | 2002-06-30
| Description | D1.4 Co-allocation and parallel job partitioning architecture
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.1.7 | Second Project release |  |  | DUE | 2003-01-15
| Description | D1.5 Components and documentation for the second Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2003-01-06 |  | J
8 | 2.1.8 | Final Project Release |  |  | DUE | 2003-09-30
| Description | D1.6 Components and documentation for the final Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
9 | 2.1.9 | Evaluation |  |  | DUE | 2003-12-31
| Description | D1.7 Final evaluation report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.2
2.2
1 | 2.2.1 | Deliver WP2 Effort |  |  | DUE | on going
| Description | Deliver WP2 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 144.2%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.2.2 | Technology Assessment |  |  | DUE | 2001-04-30
| Description | D2.1 Report of current technology
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.2.3 | Requirements & Architecture |  |  | DUE | 2001-06-30
| Description | D2.2 Detailed report on requirements, architectural design, and evaluation criteria
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.2.4 | First Project Release |  |  | DUE | 2001-09-30
| Description | D2.3 Components and documentation for the first Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.2.5 | Second Project release |  |  | DUE | 2003-01-15
| Description | D2.4 Components and documentation for the second Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2003-01-06 |  | J
6 | 2.2.6 | Final Project Release |  |  | DUE | 2003-09-30
| Description | D2.5 Components and documentation for the final Project Release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.2.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D2.6 Final evaluation report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.3
2.3
1 | 2.3.1 | Deliver WP3 Effort |  |  | DUE | on going
| Description | Deliver WP3 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 146.8%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.3.2 | Technology review |  |  | DUE | 2001-12-12
| Description | D3.1 Current Technology Evaluation
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.3.3 | Architecture |  |  | DUE | 2001-09-30
| Description | D3.2 Architecture Design
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.3.4 | First Prototype |  |  | DUE | 2001-09-30
| Description | D3.3 First Prototype
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.3.5 | Second Prototype |  |  | DUE | 2003-01-15
| Description | D3.4 Second Prototype
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Has significant input from core eScience project working with EDG
Dependency
| Status | Complete | Status Date | 2003-01-06 |  | J
6 | 2.3.6 | Final Prototype |  |  | DUE | 2003-09-30
| Description | D3.5 Final Prototype
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Has significant input from core eScience project working with EDG
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.3.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D3.6 Final Evaluation Report
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.4
2.4
1 | 2.4.1 | Deliver WP4 Effort |  |  | DUE | on going
| Description | Deliver WP4 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 256.3%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.4.2 | Technology review |  |  | DUE | 2001-04-30
| Description | D4.1 Report of current technology
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.4.3 | Architecture |  |  | DUE | 2001-06-30
| Description | D4.2 Architectural design report and evaluation criteria
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.4.4 | First project release |  |  | DUE | 2001-09-30
| Description | D4.3 Components and documentation for the first project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.4.5 | Second project release |  |  | DUE | 2003-01-15
| Description | D4.4 Components and documentation for the second project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | EDG may not stay with LCFG in the longer term
Dependency
| Status | Complete | Status Date | 2003-01-06 |  | J
6 | 2.4.6 | Final project release |  |  | DUE | 2003-09-30
| Description | D4.5 Components and documentation for the final project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | EDG may not stay with LCFG in the longer term
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.4.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D4.6 Final evaluation report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
| Dependency | EDG may not stay with LCFG in the longer term
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.5
2.5
1 | 2.5.1 | Deliver WP5 Effort |  |  | DUE | on going
| Description | Deliver WP5 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 135.9%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.5.2 | Technology review |  |  | DUE | 2001-03-31
| Description | D5.1 Report of current technology
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.5.3 | Architecture |  |  | DUE | 2001-06-30
| Description | D5.2 Detailed architectural design report and evaluation criteria
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.5.4 | First Project release |  |  | DUE | 2001-09-30
| Description | D5.3 Components and documentation for the first project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.5.5 | Second Project release |  |  | DUE | 2003-01-15
| Description | D5.4 Components and documentation for the second project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2003-01-06 |  | J
6 | 2.5.6 | Final Project release |  |  | DUE | 2003-09-30
| Description | D5.5 Components and documentation for the third project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.5.7 | Evaluation |  |  | DUE | 2003-12-31
| Description | D5.6 Final evaluation report
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful delivery of project releases
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.6
2.6
1 | 2.6.1 | Deliver WP6 Effort |  |  | DUE | on going
| Description | Deliver WP6 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 149.2%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.6.2 | Integration & Operation |  |  | DUE | 2001-04-30
| Description | D6.1 Testbed software integration process, operational policies and procedures report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.6.3 | Policies, evaluation and procedures |  |  | DUE | 2001-06-30
| Description | D6.2 Project release policy, definitions, evaluation targets and procedures
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.6.4 | First project release |  |  | DUE | 2001-09-30
| Description | D6.3 First project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on first project release deliverables from middleware workpackages
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.6.5 | First project release evaluation |  |  | DUE | 2001-12-31
| Description | D6.4 Evaluation of testbed operation
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful deployment of first project release
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
6 | 2.6.6 | Second project release |  |  | DUE | 2003-01-15
| Description | D6.5 Second project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on second project release deliverables from middleware workpackages
Dependency
| Status | Complete | Status Date | 2003-01-06 |  | J
7 | 2.6.7 | Second project release evaluation |  |  | DUE | 2003-06-01
| Description | D6.6 Evaluation of testbed operation
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful deployment of second project release
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
8 | 2.6.8 | Final project release |  |  | DUE | 2003-09-30
| Description | D6.7 Final project release
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on final project release deliverables from middleware workpackages
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
9 | 2.6.9 | Final project release evaluation |  |  | DUE | 2003-12-31
| Description | D6.8 Final evaluation of testbed operation
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Depends on successful deployment of second project release
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.7
2.7
1 | 2.7.1 | Deliver WP7 Effort |  |  | DUE | on going
| Description | Deliver WP7 effort as contracted
Primarily a UK responsibility
| Metric | Cumulative Effort Delivered
| Current Total |  | 186.7%
| Current Threshold |  | 90%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 2.7.2 | Network infrastructure report |  |  | DUE | 2001-09-30
| Description | D7.1 Report on network infrastructure for Testbed 1
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
3 | 2.7.3 | Deploy monitoring |  |  | DUE | 2001-12-31
| Description | D7.2 Demonstration and deployment of monitoring tools
Primarily done in the UK
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
4 | 2.7.4 | Infrastructure & services |  |  | DUE | 2002-06-30
| Description | D7.3 Intermediate report on network infrastructure and services
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
5 | 2.7.5 | Final report |  |  | DUE | 2003-12-31
| Description | D7.4 Final Report on network infrastructure and services
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not Started | Status Date | 2002-06-05 |  | J
6 | 2.7.6 | Interim security report |  |  | DUE | 2002-03-31
| Description | D7.5 Security Report on first project release
Primarily a UK responsibility
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J
7 | 2.7.7 | Security Design |  |  | DUE | 2003-01-31
| Description | D7.6 Security Design report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | Has input from core eScience project working with EDG
Dependency
| Status | Complete | Status Date | 2003-03-07 |  | J
8 | 2.7.8 | Final Security report |  |  | DUE | 2003-12-31
| Description | D7.7 Final security report
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not started | Status Date | 2002-06-05 |  | J

## 2.8
2.8
1 | 2.8.1 | Deliver WP8 Effort |  |  | DUE | on going
| Description | Appoint four FTE to work on WP8 in addition to the EU funded position
Primarily a UK responsibility
| Metric | Number of FTE employed
| Current Total |  | 4
| Current Threshold |  | 4
| Status | In Progress | Status Date | 2003-05-10 |  | J
2 | 2.8.2 | Grid Services Requirements |  |  | DUE | 2001-06-30
| Description | D8.1 DataGrid User Requirements and Specifications for the DataGrid Project
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2001-12-14 |  | J
3 | 2.8.3 | First Testbed Evaluation |  |  | DUE | 2001-12-31
| Description | D8.2 Testbed-1 Assessment by HEP Applications
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2002-02-07 |  | J
4 | 2.8.4 | Second Testbed Evaluation |  |  | DUE | 2002-12-31
| Description | D8.3 Assessment of the Testbed by HEP Applications during Project Year 2
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2003-04-02 |  | J
5 | 2.8.5 | Final Testbed Evaluation |  |  | DUE | 2003-12-31
| Description | D8.4 Final application report on the testbed
Not primarily a UK responsibility but UK will contribute
| Metric | Delivered on time and formally accepted by EDG
| Risk and/or | None
Dependency
| Status | Not Started | Status Date | 2003-05-05 |  | J
Under Review

## 3.1
3.1
1 | 3.1.1 | Technology, Archtecture and requirements documents |  |  |  | DUE | 2002-09-30
| Description | Review of existing Monte Carlo production mechanisms in ATLAS and prototype distributed
production systems. Establish architecture and design details of first prototype
The Atlas/LHCb GANGA review document should be used as a guide and an input.
| Metric | Documents Produced
| Risk and/or | Atlas/LHCb GANGA review and requirements document
| Dependency | [6 empty] | There may be a revised document; should check
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J | http://www.gridpp.ac.uk/atlas/Projects/ATLASGridProjects.htm
2 | 3.1.2 | Installation Tool Prototype development |  |  |  | DUE | 2002-12-31
| Description | The CMT rpm generation will be tested and the pacman converter used to generate cache files,
and pacman used to do remote installation. Non-advertised installation via the sandbox and the SE
will be attempted and compared, inside and in addition to the DC1 context.
| Metric | Tool Produced | [5 empty] | This has been demonstated but not documented
|  | Not currently a GridPP responsibility but RHUL may become involved. | [5 empty] | The LCG adoption of SCRAM may cause this to be
| Risk and/or | Pacman convertor | [5 empty] | dropped at this point.
| Dependency | Rpm generation facility in CMT | [5 empty] | See 3.1.6 below
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J
3 | 3.1.3 | First prototype of Grid interface |  |  |  | DUE | 2002-12-31 |  | 3.1.3 | First prototype of Grid interface |  |  |  | DUE | 2002-12-31
| Description | A prototype production system using the software intended for DC1 will be | [5 empty] | Click here for changeform | Description | A prototype production system using the software intended for DC2 will be produced based on
|  | produced using EGD1 tools and a prototype GUI interface | [5 empty] | Old deliverable is here ---> |  | the GANGA prototype and GUI and the installation tool
Modified because of EDG delays
| Metric | Demonstration of prototype | [5 empty] | and realignment with LCG | Metric | Demonstration of prototype
| Risk and/or | Full chain available in Athena; GANGA prototype; Installation prototpe; |  |  |  | 3.1.2 |  |  | Risk and/or | Full chain available in Athena; GANGA prototype; Installation prototpe; |  |  |  | 3.1.2
| Dependency | Replication tools for bookkeeping files. | [6 empty] | Dependency | Replication tools for bookkeeping files.
| Status | Complete | Status Date | 2003-04-07 | Modified Due Date |  | J | Demo at CHEP'03 | Status | In Progress | Status Date | 2003-01-17 | Modified Due Date |  | J
4 | 3.1.4 | First release of integrated MC production system |  |  |  | DUE | 2003-12-31 |  | 3.1.4 | First release of integrated MC production system |  |  |  | DUE | 2003-06-30
| Description | First general release of Monte Carlo production system using LCG tools for DC2 | [5 empty] | Click here for changeform | Description | First general release of Monte Carlo production system with integrated installation tools for DC2
|  | The prototype - Monitoring of job production and file replication. | [5 empty] | Click here for changeform2 |  | The prototype - Monitoring of job production and file replication.
|  | - Templating or virtual data methods for configuration | [5 empty] | Old deliverable is here ---> |  | - Templating or virtual data methods for configuration
| Metric | Demonstration of prototype plus document | [5 empty] | Realigned with LCG | Metric | Demonstration of prototype plus document
EDG delays
| Risk and/or | GLUE and LCG progress slower than planned. | [6 empty] | Risk and/or | WP1 and WP3 monitoring facilities
| Dependency | [7 empty] | Dependency
| Status | In Progress | Status Date | 2003-04-07 | Modified Due Date |  | J |  | Status | In Progress | Status Date | 2003-01-17 | Modified Due Date |  | J
5 | 3.1.5 | Data Challenge 1 |  |  |  | DUE | 2003-03-31 |  | 3.1.5 | Revised Installation Tool design document |  |  |  | DUE | 2003-06-30
| Description | Several 10's of millions of events will be simulated, reconstructed and analaysed using the EDG | [5 empty] | Click here for changeform | Description | In the light of the report on the prototype and external developments, the architecture of the
|  | 1.x release and other grid tools for a significant portion of the work. A report will review the early | [5 empty] | Old deliverable is here ---> |  | Installation Tools will be revised.
|  | experiences with DC1 | [5 empty] | New deliverable is combination
| Metric | Several 10's of millions of events produced; EDG Grid tools tested | [5 empty] | of two DC1 deliverables in | Metric | Document
|  | Report. | [5 empty] | original submission.
| Risk and/or | [6 empty] | Click here for link. | Risk and/or | Prototype released on time |  |  |  | 3.1.3
| Dependency | [7 empty] | Dependency
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J |  | Status | Not started | Status Date |  | Modified Due Date |  | J
6 | 3.1.6 | Installation with publication |  |  |  | DUE | 2003-12-31
| Description | The integration of installation tool with MDS/Grid publication of environment setting, | [5 empty] | Click here for changeform
|  | Grid inquiry for environment detection. | [5 empty] | Click here for changeform2
Deliverable deleted because
| Metric | Demonstration of tool. | [5 empty] | LCG chose SCRAM
Deliverable then reinstated because
| Risk and/or | WP3 publication services. EDG installation procedures. | [5 empty] | ATLAS decided to continue with CMT
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
7 | 3.1.7 | Prototype of revised production tool |  |  |  | DUE | 2003-12-31
| Description | Implementation of the new architecture
| Metric | Report and demonstration
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
8 | 3.1.8 | Monte Carlo production with expanded functionality. |  |  |  | DUE | 2004-03-31
| Description | Integration with the corresponding GANGA development. Integration with the revised installation tool
| Metric | Document and demonstration
| Risk and/or | EDG testbed services. GANGA expanded functionality release.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 3.1.9 | Data Challenge 2 |  |  |  | DUE | 2004-09-30 | Click her for first changeform | 3.1.9 | Final Installation Tool Version |  |  |  | DUE | 2004-06-30
| Description | Seveal 100 million events will be generated, simulated, reconstructed and analysed using LCG2 | [5 empty] | Click her for second changeform | Description | Document describing Installation Tool and public demonstration.
|  | release (plus interface to US and NorduGrid). The experience with DC2 will be reviewed and future | [5 empty] | Click her for third changeform
|  | requirements determined | [5 empty] | Click her for fourth changeform
| Metric | Several 100 million events generated | [5 empty] | Original deliverable is here ---> | Metric | Document and demonstration
|  | Report | [5 empty] | New deliverable is combination
| Risk and/or | LCG releases needed on time | [5 empty] | of two DC1 deliverables in | Risk and/or
| Dependency | [6 empty] | original submission. | Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J | 2nd-4th changes re-align with LCG | Status | Not started | Status Date |  | Modified Due Date |  | J
Click here for link.
10 | 3.1.10 | Final Monte Carlo Production System Version |  |  |  | DUE | 2004-12-31
| Description | Document describing Monte Carlo production system and public demonstration.
| Metric | Document and demonstration
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 3.2
3.2
1 | 3.2.1 | Requirements, Architecture and Design Definition |  |  |  | DUE | 2002-11-15
| Description | Document that establishes LHCb requirements for Grid based analysis and MC production.
Document establishes architecture constraints and leads to detailed design definition
| Metric | Document
| Risk and/or | None
| Dependency | [6 empty] | This is link to Technology Review
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J | This architecture document will continue to evolve
2 | 3.2.2 | Prototype of Grid Interface |  |  |  | DUE | 2002-12-31
| Description | Command line interface allows simple Gaudi analysis and Monte Carlo production jobs to be | [5 empty] | Click here for changeform
|  | submitted to batch system. Job submission scripts automatically generated and some | [5 empty] | Command line interface is in fact
|  | error handling available. GANGA GUI to scripts. | [5 empty] | hidden from user but does exist.
| Metric | Demonstration of prototype for LHCb and ATLAS in the UK.
| Risk and/or | None
Dependency
| Status | Complete | Status Date | 2003-01-14 | Modified Due Date |  | J
3 | 3.2.3 | Webpage mock GUI for feedback |  |  |  | DUE
| Description | A simple web-page mock up of the GANGA GUI design to allow user feedback
This was merged with 3.2.2 above
| Metric | Creation of web-page mock GUI | [5 empty] | and is no longer and active milestone
(Click here for link for more info.)
Risk and/or
Dependency
| Status | In Progress | Status Date |  | Modified Due Date |  | J
4 | 3.2.4 | Remote Grid Mass-Storage Write Capability |  |  |  | DUE
| Description | Demonstration that the EDG RFIO from WP5 works in the LHCb context.
Remote RFIO was not released by EDG yet.
LHCb are re-assessing the need
| Metric | Demonstration of basic functionality. | [5 empty] | (Click here for link for more info.)
| Risk and/or | Depends on RFIO being produced by EDG WP5 | [5 empty] | Click here for changeform
| Dependency | [6 empty] | Deliverable Deleted due to the non
| Status | On Hold | Status Date |  | Modified Due Date |  | J | delivery of RFIO by EDG
5 | 3.2.5 | First GANGA Prototype |  |  |  | DUE | 2003-03-31
| Description | Emphasis is on interfacing the GANGA protoype descrubed by 3.2.2 to the EDG middleware
| Metric | LHCb demonstration of defined functionality.
| Risk and/or | EDG WP1 and WP3 tools |  |  |  | 3.2.2
| Dependency | [6 empty] | Included in CVS release in early April
| Status | Complete | Status Date | 2003-03-12 | Modified Due Date |  | J | To be demo'd at GridPP7?
6 | 3.2.6 | User-Controlled Site Configuration |  |  |  | DUE | 2003-09-30
| Description | Development of syntax of a generic site configuration file.
| Metric | Demonstration of test Gaudi/Athena jobs running on Grid using standard conditions
Risk and/or
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J | See Q11 Ganga report.
7 | 3.2.7 | Second GANGA Prototype |  |  |  | DUE | 2004-03-31
| Description | GANGA prototype that includes GUI access to middleware and Gaudi/Athena services.
Functionality includes translation of meta-data into physical files; replica service to optimise location
of data; query facility to estimate resources; monitoring facilities for submitted jobs.
| Metric | Demonstration of prototype with specified functionality.
| Risk and/or | EDG WP1 WP2 WP3 services.
Dependency
| Status | In Progress | Status Date |  | Modified Due Date |  | J
8 | 3.2.8 | Interface experiment Grid tools to GANGA |  |  |  | DUE | 2004-09-30
| Description | Incorporated MC production system into GANGA supporting user-query of environment. Interface to
experiment specific installation tools.
| Metric | Demonstration of prototype with specified functionality.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 3.2.9 | Final GANGA Version |  |  |  | DUE | 2004-12-31
| Description | Document and demonstration of final GANGA product.
| Metric | Document and demonstration in LHCb and ATLAS contexts.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 3.3
3.3
1 | 3.3.1 | PVSS Review & Development |  |  |  | DUE | 2002-09-30
| Description | Adapt & develop current PVSS system to the DATA Challenges & the developing MC production
system. Review the current PVSS based control system & compare with WP3 middleware
| Metric | Document and prototype
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J
2 | 3.3.2 | Monitoring Prototype |  |  |  | DUE | 2003-03-31 |  | 3.3.2 | Monitoring Prototype |  |  |  | DUE | 2002-12-31
| Description | Initial development of Grid based monitoring and control system | [5 empty] | Conclusion of 3.3.1 is not to use WP3 stuff. | Description | Introduce monitoring based on WP3 middleware (assumes WP3 APIs exist) & assess whether to
|  | Introduces the use of Work Flow Description Language | [5 empty] | Click her for changeform |  | maintain current PVSS system.
Old deliverable is here --->
| Metric | Demo in the UK | [5 empty] | Conclusion of 3.3.1 was not to | Metric | Document and prototype
use WP3 stuff so this redefined
| Risk and/or | [6 empty] | 3.3.2 | Risk and/or | API's to WP3 are produced in time.
| Dependency | [7 empty] | Dependency
| Status | Complete | Status Date | 2003-03-19 | Modified Due Date |  | J |  | Status | In Progress | Status Date | 2003-01-17 | Modified Due Date |  | J
3 | 3.3.3 | First prototype of New Experimental System |  |  |  | DUE | 2003-09-30 |  | 3.3.3 | First prototype of New Experimental System |  |  |  | DUE | 2003-06-30
| Description | Introduce monitoring of details of a running job. eg. run number. A first implementation of data | [6 empty] | Description | Introduce monitoring of details of a running job eg. run number. A first implementation of online
|  | quality monitoring | [5 empty] | Click her for changeform |  | histogram production.
Old deliverable is here --->
| Metric | Demonstration of new system | [5 empty] | Broadened scope somewhat as a | Metric | Demonstration of new system
better understanding achieved.
| Risk and/or | [6 empty] | Intoduces some delay | Risk and/or
| Dependency | [7 empty] | Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J |  | Status | Not started | Status Date |  | Modified Due Date |  | J
4 | 3.3.4 | Online Data Quality |  |  |  | DUE | 2003-12-31 | Title and description modified to agree with | 3.3.4 | Online Histogram Monitoring |  |  |  | DUE | 2003-12-31
| Description | Detailed online visualisation and data quality assurance | [5 empty] | the change in 3.3.3. See the above ChangeForm | Description | Sophisticated online histogram production & data quality assurance.
| Metric | Release of production version. | [6 empty] | Metric | Release of production version.
| Risk and/or | [7 empty] | Risk and/or
| Dependency | [7 empty] | Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J |  | Status | Not started | Status Date |  | Modified Due Date |  | J
5 | 3.3.5 | Interface to GANGA |  |  |  | DUE | 2004-09-30
| Description | Merge the current MC production & monitoring system into GANGA
| Metric | Prototype exists
| Risk and/or | Ganga exists
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
6 | 3.3.6 | Final GANGA Version |  |  |  | DUE | 2004-12-31
| Description | Document describing Monte Carlo monitoring and production with GANGA and public demonstration
| Metric | Document and demonstration
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
7
8
9

## 3.4
3.4
1 | 3.4.1 | Production of CMS Monte Carlo on testbed |  |  |  | DUE | 2002-09-30
| Description | The BOSS and IMPALA programs will be modified to produce the cmkin and cmsim parts
of the MC data samples using the grid testbeds. The data will be sent to the SE and
published in the replica catalogue using GDMP.
| Metric | 1TB of data produced in a Grid-like way from the UK for CMS data challenge.
| Risk and/or | CMS international MC production effort delayed.
| Dependency | Stable testbed. | [5 empty] | Link to PH GridPP6 talk (see P3)
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J | Also P3 and top of P5 of this link
2 | 3.4.2 | Prototype Regional Data-Centre |  |  |  | DUE | 2003-09-30
| Description | The RAL Tier-1 facilities will be used to store more than 10TB of CMS simulated data in flat files | [5 empty] | Click her for changeform
|  | and will act as a repository for the CMS collaboration worldwide. All data will be published in a | [5 empty] | Date put back 10 months because EDG
|  | replica catalogue via GDMP and made available worldwide. | [5 empty] | release was not adequate. This risk
| Metric | >10TB of data stored at RAL, published in a replica catalogue and available worldwide. | [5 empty] | was noted in the original definition
| Risk and/or | GDMP release is not adequate. Storage is not available. | [5 empty] | Link to PH GridPP6 talk (see P6)
| Dependency | Stable testbed; SE support; robust storage facilities; stable GDMP | [5 empty] | Link to more detailed email about delay
| Status | Complete | Status Date |  | Modified Due Date |  | J | GDMP = Grid Data Mirroring Package
See P2 and P3 of the link
3 | 3.4.3 | Initial Monitoring |  |  |  | DUE | 2002-11-30
| Description | Develop the use of R-GMA on top of BOSS.
| Metric | Demonstration
| Risk and/or | Stable testbed 1.2
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J | Link to PH GridPP6 talk (see P7+)
4 | 3.4.4 | CMS Monte Carlo Analysis |  |  |  | DUE | 2003-06-30
| Description | Provide a simple job submission framework for ORCA based reconstruction and analysis jobs.
Framework will allow simple job partitioning and aggregation of the output.
(IC)
| Metric | CMS users will be able to submit jobs to testbed with simple job partitioning and aggregation.
Demonstration in the UK.
| Risk and/or | Stable testbed; EDG WP1 implementation of job partitioning. EDG release
| Dependency | to ensure a consistent execution environment. | [5 empty] | LCG instead of EDG?
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J
5 | 3.4.5 | UK CMS Web Portal |  |  |  | DUE | 2003-09-30
| Description | Implementation of web portal for MC production and analysis
(IC)
| Metric | CMS users will be able to submit production and analysis jobs from UK via a web interface
| Risk and/or | Stable testbed.
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J | Pretty much done actually; link to GUIDO
6 | 3.4.6 | Integration of Object Persistency into UK production system |  |  |  | DUE | 2003-12-31
| Description | An important CMS milestone is the Integration of new persistent objects in CMS software.
The UK will need to install and test this development that will be based on the LCG
recommendations. (Bristol)
| Metric | CMS software runs in production mode using the LCG common LHC solution to persistent objects
Demonstation in the UK
| Risk and/or | LCG recommendations; adoption and implementation by CMS
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J | Will need to realign with LCG milestone in mar 04
7 | 3.4.7 | CMS Grid Status Document |  |  |  | DUE | 2003-12-31
| Description | Review of the current functionality of CMS grid-tools for production, monitoring and analysis.
The document will produce recommendations for future higher-level functionality with a focus on
data-handling, scheduling efficiency, and ease of use.
| Metric | Document describing current grid-tools and future emphasis.
| Risk and/or | CMS grid tools will have to have reached some level of maturity and be
| Dependency | widely deployed.
| Status | Not started | Status Date |  | Modified Due Date |  | J
8 | 3.4.8 | Toolkit to obtain Internal Monitoring data from CMS Applications |  |  |  | DUE | 2003-12-31
| Description | The CMS COBRA framework does not interact directly with the Grid. To enable internal monitoring, | [5 empty] | COBRA: Coherent OO base for reconstruction, analysis and simulation.
|  | services will need to be attached via a monitoring portal to BOSS. A simple CLI toolkit will be | [5 empty] | (NOT CORBA!)
provided for data analysis with some simple alarms.
| Metric | Toolkit provided for simple internal monitoring of CMS analysis jobs and a demonstration
application.
| Risk and/or | Stable testbed release. WP1 and WP3 monitoring tools.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 3.4.9 | Monitoring Analysis Tools |  |  |  | DUE | 2004-12-31
| Description | These tools are to provide a user interface to the monitoring data obtained from
instrumented CMS applications. They will allow real-time and off-line analysis.
| Metric | User interface to CMS monitoring data made available.
| Risk and/or | Stable testbed release. WP1 and WP3 monitoring tools.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
10 | 3.4.10 | CMS Grid |  |  |  | DUE | 2004-12-31
| Description | Final deployment of CMS grid enabled software incorporating functionality identified in 3.4.7.
| Metric | Deployment of CMS grid software in the UK.
User documentation and final report.
| Risk and/or | Stable testbed.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 3.5
3.5
1 | 3.5.1 | Preliminary Replica Catalog System |  |  |  | DUE | 2002-09-30
| Description | Design and implement a preliminary system that will provide each site with the location(s) of every
data file by adding one byte per file per site to the existing mySQL system
| Metric | Tool is demonstrated
Risk and/or
Dependency
| Status | Complete | Status Date | 2003-01-13 | Modified Due Date |  | J | This is the skimData referred to in this talk
2 | 3.5.2 | Prototype Job Creator and Submitter |  |  |  | DUE | 2002-12-31
| Description | Use the BaBar Preliminary Replica catalog system and the EDG resource broker to implement.
Creater produces jobs with data grouped according to availability at sites. Submitter (RB) receives
jobs with site specfied so has little flexibility at this point.
| Metric | Tool is demonstated
| Risk and/or | Replica catalogue system |  |  |  | 3.5.1
| Dependency | EDG Resource Broker (stable in current release).
| Status | Complete | Status Date | 2003-01-13 | Modified Due Date |  | J | This is the submitter referred to in this talk
3 | 3.5.3 | Assessment Document |  |  |  | DUE | 2003-06-30
| Description | Produce an assessment of the BaBarGrid system as it currently exists, including actual
experience and progress being made with the EDG system.
| Metric | Document available
| Risk and/or | Prototype Job Creator and Submitter |  |  |  | 3.5.2
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J | Waiting for Link from RB
4 | 3.5.4 | Production BaBarGrid |  |  |  | DUE | 2003-12-31
| Description | A production version of the previous tools 3.4.1 and 3.4.2 enabling BaBar users to run
jobs on any available data without specifying the site(s) to be used, and to retrieve merged output.
| Metric | Grid available for UK users.
| Risk and/or | Replica catalog |  |  |  | 3.5.1
| Dependency | Job submitter |  |  |  | 3.5.2
| Status | In Progress | Status Date |  | Modified Due Date |  | J
5 | 3.5.5 | Assessment of Production System |  |  |  | DUE | 2004-06-30
| Description | Assessment of the production system, including its popularity with BaBar users
| Metric | Document Produced
| Risk and/or | Production BaBarGrid |  |  |  | 3.5.4
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
6 | 3.5.6 | Final BaBar System |  |  |  | DUE | 2004-12-31
| Description | Tune, document and optimse the production system
| Metric | Document describing system
| Risk and/or | Production Grid |  |  |  | 3.5.4
| Dependency | Assessment document |  |  |  | 3.5.5
| Status | Not started | Status Date |  | Modified Due Date |  | J
7 | 3.5.7 | Persistent Data Policy |  |  |  | DUE | 2003-03-31 | Click her for changeform
| Description | Assess the requirements for persistent data in BaBarGrid in the light of the revised BaBar | [5 empty] | BaBar computing model was not presented in Sep
|  | computing model | [5 empty] | as planned but was delayed to December.
| Metric | Document available
Roger to put report on web. Email 28/4/03
| Risk and/or | BaBar computing model report (due Sep 2002)
Dependency
| Status | Complete | Status Date | 2003-01-13 | Original Due Date | 2002-12-31 | J

## 3.6
3.6
1 | 3.6.1 | Architecture Design and Technology Review |  |  |  | DUE | 2002-06-30
| Description | Document describing architecture to be used for the upgrade of SAM
Document reviewing current technology
| Metric | Documents produced
| Risk and/or | None |  |  |  |  | D0
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
2 | 3.6.2 | Prototype CDF-SAM Interface |  |  |  | DUE | 2002-06-30
| Description | A preliminary interface between the CDF analysis framework and SAM including a GUI for large
scale declaration of data-sets to SAM and an interface to the SAM data retrieval system.
| Metric | Demonstration of functionality on UK site.
Working CDF SAM stations at Glasgow/UCL etc.
| Risk and/or | None |  |  |  |  | CDF
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
3 | 3.6.3 | Phase-1 SAM Development |  |  |  | DUE | 2002-09-30
| Description | SAM modified to include GridFTP transport option; Condor-G job submission to a hand-chosen
remote site; monitoring information services.
| Metric | Demonstration of functionality
| Risk and/or | May be problems with interface to GSI. |  |  |  |  | D0
| Dependency | Depends on Condor-g deployment.
| Status | Complete | Status Date | 2003-01-13 | Modified Due Date |  | J
4 | 3.6.4 | Final CDF-SAM interface |  |  |  | DUE | 2002-12-31
| Description | Based upon prototype results, final design will be implemented.
| Metric | Demonstration of interface on UK site.
| Risk and/or | Depends on prototype. |  |  |  | 3.6.2 | CDF
Dependency
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J
5 | 3.6.5 | CDF Monte Carlo Production as a SAM Task. |  |  |  | DUE | 2003-10-01
| Description | Extend CDF use of SAM from simple file retrieval to fully integrated Monte Carlo production. | [5 empty] | Click here for changeform
Re-prioritorized according to CDF
plans. The 3.6.7 deliverable has been
| Metric | Demonstration of CDF Monte Carlo production using SAM in the UK | [5 empty] | bought forward and this one delayed.
| Risk and/or | Depends on completion of related work within the CDF collaboration to |  |  |  |  | CDF
| Dependency | allow communication with various databases (geometry, calibration, etc).
| Status | In Progress | Status Date | 2003-01-13 | Modified Due Date |  | J
6 | 3.6.6 | Prototype SAM Monte Carlo Production system using Resource Broker |  |  |  | DUE | 2003-03-31
| Description | Extension of SAM functionality to include use of resource broker. Will also include monitoring
services and request interface.
| Metric | Demonstration of SAM prototype with specified functionality in the UK.
| Risk and/or | Depends on D0 architecture definition |  |  |  | 3.6.1 | D0
| Dependency | and development of associated areas within D0
| Status | Complete | Status Date | 2003-04-23 | Modified Due Date |  | J | See this link also…
7 | 3.6.7 | Demonstration of CDF/SAM jobs moving to data. |  |  |  | DUE | 2003-03-31
| Description | Adaptation of SAM to move jobs to data as an option needs to be integrated into CDF framework.
| Metric | Demonstration of CDF/SAM jobs moving to data in the UK.
| Risk and/or | Depends on development of this SAM functionality by the core SAM team. |  |  |  |  | CDF
| Dependency | and the SAM Grid team
| Status | Complete | Status Date | 2003-01-17 | Modified Due Date |  | J | Link to GridPP web page news item
8 | 3.6.8 | Report on first year SAM/CDF Progress |  |  |  | DUE | 2003-06-30
| Description | A brief summary document that describes progress in the first year and highlights problems and
issues. This will be used to set/modify targets for the remainder of the project.
| Metric | Document produced
| Risk and/or | None |  |  |  |  | CDF
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J | NEED THIS LINK
9 | 3.6.9 | Pilot SAM Grid for D0 users. |  |  |  | DUE | 2003-12-01
| Description | Documentation and demonstration of a limited D0-grid based on SAM capable of providing a service | [5 empty] | Click here for changeform
|  | to 'intelligent users' in the UK. Functionality includes automated submission of Monte Carlo and | [5 empty] | Delayed by 2 months due to a change
|  | analysis jobs. | [5 empty] | in priorities within D0
| Metric | Documented demonstration.
| Risk and/or | Depends on much associated work with core SAM team and D0 |  |  |  |  | D0
| Dependency | collaboration.
| Status | Not started | Status Date |  | Modified Due Date |  | J
10 | 3.6.10 | Demonstration of SAM as a Data Handling System for CDF |  |  |  | DUE | 2003-12-31
| Description | Deliver SAM for use on CDF's central analysis facility as the data handling system.
| Metric | Demonstration of SAM for data handling in UK and Fermilab
| Risk and/or | Depends on formal adoption of SAM by CDF |  |  |  |  | CDF
| Dependency | Provision of sufficient CDF manpower
| Status | Complete | Status Date |  | Modified Due Date |  | J | According to Q9 report; awaiting confirmation
11 | 3.6.11 | Robust SAM-based grid service for D0 |  |  |  | DUE | 2004-09-30
| Description | Demonstration and documentation of a robust SAM-based service for significant D0 physics | [5 empty] | Click here for changeform
|  | production tasks suitable for use by general collaboration members. | [5 empty] | Delayed by 6 months due to a change
in priorities within D0
| Metric | Documented demonstration
| Risk and/or | Depends on development of SAM and D0 software and by formal |  |  |  |  | D0
| Dependency | acceptance by the D0 collaboration.
| Status | Not started | Status Date |  | Modified Due Date |  | J
12 | 3.6.12 | Final Report on SAM/CDF integration |  |  |  | DUE | 2004-12-31
| Description | A document on the final product for CDF. Issues addressed include the technical success of the
integration of SAM and the degree to which CDF has adopted this for data handling.
| Metric | Document
| Risk and/or | [5 empty] | CDF
| Dependency | [6 empty] | May change this to a milestone 9 months earlier that specifies
| Status | Not started | Status Date |  | Modified Due Date |  | J | work required in last 9 months.

## 3.7
3.7
1 | 3.7.1 | Develop XLM schema for lattice QCD calculations |  |  |  | DUE | 2002-06-30
| Description | Develop an XLM schema to define the format of the metadata documents for lattice QCD data files
| Metric | Schema defined.
Risk and/or
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
2 | 3.7.2 | Develop meta-data catalogue for simulation data |  |  |  | DUE | 2002-06-30
| Description | Develop and XML database server for storing and querying lattice QCD metadata. Access will be
via command-line tools.
| Metric | Demonstration of command line access to meta-data catalogue.
Risk and/or
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J | See end of talk linked to C20
3 | 3.7.3 | Develop browser for meta-data catalogue |  |  |  | DUE | 2002-09-30
| Description | Develop browser to allow users to query metadata catalogue. Brower will supply a single interface
to the metadata and ultimately the data.
| Metric | Demonstration of browser access to metadata catalogue.
| Risk and/or |  |  |  |  | 3.7.2 |  | Delayed to Dec-31 because they are early adopters of OGSA-DAI STUFF
| Dependency | [6 empty] | To be demonstrated at GridPP6
| Status | Complete | Status Date |  | Modified Due Date |  | J | See end of talk linked to C30
4 | 3.7.4 | Implement four-site data-storage and access |  |  |  | DUE | 2002-09-30 |  | 3.7.4 | Implement four-site data-storage and access |  |  |  | DUE | 2002-09-30
| Description | Deployment of a small grid using EG testbed release middleware, allowing members of UKQCD | [5 empty] | Click her for changeform | Description | Deployment of a small grid using EG testbed release middleware, allowing all members of UKQCD
|  | access to data at at least two if the four sites (via browser and/or line commands at this point). | [5 empty] | Old deliverable is here ---> |  | access to data at all four sites (via browser and/or line commands at this point).
Only 3 of the 4 sites are up and
| Metric | Users can access data in a site-transparent manner. | [5 empty] | running due to manpower | Metric | Users can access data in a site-transparent manner.
shortages.
| Risk and/or | Stable EDG middleware | [6 empty] | Risk and/or | Stable EDG middleware
| Dependency | [6 empty] | (See table on P2 of the link to C40) | Dependency
| Status | Complete | Status Date | 2003-04-23 | Modified Due Date |  | J | NOW FOUR SITES: 8/May/2003 | Status | In Progress | Status Date | 2003-01-22 | Modified Due Date |  | J
5 | 3.7.5 | Pilot job submission system |  |  |  | DUE | 2003-12-31
| Description | Pilot job submission system to access selected test nodes | [5 empty] | Click her for changeform
|  | submitted | [5 empty] | Click her for changeform2
UKQCD originally went for an
| Metric | Demonstration of functionality | [5 empty] | accellerated project by doubling
up staffing. Now revert to 1.0 FTE
| Risk and/or | [6 empty] | so time frame slips back a bit
Dependency
| Status | In Progress | Status Date | 2003-05-10 | Modified Due Date |  | J
6 | 3.7.6 | Full job submission system |  |  |  | DUE | 2004-06-01
| Description | Data access and job submission system across available UKQCD storage and compute resources | [5 empty] | Click her for changeform
Follows on from delay above
an reflects increased importance
| Metric | Demonstration of functionality | [5 empty] | of submission mechanism over
portal
| Risk and/or | Stable EDG release |  |  |  | 3.7.5
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 3.8
3.8
1 | 3.8.1 | One non-funded application has used UK testbed |  |  | DUE | 2002-09-30
Description
| Metric | One non-funded application has used UK testbed
Risk and/or
Dependency
| Status | Complete | Status Date | Modified Due Date |  | J | LISA jobs were run
2 | 3.8.2 | Two non-funded application have used testbed |  |  | DUE | 2003-09-30
Description
| Metric | Two non-funded application have used testbed
Risk and/or
Dependency
| Status | Complete | Status Date | Modified Due Date |  | J | MICE jobs were run: See Page-14 of the link
3 | 3.8.3 | Significant bids for resources by non-funded applications |  |  | DUE | 2004-12-31
| Description | There are significant bids for GridPP resources from applications that were not directly funded by
the GridPP programme.
| Metric | Amount of resources requested by non-funded applications
Risk and/or
Dependency
| Status | Not started | Status Date | Modified Due Date |  | J

## 4.1
4.1
1 | 4.1.1 | 2002 BaBar common fund rebate is agreed. |  |  |  | DUE | 2002-04-01
| Description | BaBar agrees that Tier-A hardware generates common-fund rebate
| Metric | Common fund rebate.
| Risk and/or | BaBar does not agree.
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
2 | 4.1.2 | New Tier-A hardware installed |  |  |  | DUE | 2002-10-01
| Description | New Tier-A hardware installed and demonstrated to meet requirements.
| Metric | Hardware is tested at full capacity and available for use.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | Link to final version of JG's OC report.
3 | 4.1.3 | BaBar Successfully use Tier-A Hardware |  |  |  | DUE | 2002-12-31
| Description | Tier-A hardware is successfully incorporated into BaBar production.
| Metric | BaBar using more than 80% of hardware reserved for its use.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | Link to final version of JG's OC report.
4 | 4.1.4 | 2003 BaBar common fund rebate is agreed. |  |  |  | DUE | 2003-04-01
| Description | BaBar agrees that new Tier-A hardware generates common-fund rebate
| Metric | Common fund rebate.
| Risk and/or | BaBar does not agree.
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
5 | 4.1.5 | 2003 Tier-A hardware installed |  |  |  | DUE | 2003-06-01
| Description | 2003 Tier-A hardware installed and demonstrated to meet requirements. | [5 empty] | Click here for changeform
Delay of 3 months
No serious consequence
| Metric | Hardware is tested at full capacity and available for use.
Risk and/or
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
6 | 4.1.6 | BaBar Successfully use Tier-A Hardware |  |  |  | DUE | 2003-09-30
| Description | Tier-A hardware is successfully incorporated into BaBar production.
| Metric | BaBar using more than 80% of hardware reserved for its use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
7 | 4.1.7 | 2004 BaBar common fund rebate is agreed. |  |  |  | DUE | 2004-03-31
| Description | BaBar agrees that new Tier-A hardware generates common-fund rebate
| Metric | Common fund rebate.
| Risk and/or | BaBar does not agree.
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
8 | 4.1.8 | New Tier-A hardware installed |  |  |  | DUE | 2004-09-30
| Description | New Tier-A hardware installed and demonstrated to meet requirements.
| Metric | Hardware is tested at full capacity and available for use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
9 | 4.1.9 | BaBar Successfully use Tier-A Hardware |  |  |  | DUE | 2004-12-31
| Description | Tier-A hardware is successfully incorporated into BaBar production.
| Metric | BaBar using more than 80% of hardware reserved for its use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.2
4.2
1 | 4.2.1 | 2002 Tier-1 hardware commissioned |  |  |  | DUE | 2002-10-01
| Description | Hardware installed and demonstrated to meet tender specifications
300 CPUs and 40TB of disk shared with BaBar.
| Metric | Purchase accepted
Hardware available for use.
| Risk and/or | [6 empty] | 312 CPU (156 dual) installed
| Dependency | [6 empty] | Link to final version of JG OC document
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | Some concern about some disks but issue resolved with vendor.
2 | 4.2.2 | Tier-1 Centre used. |  |  |  | DUE | 2002-12-31
| Description | Hardware should meet the needs (as far as possible) of the LHC experiments | [5 empty] | Due to the quantized nature of the data Challenges this was not
quite completed according to the due date or to the metric, but,
from January to May 2003 the LHC experiments used 77% of their
| Metric | LHC experiments use more than 80% of hardware nominally reserved for their use for | [5 empty] | resource allocation (nominally 30% of the hardware)
|  | substantial periods. | [5 empty] | See this link
| Risk and/or | [6 empty] | and this link
Dependency
| Status | Complete | Status Date | 2003-05-08 | Modified Due Date |  | J
3 | 4.2.3 | 2003 Tier-1 hardware commissioned |  |  |  | DUE | 2003-10-01
| Description | Hardware installed and demonstrated to meet tender specifications
| Metric | Purchase accepted
Hardware available for use.
Risk and/or
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
4 | 4.2.4 | Tier-1 Centre used. |  |  |  | DUE | 2003-12-31
| Description | Hardware should meet the needs (as far as possible) of the LHC experiments
| Metric | LHC experiments use more than 80% of hardware nominally reserved for their use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
5 | 4.2.5 | 2004 Tier-1 hardware commissioned |  |  |  | DUE | 2004-10-01
| Description | Hardware installed and demonstrated to meet tender specifications
| Metric | Purchase accepted
Hardware available for use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
6 | 4.2.6 | Tier-1 Centre used. |  |  |  | DUE | 2004-12-31
| Description | Hardware should meet the needs (as far as possible) of the LHC experiments
| Metric | LHC experiments use more than 80% of hardware nominally reserved for their use.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
7 | 4.2.7 | Tier-1 Centre meets target size. |  |  |  | DUE | 2004-12-31
| Description | Tier-1 Centre meets target size.
| Metric | Expect 2000 nodes and 500TB in the UK. Approximately 50% in Tier-1.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.3
4.3
1 | 4.3.1 | Tier-2 centre preliminary definition established |  |  |  | DUE | 2002-10-01
| Description | The role and structure of Tier-2 centres is currently being examined by an LCG group. GridPP will
consider this input in establishing a preliminary definition for UK Tier-2 centres.
| Metric | Document specifying Tier-2 centres
| Risk and/or | LCG report delayed
Dependency
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | Link to final version of SL OC document
2 | 4.3.2 | Location of UK Tier-2 centres established |  |  |  | DUE | 2003-01-01
| Description | GridPP plans to establish about 4 Tier-2 centres in the UK. Once the formal specification is made
discussions with likely candidates will begin with a goal of establishing the location of centres.
| Metric | Formal commitment (MOU?) by institutions to become Tier-2 centres for at least the remainder of the
current GridPP project.
| Risk and/or | Resources are not available at institutions or agreements not made. |  |  |  | 4.3.1
Dependency
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | Link to GridPP-6 talks
3 | 4.3.3 | Tier-2 architecture and development plan established |  |  |  | DUE | 2003-07-01
| Description | The identified Tier-2 centres will be engaged in the discussion of how the Tier-2 resources will
evolve to a level where the total UK tier-2 resources are similar to the UK Tier-1 resources.
Plans for both architecture and development are needed.
| Metric | Agreed plans with each Tier-2 centre on architecture and development over the following 2 years.
| Risk and/or | Tier-2 centres are unable to attract resources
Dependency
| Status | Complete | Status Date |  | Modified Due Date |  | J
4 | 4.3.4 | Tier-2 centers meet preliminary definition specification |  |  |  | DUE | 2003-10-01
| Description | Tier-2 centres are expected to have met at least the preliminary specifications.
| Metric | Tier-2 centres have resources to match agreed definition.
| Risk and/or |  |  |  |  | 4.3.1
| Dependency |  |  |  |  | 4.3.2
| Status | Not started | Status Date |  | Modified Due Date |  | J
5 | 4.3.5 | Tier-2 centers developed according to plan |  |  |  | DUE | 2004-12-01
| Description | By the end of the current GridPP project the Tier-2 centres should have developed according to the
plan established in 4.3.3
| Metric | Degree to which Tier-2 centres match planned level of resources.
| Risk and/or | Tier-2 centres fail to attract resources. |  |  |  | 4.3.3
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.4
4.4
1 | 4.4.1 | UK testbed is established |  |  |  | DUE | 2002-05-01
| Description | Initial UK testbed established usable by GridPP V0 Members.
| Metric | At least 5 members, a UK resource broker, and information hierarchy, and V0 server.
Simple jobs should run
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J | Link to Andy McNabs GridPP6 talk summary slide
2 | 4.4.2 | BaBar simulation or analysis demonstration |  |  |  | DUE | 2002-10-01
| Description | BaBar simulation or analysis demonstration on the UK testbed
| Metric | Successful submission and completion of BaBar jobs
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
3 | 4.4.3 | Core-sites part of EDG testbed |  |  |  | DUE | 2002-10-01
| Description | The UK testbed core-sites (i.e. with WP6 posts: RAL, ICSTM, Manchester, Bristol) should by this
time be part of the EDG testbed
| Metric | RAL, ICSTM, Manchester, and Bristol members of the EDG testbed.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-10-01 | Modified Due Date |  | J | Link to Andy McNabs GridPP6 talk summary slide
4 | 4.4.4 | GridPP Hetrogeneous Testbed demonstration |  |  |  | DUE | 2003-04-01 | Hetrogenous Testbed demonstration?
| Description | Demonstration that the UK testbed has grown to include a mixture of resources. | [5 empty] | LHCb can do this (? NB) 12/3/3
JetWeb and Guido? (JG) 12/3/3
| Metric | Demonstration of simple application running across heterogeneous resources such as EDG testbed | [5 empty] | Loads of machines in different parts of the county and a simple
|  | and dedicated BaBar resources (one off demonstration). | [5 empty] | job can run on many of them
Risk and/or
| Dependency | [6 empty] | JG: One off test showing no fundemental problem (GridPP VO plus resource broker should be sufficient)
| Status | Not started | Status Date |  | Modified Due Date |  | J | JG to assign task to one of the new people
5 | 4.4.5 | Tier-2 Centre Integration |  |  |  | DUE | 2003-10-01
| Description | By this time at least one Tier-2 centre should be part of the UK testbed
| Metric | Tier-2 centre is part of testbed
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J
6 | 4.4.6 | LCG Testbed |  |  |  | DUE | 2003-12-31
| Description | The UK will be part of the LCG approved test-bed
| Metric | UK is recognised by LCG as a member of test-bed
| Risk and/or | LCG testbed not developed
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.5
4.5
1 | 4.5.1 | Preliminary Rollout Plan Established |  |  |  | DUE | 2002-05-01
| Description | Initial planning for the Grid rollout in the UK is undertaken.
| Metric | Rollout plan presented to PMB
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
2 | 4.5.2 | Installation Instruction Set Tested |  |  |  | DUE | 2002-09-01
| Description | Preliminary instructions set for joining/using Grid should be tested on two category-2 sites.
| Metric | Tests completed on two sites.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 | Modified Due Date |  | J
3 | 4.5.3 | Grid Rolled Out to Category-2 Sites |  |  |  | DUE | 2003-04-01
| Description | All interested category-2 sites should now be involved.
| Metric | Involvement of all interested category-2 sites.
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | Link to map or news item
4 | 4.5.4 | Grid rolled out to category-3 (turn-key) users |  |  |  | DUE | 2004-10-01
| Description | By this time the UK Grid should be available to Turn-Key users according to the developed rollout
plan.
| Metric | Number of institutes in the UK engaged.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 4.6
4.6
1 | 4.6.1 | One LHC Experiment uses significant UK resources |  |  |  | DUE | 2002-09-30
| Description | At least one LHC Experiment should have used significant UK resources for a data challenge
| Metric | At least 1TB of data produced in the UK
Risk and/or
| Dependency | [6 empty] | CMS produced 1.2TB of reconstructed data (400k events)
| Status | Complete | Status Date | 2002-09-10 | Modified Due Date |  | J | The raw data produced was about 0.5TB
Link to final version of JGs OC document
2 | 4.6.2 | Two LHC Experiments using significant UK resources |  |  |  | DUE | 2003-03-30
| Description | At least two LHC experiments should be using significant UK resources for data challenges.
| Metric | At least 3TB of data produced in the UK in data challenges.
Risk and/or
| Dependency | [6 empty] | Atlas UK provide 19% or resources for phase-2 of their challenge
| Status | Complete | Status Date |  | Modified Due Date |  | J | Link to LHCb production map showing 48% of >40m events in UK
3 | 4.6.3 | Three LHC Experiments using significant UK resources |  |  |  | DUE | 2003-12-31
| Description | Three LHC experiments should be using significant UK resources for data challenges.
| Metric | At least 10 TB of data should have been produced in UK data challenges
At least 20TB of data should be stored and available to worldwide community through catalogue.
Risk and/or
Dependency
| Status | Not started | Status Date |  | Modified Due Date |  | J

## 5.1
5.1
1 | 5.1.1 | GGF Standards |  |  | DUE | on going
| Description | GridPP will make every effort to align with GGF standards in order to ensure interoperability
To help accomplish this GridPP members will attend GGF meetings.
| Metric | Number of GridPP members attending GGF meetings
| Current Total |  | 70
| Current Threshold |  | 62 | 30 per year (10 people at each of three meetings)
| Status | In Progress | Status Date | 2003-10-01 |  | J
2 | 5.1.2 | GGF Standards |  |  | DUE | on going
| Description | GridPP will make every effort to align with GGF standards in order to ensure interoperability
This will be assisted if GridPP members have formal roles in GGF.
| Metric | Number of GridPP members belonging to formal GGF groups.
| Current Total |  | 4
| Current Threshold |  | 1
| Status | Not started | Status Date | 2003-10-01 |  | J
3 | 5.1.3 | GGF Standards |  |  | DUE | on going
| Description | GridPP will make every effort to align with GGF standards in order to ensure interoperability
| Metric | Ultimately this is measured by the number of times GGF standards are broken by GridPP.
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 5.2
5.2
1 | 5.2.1 | Open Source Development |  |  | DUE | on going
| Description | GridPP hopes to contribute open source packages to the community
| Metric | Number of packages contributed to the open source community
| Current Total |  | 6
| Current Threshold |  | 2 | Two per year
| Status | In Progress | Status Date | 2002-09-11 |  | J
2 | 5.2.2 | Open Source Use |  |  | DUE | on going
| Description | GridPP will endeavor to use open source products where possible.
| Metric | Number of external packages used which are not open source.
| Current Total |  | -5
| Current Threshold |  | -5
| Status | Not started | Status Date | 2002-06-05 |  | J
3 | 5.2.3 | Open Source Conflict |  |  | DUE | on going
| Description | Number of times when an open source approach is not adhered to by GridPP
| Metric | Number of times when an open source approach is not adhered to by GridPP
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 5.3
5.3
1 | 5.3.1 | InterGrid |  |  | DUE | on going
| Description | GridPP will promote interoperability through the InterGrid project
To help accomplish this GridPP members will be part of the InterGrid technical board.
| Metric | Number of GridPP members of InterGrid Technical Board (HIJTB)
| Current Total |  | 1 |  |  |  | Pete Clarke
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2003-10-01 |  | J
2 | 5.3.2 | InterGrid |  |  | DUE | on going
| Description | GridPP will promote interoperability through the InterGrid project
To help accomplish this GridPP members will be part of the InterGrid Collaboration Board
| Metric | Number of GridPP members of InterGrid Collaboration Board (HICB)
| Current Total |  | 3 |  |  |  | Tony Doyle
| Current Threshold |  | 1 |  |  |  | Robin Middleton
| Status | Not started | Status Date | 2003-10-01 |  | J | Neil Gedders
3 | 5.3.3 | InterGrid |  |  | DUE | on going
| Description | A measure of success is how well GridPP manages to adhere to InterGrid agreements
| Metric | Number of times InterGrid agreements are broken by GridPP
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 5.4
5.4
1 | 5.4.1 | E-Science Centres |  |  | DUE | on going
| Description | A measure of the integration of GridPP with the UK e-Science centres is the number of GridPP
members belonging to the ETF
| Metric | Number of GridPP members of ETF
| Current Total |  | 4
| Current Threshold |  | 1
| Status | In Progress | Status Date | 2003-10-01 |  | J
2 | 5.4.2 | E-Science Centres |  |  | DUE | on going
| Description | A measure of the integration of GridPP with the UK e-Science centres is the number of GridPP
members belonging to the e-Science Centre Executive Boards.
| Metric | Number of GridPP members of e-Science Centre Executive Boards.
| Current Total |  | 2 |  |  |  | Tony Doyle
| Current Threshold |  | 1 |  |  |  | Andy Parker
| Status | Not started | Status Date | 2003-10-01 |  | J
3 | 5.4.3 | JISC |  |  | DUE | on going
Description
| Metric | The number of GridPP members belonging to JISC Technical Boards
| Current Total |  | 2
| Current Threshold |  | 1
| Status | Not started | Status Date | 2003-10-01 |  | J
4 | 5.4.4 | JISC |  |  | DUE | on going
Description
| Metric | The number of GridPP members belonging to JISC Executive Boards
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2003-10-01 |  | J
5 | 5.4.5 | e-Science Support Tools |  |  | DUE | on going
Description
| Metric | The number of e-Science supported tools relevent to GridPP that are not adopted by GridPP.
| Current Total |  | 0
| Current Threshold |  | 0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 6.1
6.1
1 | 6.1.1 | GridPP Presentations |  |  | DUE | on going
| Description | Dissemination of GridPP work via presentations to other physicists, other scientists, industry,
or the general public.
| Metric | Number of presentations
| Current Total |  | 37
| Current Threshold |  | 25 | Once a month
| Status | In Progress | Status Date | 2003-10-01 |  | J
2 | 6.1.2 | GridPP Workshops |  |  | DUE | on going
| Description | Dissemination of GridPP work via technical workshops.
| Metric | Number of workshops
| Current Total |  | 7
| Current Threshold |  | 8 | Four per year
| Status | In Progress | Status Date | 2003-10-01 |  | J
3 | 6.1.3 | GridPP Demonstrations |  |  | DUE | on going
| Description | Dissemination of GridPP work via demonstrations
| Metric | Number of demonstrations
| Current Total |  | 12
| Current Threshold |  | 8 | Four per year
| Status | In Progress | Status Date | 2003-10-01 |  | J
4 | 6.1.4 | GridPP Posters |  |  | DUE | on going
| Description | Dissemination of GridPP work via posters
| Metric | Number of posters
| Current Total |  | 17
| Current Threshold |  | 12 | Six per year
| Status | In Progress | Status Date | 2003-10-01 |  | J
5 | 6.1.5 | GridPP Publications |  |  | DUE | on going
| Description | Dissemination of GridPP by publications (includes extended abstracts)
| Metric | Number of publications
| Current Total |  | 84
| Current Threshold |  | 20 | Ten per year
| Status | In Progress | Status Date | 2003-10-01 |  | J

## 6.2
6.2
1 | 6.2.1 | GridPP Representation at related events |  |  | DUE | on going
| Description | To promote communication, GridPP members will attend related events.
| Metric | Number of attendances
| Current Total |  | 163
| Current Threshold |  | 108 | 1 per week
| Status | In Progress | Status Date | 2003-10-01 |  | J
2 | 6.2.2 | GridPP Involvement with e-Science Centres |  |  | DUE | on going
| Description | To promote communication, GridPP will endeavor to keep the e-Science centres involved by
actively seeking contact.
| Metric | Number of interactions
| Current Total |  | 17
| Current Threshold |  | 20 | Two per year for the 5 centres closely associated with GridPP
| Status | In Progress | Status Date | 2003-10-01 |  | J
3 | 6.2.3 | GridPP Membership of Related Projects |  |  | DUE | on going
| Description | To promote the work of GridPP, members will belong to related projects and will keep these projects
up to date with the work of GridPP
| Metric | Number of members of related projects
| Current Total |  | 27
| Current Threshold |  | 12 | (Depends on number of related projects)
| Status | In Progress | Status Date | 2003-10-01 |  | J

## 6.3
6.3
1 | 6.3.1 | External use of GridPP Products |  |  | DUE | on going
| Description | Engagement of the community can be measured by the number of non-GridPP funded groups
who make use of GridPP middleware, or technical assistance.
| Metric | Number of External Groups who use GridPP Middleware
| Current Total |  | 3
| Current Threshold |  | 2 | One per year
| Status | In Progress | Status Date | 2003-10-01 |  | J
2 | 6.3.2 | External use of GridPP Infrastructure |  |  | DUE | on going
| Description | Engagement of the community can be measured by the number of non-GridPP funded groups
who make use of the GridPP infrastructure.
| Metric | Number of External Groups who use GridPP Hardware
| Current Total |  | 3
| Current Threshold |  | 2 | One per year
| Status | In Progress | Status Date | 2003-10-01 |  | J
3 | 6.3.3 | Press Articles |  |  | DUE | on going
| Description | The engagement of outside interest may be measured by the number of articles referencing GridPP.
| Metric | Number of articles in the scientific or general press.
| Current Total |  | 4
| Current Threshold |  | 2 | One per year
| Status | In Progress | Status Date | 2003-10-01 |  | J
4 | 6.3.4 | GridPP Web-site Hits |  |  | DUE | on going
| Description | The external interest in GridPP can be measured by counting the number of hits on the GridPP
website from external sources.
| Metric | Web index (hits divided into various catagories then divided by scaling factor)
| Current Total |  | 171
| Current Threshold |  | 50
| Status | In Progress | Status Date | 2003-10-01 |  | J

## 7.1
7.1
1 | 7.1.1 | Resource Deployment by Area |  |  | DUE | on going
| Description | The fraction of resources deployed according to current planning is a measure of effective
resource management
| Metric | Fraction deployed according to plan
| Current Total |  | 95.53% |  |  |  | Underspend of £0.09m at RAL in FY02
| Current Threshold |  | 95%
| Status | In Progress | Status Date | 2002-06-05 |  | J
2 | 7.1.2 | Missing Effort |  |  | DUE | on going
| Description | Number of posts that are not presently filled
| Metric | Number of posts that are not presently filled
| Current Total |  | -1
| Current Threshold |  | -2 |  |  |  | CDF post at Glasgow
| Status | Not started | Status Date | 2002-10-01 |  | J
3 | 7.1.3 | Hardware Delays |  |  | DUE | on going
| Description | Any delay in hardware purchases beyond planned schedule is a measure of how effectively
the process is managed.
| Metric | Number of months delay
| Current Total |  | -3
| Current Threshold |  | -3
| Status | Not started | Status Date | 2002-06-05 |  | J
4 | 7.1.4 | Travel Budget |  |  | DUE | on going
| Description | The match between the travel spend and the travel budget reflects on how well the travel budget
is managed.
| Metric | Travel overspend(£K)
(Overspend entered as negative number; underspend as positive number)
| Current Total |  | 37 | Only really known at end of FY so we will enter
| Current Threshold |  | -5 | projected overspend given current information
| Status | Not started | Status Date | 2002-06-05 |  | J

## 7.2
7.2
1 | 7.2.1 | Monitoring Mechanism |  |  | DUE | 2002-05-01
| Description | An easy to use mechanism for monitoring effort in the project on a quarterly basis is required
| Metric | Development of Mechanism
Risk and/or
| Dependency | [5 empty] | See next deliverable
| Status | Complete | Status Date | 2002-06-05 |  | J
2 | 7.2.2 | Monitoring Implementation |  |  | DUE | 2002-10-15
| Description | The monitoring mechanism needs to be implemented and run.
| Metric | First full run of monitoring mechanism completed.
Risk and/or
Dependency
| Status | Complete | Status Date | 2001-10-01 |  | J
3 | 7.2.3 | Monitoring information processing |  |  | DUE | 2002-12-15
| Description | A semi-automated mechanism for processing the monitoring information needs to be developed
Link to OC resource report May03 that has tables
for both EDG and Applications that are generated
| Metric | Development of processing system |  |  |  |  | from this processing system
Risk and/or
Dependency
| Status | Complete | Status Date | 2002-06-05 |  | J

## 7.3
7.3
1 | 7.3.1 | Non GridPP-funded Effort |  |  | DUE | on going
| Description | UK effort on GridPP (or EDG within the UK context) not funded by GridPP (or the EU).
| Metric | Amount of effort in last period (integral number of quarters between OC meetings) - Man Months
| Current Total |  | 151.5 | Sum of Q6-9
| Current Threshold |  | 69.55 | Set at 25% of GridPP funded effort
| Status | In Progress | Status Date | 2003-05-10 |  | J
2 | 7.3.2 | Non-GridPP-funded resources at Tier-2 Centres |  |  | DUE | on going
| Description | The resources (hardware and posts) at Tier-2 Centres not funded by GridPP.
Metric
| Current Hardware Total |  | 1140000 | Current Number of FTE Total | 0
| Current Threshold |  | 0 | Current Threshold | 0
| Status | In Progress | Status Date | 2002-06-05 |  | J | Need to split this into two metrics.
3 | 7.3.3 | Other non GridPP-funded resources in the UK |  |  | DUE | on going
| Description | Other hardware resources in the UK dedicated to GridPP usage.
| Metric | Hardware value (purchase cost).
| Current Total |  | 424000 |  |  |  | Pre-Tier-1/A RAL hardware
| Current Threshold |  | 0
| Status | In Progress | Status Date | 2002-06-05 |  | J
4 | 7.3.4 | Additional funding Opportunities |  |  | DUE | on going
| Description | The extension of GridPP due to new funding initiatives such as SR2002 or FW-VI
| Metric | Value of additional funding
| Current Total |  | £0
| Current Threshold |  | £0
| Status | Not started | Status Date | 2002-06-05 |  | J

## 6.1.1
6.1.1 | Number of GridPP Presentations
Total: | 37
Count | Category
11 | Overviews
9 | Data Storage Management
1 | Configuration Management
0 | Workload Management
2 | Information & Monitoring
2 | Security
10 | Applications
0 | Networking
2 | Grid Infrastructure
Note since 5/11/03 individual talks are no longer stored here.
You can access them on the GridPP Website:
GridPP Talks

## 6.1.2
6.1.2 | Number of Technical Workshops
Total: | 7
Count | Title | Venue | Date
1 | Technical Workshop | Coseners | 2003-02-24
1 | GridPP - ETF Joint Meeting | RAL | 2002-05-28
1 | ATLAS LHCb Joint Workshop | Coseners | 2002-05-22
1 | AstroGrid - GridPP Liaison | UCL | 2002-05-02
1 | LCFG/EDG Synchronization Workshop | Edinburgh | 2002-04-30
1 | Tutorial session at Sysman Meeting | RAL | 2002-04-22
1 | Application Builders Teach In | RAL | 2002-01-31

## 6.1.3
6.1.3 | Number of GridPP Demonstrations
Total | 12
Count | Title | Venue | Date
1 | Guido | All Hands Meeting | 2003-09-02
1 | R-GMA | All Hands Meeting | 2003-09-02
1 | SAM Grid | All Hands Meeting | 2003-09-02
1 | Guido | LeSc Open Day | 2003-04-08
1 | R-GMA | LeSc Open Day | 2003-04-08
1 | GridSite, GACL and SlashGrid: Giving Grid Security to Web and File Applications | All Hands Meeting | 2002-09-02
1 | Studying Dynamic Grid Optimisation Algorithms for File Replication | All Hands Meeting | 2002-09-02
1 | Demonstration of Production Monte Carlo simulated data of the CMS Experiment using the EU DataGrid Testbed | All Hands Meeting | 2002-09-02
1 | Building the Grid for Babar | DTI | 2002-06-25
1 | Exploiting the Grid to Simulate and Design the LHCb Experiment | NeSC Opening | 2002-04-25
1 | Building the Grid for Babar | NeSC Opening | 2002-04-25
1 | Dynamic Grid Optimisation | NeSc Opening | 2002-04-25

## 6.1.4
6.1.4 | Number of GridPP Posters
Total: | 17
Count | Title
1 | Security
1 | GridPP Testbed
1 | UK Grid Simulation with OptorSim
1 | ATLAS and GridPP
1 | Relational Grid Monitoring Architecture
1 | The Grid
1 | From Web to Grid - Building the Next IT Revolution
1 | Studying Dynamic Grid Optimisation Algorithms for File Replication
1 | SAMGrid - enabling full function Grid Computing
1 | PetaBytes of Data from CMS
1 | Enabling Access to Mass Stroage Systems
1 | Computing Grid Applications for the ATLAS LHC Experiment and Beyond
1 | Exploiting the Grid to Simulate and Design the LHCb Experiment
1 | Building the Grid for BaBar
1 | Dynamic Grid Optimisation and ScotGrid
1 | European DataGrid Middleware and the Tier 1/A Centre
1 | From Web to Grid - Building the Next IT Revolution

## 6.1.5
6.1.5 | Number of GridPP Publications
Total: | 84
Count | Category
9 | Overviews
17 | Data Storage Management
2 | Configuration Management
2 | Workload Management
8 | Information & Monitoring
7 | Security
34 | Applications
4 | Networking
1 | Grid Infrastructure
Note since 5/11/03 individual papers are no longer stored here.
You can access them on the GridPP Website:
GridPP Papers

## 6.2.1
6.2.1 | Number of Attendances at Related Events
Total: | 163
Count | Event | Date
2 | NeSC Glasgow Opening | 2003-09-17
21 | e-Science All Hands Meeting, Nottingham | 2003-09-02
4 | Core Programme Town Meeting | 2003-05-14
8 | LeSC Open Day, London | 2003-04-08
1 | 1st European AcrossGrids Conference | 2003-02-13
4 | PFLDnet Workshop CERN | 2003-02-03
1 | UK Grid Security Workshop - National e-Science Centre, Edinburgh, Scotland | 2003-12-05
1 | Meeting with Radio Astronomer with Dante and NRNs, Amsterdam | 2003-01-15
8 | LeSC Open Day, London | 2003-04-08
1 | GridWeaver meeting, HP Labs, Bristol | 2002-09-25
19 | e-Science All Hands Meeting, Sheffield | 2002-09-02
3 | Ministerial briefing on e-science, DTI | 2002-06-25
1 | UK Core e-Science Programme Security Task Force | 2002-05-30
11 | NeSC Opening | 2002-04-25
5 | UK Grid Roadmap Meeting, London | 2002-04-18
3 | EDG/Globus co-ordination workshop, Argonne, USA | 2001-03-01
5.1.1 | Number of GridPP members attending GGF meetings
Total: | 70
Count | Event | Date
4 | GGF9 Chicago, USA | 2003-10-05
8 | GGF8 Seattle, USA | 2003-06-24
4 | GGF7 Tokyo, Japan | 2003-03-04
6 | GGF6 Chicago, USA | 2003-10-14
27 | GGF5 Edinburgh, Scotland | 2002-07-22
6 | GGF4 Toronto, Canada | 2002-02-17
15 | GGF3 Rome, Italy | 2001-10-07

## 6.2.2
6.2.2 | Number of Interactions with e-Science centres
Total: | 17
Count | Interaction | Person(s) | e-Science Centre | Date
1 | 8th GridPP Collaboration Meeting | All | Oxford | 2003-06-30
1 | Discussion with Mike Giles of OeSC | Steve Lloyd | Oxford | 2003-03-24
1 | 6th GridPP Collaboration Meeting | All | CLRC | 2003-01-30
1 | 5th GridPP Collaboration Meeting | All | London | 2002-09-02
1 | 4th GridPP Collaboration Meeting | All | Manchester | 2002-05-09
1 | Discussions with Oxford HEP, GridPP, OeSC | Steve Lloyd | Oxford | 2002-03-07
1 | 3rd GridPP Collaboration Meeting | All | Cambridge | 2002-02-14
9 | Letter to all e-Science Directors | Steve Lloyd | All | 2002-01-25
1 | 2nd GridPP Collaboration Meeting | All | NeSC | 2001-11-05

## 6.2.3
6.2.3 | GridPP Membership of Related Projects
Total: | 27
Count | Project or Organisation | Members
0
3 | DataTAG | Pete Clarke | Richard Hughes-Jones | Peter van Santen
3 | EDG Working Group Leaders | Steve Fisher (WP3) | John Gordon (WP5) | Frank Harris (WP8)
1 | LCG PEB | Tony Doyle
2 | LCG SC2 | NickBrook | John Gordon
1 | LCG Security Group Leader | Dave Kelsey
1 | LCG Grid Development Board | John Gordon | Norman McCubbin | Dave Kelsey
5.1.2 | Number of GridPP members in charge of formal GGF Working Groups
Total: | 4
Count | Project or Organisation | Members
0
1 | Authorization framewords and mechanisms | Andrew McNab
0 | OGSA Authorisation Working Group | Andrew McNab
1 | Network Measurements Working Group | Richard Hughes-Jones
1 | Relational Grid Information Services Research Group | Steve Fisher
1 | GGF Steering Group/Data Area Director | Pete Clarke
5.3.1 | Number of GridPP members of InterGrid Technical Board (HIJTB)
Total: | 1
Count | Project or Organisation | Members
0
1 | HIJTB | Pete Clarke
5.3.2 | Number of GridPP members of InterGrid Collaboration Board (HIJCB)
Total: | 3
Count | Project or Organisation | Members
3 | HICB | Tony Doyle | Robin Middleton | Neil Geddes
5.4.1 | Number of GridPP members of e-Science Centre Technical Boards.
Total: | 4
Count | Project or Organisation | Members
0
4 | Grid Engineering Task Force | Andrew Sansum | Jens Jensen | Andy Parker | Andrew McNab
5.4.2 | Number of GridPP members of e-Science Centre Executive Boards.
Total: | 2
Count | Project or Organisation | Members
0
1 | CeSC Director | Andy Parker
1 | NeSC Board | Tony Doyle
5.4.3 | Number of GridPP members belonging to JISC Technical Boards
Total: | 2
Count | Project or Organisation | Members
0
1 | JISC JCSR | Tony Doyle
1 | JISC JCN | Pete Clarke
5.4.4 | Number of GridPP members belonging to JISC Executive Boards
Total: | 0
Count | Project or Organisation | Members
0

## 6.3.1
6.3.1 | Number of External Groups who use GridPP Middleware
Total: | 3
Count | Group | Details
1 | MICE Muon Ionisation Cooling Experiment | Monte Carlo Production
1 | JetWeb | QCD Structure Function Calculations
1 | LISA/STEP Gravitational Wave Experiment | GEANT4 Monte Carlo Production

## 6.3.2
6.3.2 | Number of External Groups who use GridPP Hardware
Total: | 3
Count | Group | Details
1 | MICE Muon Ionisation Cooling Experiment | Monte Carlo Production
1 | JetWeb | QCD Structure Function Calculations
1 | LISA/STEP Gravitational Wave Experiment | GEANT4 Monte Carlo Production

## 6.3.3
6.3.3 | Number of Press Articles about GridPP
Total: | 4
Count | Title | Publication | Date
1 | Building the next IT revolution | Physics World | 2003-10-01
1 | From Web to Grid | Public Service Review: Central Government | Spring 2003
1 | From Web to Grid | Public Service Review: Department of Trade and Industry | Winter 2003
1 | From Web to Grid - Building the next IT Revolution | Wissenschafts Management, Zeitung fur Innovation, Special edition e-Science | 2002-09-01

## 6.3.4
6.3.4 | GridPP Website Hit Index
Total: | 171 | 2003-11-05
Count | Category | Number
45 | Total page requests (10,000s) | 446426
4 | Number of distinct hosts served (10,000s) | 41673
58 | Distinct files requested (1,000s) | 58395
7 | Referrals from www.google.com (1,000s) | 6703 | Note: This has not been updated as it is no longer available in the statistics
57 | Resolved .com requests (10,000s) | 566901